## AI
Project | Project Name | Source | IN | Action Item | Comments | Waiting for | Bill | Type | Deadline | Plan Date | Plan (hrs) | Actual (hrs) | OUT | Done
1569 | International Hydraulics |  | 2017-01-02 | p10-16 |  |  | billed |  |  | 2017-01-17 |  |  | 2017-01-17 | Done
1569 | International Hydraulics |  | 2017-01-11 | p10-21 (2) |  |  | billed |  |  | 2017-01-17 |  |  | 2017-01-17 | Done
1610 | UNT HSC Child Care |  | 2017-01-19 | p10-26 |  |  | billed |  |  | 2017-01-26 |  |  | 2017-01-26 | Done
1610 | UNT HSC Child Care |  | 2017-01-24 | p10-27 |  |  | billed |  |  | 2017-01-26 |  |  | 2017-01-26 | Done
1580 | Rental One - Denton |  | 2017-01-24 | p10-26 | Completed on Rev 1 |  | billed |  |  | 2017-01-28 |  |  | 2017-01-28 | Done
1421 | KXAS Remodel |  | 2017-01-03 | p10-16 | Transferred to DesignCriteria sheet |  | billed |  |  | 2017-01-30 |  |  | 2017-01-30 | Done
1591 | JPS 3rd Floor OR Renovation |  | 2017-01-03 | p10-16 | Transferred to DesignCriteria sheet |  | billed |  |  | 2017-01-30 |  |  | 2017-01-30 | Done
1592 | Deer Park Animal Shelter |  | 2017-01-05 | Add TP-2 to design |  |  | billed |  |  | 2017-01-30 |  |  | 2017-01-30 | Done
1594 | Pflugerville AS |  | 2017-01-03 | p10-16 | Wait for implementation. 1/10/17 |  | billed |  |  | 2017-01-30 |  |  | 2017-01-30 | Done
1591 | JPS 3rd Floor OR Renovation |  | 2017-01-04 | p10-16 | Transferred to DesignCriteria sheet |  | billed |  |  | 2017-01-30 |  |  | 2017-01-30 | Done
1591 | JPS 3rd Floor OR Renovation |  | 2017-01-10 | p10-19 | Transferred to DesignCriteria sheet |  | billed |  |  | 2017-01-30 |  |  | 2017-01-30 | Done
1581 | Crescent Schools |  | 2017-01-10 | p10-20 | Superceded |  | billed |  |  | 2017-01-30 |  |  | 2017-01-30 | Done
1594 | Pflugerville AS |  | 2017-01-10 | p10-21 | Transferred to DesignCriteria sheet |  | billed |  |  | 2017-01-30 |  |  | 2017-01-30 | Done
1581 | Crescent Schools |  | 2017-01-10 | p10-21 | Transferred to DesignCriteria sheet |  | billed |  |  | 2017-01-30 |  |  | 2017-01-30 | Done
1592 | Deer Park Animal Shelter |  | 2017-01-18 | COMCheck |  |  | billed |  |  | 2017-01-30 |  |  | 2017-01-30 | Done
1592 | Deer Park Animal Shelter |  | 2017-01-18 | Add EWC |  |  | billed |  |  | 2017-01-30 |  |  | 2017-01-30 | Done
1592 | Deer Park Animal Shelter |  | 2017-01-18 | Add Trap primers in 3 locations. P10-25 |  |  | billed |  |  | 2017-01-30 |  |  | 2017-01-30 | Done
1392 | UNT Clark Bakery |  | 2017-01-18 | p10-25 | Transferred to DesignCriteria sheet |  | billed |  |  | 2017-01-30 |  |  | 2017-01-30 | Done
1581 | Crescent Schools |  | 2017-01-09 | p10-19 | Done |  | billed |  |  | 2017-01-30 |  |  | 2017-01-30 | Done
1594 | Pflugerville AS |  | 2017-01-24 | p10-26 | Transferred to DesignCriteria sheet |  | billed |  |  | 2017-01-30 |  |  | 2017-01-30 | Done
1592 | Deer Park Animal Shelter |  | 2017-01-24 | p10-27 |  |  | billed |  |  | 2017-01-30 |  |  | 2017-01-30 | Done
1592 | Deer Park Animal Shelter |  | 2017-02-01 | Utility Coordination | 2/1 Called and left message p10-34 |  | billed |  |  | 2017-02-15 |  |  | 2017-02-15 | Done
1538 | UNT Coliseum Concourse | p10-42 | 2017-02-14 | p10-42 |  |  | billed |  |  | 2017-02-15 |  |  | 2017-02-15 | Done
1559 | Southlake MOB Shell |  | 2017-02-01 | Item 10 on city comments | 2/1 sent email to City |  | billed |  |  | 2017-02-16 |  |  | 2017-02-16 | Done
1594 | Pflugerville AS |  | 2017-02-01 | Utility Coordination | 2/1 requested address p10-34 |  | billed |  |  | 2017-02-17 |  |  | 2017-02-17 | Done
1538 | UNT Coliseum Concourse |  | 2017-02-21 | Concourse LTG layout |  |  | billed |  |  | 2017-02-23 | 2 | 2 | 2017-02-23 | Done
1538 | UNT Coliseum Concourse |  |  | Restroom LTG layout |  |  | billed |  |  | 2017-02-23 | 1 | 2 | 2017-02-23 | Done
1538 | UNT Coliseum Concourse |  |  | Office LTG layout |  |  | billed |  |  | 2017-02-23 | 1 | 2 | 2017-02-23 | Done
1538 | UNT Coliseum Concourse |  |  | Office LTG controls |  |  | billed |  |  | 2017-02-23 | 1 | 2 | 2017-02-23 | Done
1538 | UNT Coliseum Concourse |  |  | Office PWR |  |  | billed |  |  | 2017-02-23 | 1 | 2 | 2017-02-23 | Done
1627 | Blo Blow Dry Bar |  | 2017-02-25 | MP Proposal |  |  | billed | 1 |  | 2017-02-25 | 1 | 0.5 | 2017-02-25 | Done
1570 | Forney MOB Tenant Improvement | Final Comments - Gas Generator | 2017-02-25 | LTG Submittal |  |  | billed | 2 |  | 2017-02-25 | 1 | 0.5 | 2017-02-25 | Done
1628 | Machine House |  | 2017-02-25 | Proposal |  |  | billed | 3 |  | 2017-02-25 | 1 | 0.5 | 2017-02-25 | Done
1627 | Blo Blow Dry Bar |  | 2017-02-25 | Review Set |  |  | billed | 4 |  | 2017-02-25 | 3 | 3 | 2017-02-27 | Done
1392 | UNT Clark Bakery | p10-48 | 2017-02-25 | Retarder Feed mismatch issue | Final Comments - Gas Generator | 2/25 Debbie to confirm voltage | billed |  |  | 2017-02-26 |  |  | 2017-03-13 | Done
1392 | UNT Clark Bakery | p10-49 | 2017-02-25 | Chuncker Feed mistmatch issue |  |  | billed | 1 |  | 2017-02-27 | 1 | 1 | 2017-02-27 | Done
1617 | Werner Enterprises Laredo |  | 2017-02-25 | p10-49 |  |  | billed | 2 |  | 2017-02-27 | 2 | 2 | 2017-02-27 | Done
MKT | Marketing |  | 2017-02-25 | Form 330 to Patricia |  |  | billed | 3 |  | 2017-02-27 | 1 | 1 | 2017-02-28 | Done
1416 | DCCCD Eastfield Generator | p10-49 | 2017-02-27 | Pipeline / Arcadia |  |  | billed | 4 |  | 2017-02-27 |  |  | 2017-02-28 | Done
1617 | Werner Enterprises Laredo |  | 2017-02-28 | IFR |  |  | billed |  |  | 2017-02-28 | 5 | 5 | 2017-02-28 | Done
OPS | Operations |  | 2017-02-23 | Talk to Melissa about prof liability |  |  | billed | 6 |  | 2017-03-01 | 1 | 1 | 2017-03-01 | Done
1392 | UNT Clark Bakery |  | 2017-02-28 | Site Visit |  |  | billed |  |  | 2017-03-02 | 3 | 3 | 2017-03-02 | Done
1581 | Crescent Schools |  | 2017-02-28 | Set up site plans |  |  | billed |  |  | 2017-03-03 | 2 | 2 | 2017-03-03 | Done
1592 | Deer Park Animal Shelter | Pipeline / Arcadia | 2017-02-25 | Final Comments - Gas Generator | Need to answer the "?" on plans |  | billed | 5 |  | 2017-03-06 | 2 | 2 | 2017-03-07 | Done
1538 | UNT Coliseum Concourse |  | 2017-03-06 | DD Meeting |  |  | billed |  |  | 2017-03-06 | 5 | 5 | 2017-03-06 | Done
1610 | UNT HSC Child Care |  | 2017-02-09 | Addendum | 3/3 - Revision 2 2/9 Need date |  | billed |  |  | 2017-03-07 | 0 | 0 | 2017-03-07 | Done
1610 | UNT HSC Child Care |  | 2017-03-06 | Revision 2 |  |  | billed |  |  | 2017-03-07 | 2 | 2 | 2017-03-07 | Done
1587 | Rental One Willow Park |  | 2017-03-06 | Site Visit |  |  | billed |  |  | 2017-03-07 | 2 | 2 | 2017-03-07 | Done
1592 | Deer Park Animal Shelter |  | 2017-03-06 | IFC |  |  | billed |  |  | 2017-03-07 | 2 | 2 | 2017-03-07 | Done
ops | Operations |  | 2017-03-07 | Invoicing |  |  | billed |  |  | 2017-03-07 | 1 | 1 | 2017-03-07 | Done
1416 | DCCCD Eastfield Generator |  | 2017-03-07 | Address bid questions |  |  | billed |  |  | 2017-03-08 | 2 | 1 | 2017-03-08 | Done
1416 | DCCCD Eastfield Generator | Issue IFR | 2017-03-07 | Address bid questions |  |  | billed |  |  | 2017-03-08 | 1 | 1 | 2017-03-08 | Done
1416 | DCCCD Eastfield Generator |  | 2017-03-08 | Revision 1 |  |  | billed | 1 |  | 2017-03-09 | 2 | 2 | 2017-03-09 | Done
1587 | Rental One Willow Park |  | 2017-03-07 | IFR |  |  | billed | 2 |  | 2017-03-09 | 2 | 2 | 2017-03-09 | Done
1392 | UNT Clark Bakery |  | 2017-03-08 | Set up drawings |  |  | billed | 3 |  | 2017-03-09 | 2 | 2 | 2017-03-09 | Done
1633 | Car Customizing Co. Event Center |  | 2017-03-09 | Proposal |  |  | billed |  |  | 2017-03-09 | 1 | 1 | 2017-03-09 | Done
1634 | Dalrock Crossing |  | 2017-03-09 | Proposal |  |  | billed |  |  | 2017-03-09 | 1 | 1 | 2017-03-09 | Done
1392 | UNT Clark Bakery |  | 2017-03-10 | Power and Lighting |  |  | billed |  |  | 2017-03-10 | 4 | 4 | 2017-03-10 | Done
1621 | The Creek Church Phase II |  | 2017-03-08 | Set up drawings |  |  | billed | 4 |  | 2017-03-11 | 2 | 2 | 2017-03-11 | Done
1392 | UNT Clark Bakery |  | 2017-03-10 | Finish IFR |  |  | billed |  |  | 2017-03-11 | 8 | 6 | 2017-03-11 | Done
1621 | The Creek Church Phase II |  | 2017-03-10 | DD Set |  |  | billed |  |  | 2017-03-12 | 4 | 4 | 2017-03-12 | Done
1632 | Upper Trinity Conservation | E170307a | 2017-03-07 | Proposal | Issue IFR |  | billed |  |  | 2017-03-13 | 1 | 1 | 2017-03-13 | Done
1392 | UNT Clark Bakery |  | 2017-03-13 | Issue IFR |  |  | billed |  |  | 2017-03-13 | 2 | 2 | 2017-03-13 | Done
1621 | The Creek Church Phase II |  | 2017-03-13 | Issue DD Set |  |  | billed |  |  | 2017-03-13 | 2 | 2 | 2017-03-13 | Done
1538 | UNT Coliseum Concourse |  | 2017-03-13 | CC Mtg |  |  | billed |  |  | 2017-03-13 | 1 | 1 | 2017-03-13 | Done
1635 | Camp Bow Wow | Seal Projects | 2017-03-14 | Proposal |  |  | billed |  |  | 2017-03-14 | 1 | 0.5 | 2017-03-14 | Done
OPS | Operations |  | 2017-03-14 | Taxes |  |  | billed | 1 |  | 2017-03-14 | 4 | 3 | 2017-03-14 | Done
1578 | WRMC Street Lighting | 1656 | 2017-03-14 | ASA Proposal |  |  | billed |  |  | 2017-03-14 | 1 | 0.5 | 2017-03-14 | Done
1615 | Celeris (2017) |  | 2017-03-15 | Seal Projects |  |  | billed |  |  | 2017-03-15 | 1 | 1 | 2017-03-15 | Done
1570 | Forney MOB Tenant Improvement | 1658 | 2017-03-15 | Owner Changes |  |  | billed |  |  | 2017-03-15 | 2 | 1 | 2017-03-15 | Done
1538 | UNT Coliseum Concourse |  | 2017-03-13 | LTG DWGs to EoA for coordination |  |  | billed |  |  | 2017-03-15 | 4 | 4 | 2017-03-15 | Done
1615 | Celeris (2017) |  | 2017-03-13 | Billing vs Project analysis |  |  | billed |  |  | 2017-03-15 | 2 | 1 | 2017-03-14 | Done
1636 | Living Waters Worship Center | Schematic plan from EoA | 2017-03-15 | Proposal |  |  | billed |  |  | 2017-03-15 | 1 | 1 | 2017-03-15 | Done
1600 | Gun Experience |  | 2017-03-14 | Narrative | p10-59 |  | billed |  |  | 2017-03-16 | 2 | 3 | 2017-03-16 | Done
1615 | Celeris (2017) |  | 2017-03-15 | Seal Projects |  |  | billed |  |  | 2017-03-16 | 1 | 1 | 2017-03-16 | Done
1617 | Werner Enterprises Laredo |  | 2017-03-16 | work on IFC |  |  | billed |  |  | 2017-03-16 | 2 | 1 | 2017-03-16 | Done
1615 | Celeris (2017) |  | 2017-03-15 | Seal Projects |  |  | billed |  |  | 2017-03-17 | 1 | 0 | 2017-03-17 | Done
1617 | Werner Enterprises Laredo |  | 2017-03-16 | IFC QC |  |  | billed |  |  | 2017-03-17 | 2 | 2 | 2017-03-17 | Done
1617 | Werner Enterprises Laredo |  | 2017-03-17 | IFC |  |  | billed |  |  | 2017-03-18 | 1 | 1 | 2017-03-18 | Done
1538 | UNT Coliseum Concourse | E170313c | 2017-03-13 | CC Mtg |  |  | billed |  |  | 2017-03-20 | 1 | 1 | 2017-03-20 | Done
1546 | Mont Belvieu | Lighting Fixture submittal | 2017-03-20 | Schematic plan from EoA |  |  | billed |  |  | 2017-03-20 | 1 | 1 | 2017-03-20 | Done
1604 | Botanic Garden Assessment | E170307a | 2017-03-07 | KO Meeting |  |  | billed |  |  | 2017-03-21 | 3 | 2 | 2017-03-21 | Done
1477 | Eugene McCray Recreation Center | E270320b | 2017-03-20 | KO Site Visit |  |  | billed |  |  | 2017-03-21 | 2 | 2 | 2017-03-21 | Done
1478 | Handley Meadowbrook Rec Center | E270320b | 2017-03-20 | KO Site Visit |  |  | billed |  |  | 2017-03-21 | 2 | 2 | 2017-03-21 | Done
1538 | UNT Coliseum Concourse | E170320c | 2017-03-20 | Send email about LTG controls |  |  | billed |  |  | 2017-03-21 | 1 | 1 | 2017-03-22 | Done
1587 | Rental One Willow Park |  | 2017-03-22 | IFC |  |  | billed |  |  | 2017-03-22 | 1 | 1 | 2017-03-22 | Done
1577 | WRMC Sales Center | E170322c | 2017-03-22 | Lightning Protection Submittal |  |  | billed |  |  | 2017-03-23 | 1 | 0.5 | 2017-03-24 | Done
1577 | WRMC Sales Center | E170322d | 2017-03-22 | Lighting Fixture submittal | See E170323g for reqs. |  | billed |  |  | 2017-03-23 | 1 | 1 | 2017-03-24 | Done
1604 | Botanic Garden Assessment |  | 2017-03-22 | Scan KO Materias and forward to Tim |  |  | billed |  |  | 2017-03-23 | 1 | 0.5 | 2017-03-24 | Done
1478 | Handley Meadowbrook Rec Center |  | 2017-03-22 | Scan SV |  |  | billed |  |  | 2017-03-23 | 1 | 0.5 | 2017-03-24 | Done
1480 | Duke Schools Bond Program | E170323a | 2017-03-23 | Welding outlet issue |  |  | billed |  |  | 2017-03-23 | 1 | 2 | 2017-03-23 | Done
1617 | Werner Enterprises Laredo |  | 2017-03-22 | IFC |  |  | billed |  |  | 2017-03-23 | 1 | 1 | 2017-03-23 | Done
1477 | Eugene McCray Recreation Center |  | 2017-03-24 | Set up project |  |  | billed |  |  | 2017-03-24 | 2 | 2 | 2017-03-24 | Done
1478 | Handley Meadowbrook Rec Center |  | 2017-03-24 | Set up project |  |  | billed |  |  | 2017-03-24 | 2 | 1 | 2017-03-24 | Done
1538 | UNT Coliseum Concourse | E170320c | 2017-03-20 | DD Comments |  |  | billed |  |  | 2017-03-25 | 2 | 4 | 2017-03-25 | Done
1538 | UNT Coliseum Concourse | E170320b | 2017-03-20 | Review IT requirements | Cameras use PoE. |  | billed |  |  | 2017-03-25 | 1 | 0.5 | 2017-03-25 | Done
1538 | UNT Coliseum Concourse |  | 2017-03-25 | Incorporate Fire Alarm Specs from Guidelines |  |  | billed |  |  | 2017-03-25 | 1 | 1 | 2017-03-29 | Done
1538 | UNT Coliseum Concourse |  | 2017-03-25 | Review design guidelines |  |  | billed |  |  | 2017-03-25 | 2 | 1 | 2017-03-29 | Done
1538 | UNT Coliseum Concourse | E170320e | 2017-03-20 | LTG internal comments |  |  | billed |  |  | 2017-03-25 | 3 | 3 | 2017-03-25 | Done
1538 | UNT Coliseum Concourse | E170320b | 2017-03-14 | Assign panels to equipment |  |  | billed |  |  | 2017-03-27 | 3 | 2 | 2017-03-29 | Done
1477 | Eugene McCray Recreation Center |  | 2017-03-24 | Site Visit |  |  | billed |  |  | 2017-03-27 | 2 | 1.5 | 2017-03-27 | Done
1478 | Handley Meadowbrook Rec Center |  | 2017-03-24 | Site Visit |  |  | billed |  |  | 2017-03-27 | 2 | 1.5 | 2017-03-27 | Done
1538 | UNT Coliseum Concourse | E170313c | 2017-03-13 | CC Mtg |  |  | billed |  |  | 2017-03-27 | 1 | 1 | 2017-03-27 | Done
1477 | Eugene McCray Recreation Center |  | 2017-03-24 | Mark up SD set |  |  | billed |  |  | 2017-03-28 | 1 | 1 | 2017-03-29 | Done
1478 | Handley Meadowbrook Rec Center |  | 2017-03-24 | Mark up SD set |  |  | billed |  |  | 2017-03-28 | 1 | 1 | 2017-03-29 | Done
1478 | Handley Meadowbrook Rec Center |  | 2017-03-24 | CAD SD set |  |  | billed |  |  | 2017-03-28 | 1 | 1 | 2017-03-29 | Done
1614 | Euless Library |  | 2017-03-24 | Site Visit |  |  | billed |  |  | 2017-03-28 | 3 | 3 | 2017-03-28 | Done
1617 | Werner Enterprises Laredo | E170328a | 2017-03-28 | Revised Ifc |  |  | billed |  |  | 2017-03-28 | 1 | 1 | 2017-03-28 | Done
1538 | UNT Coliseum Concourse |  | 2017-03-28 | 60% LTG |  |  | billed |  |  | 2017-03-28 | 4 | 4 | 2017-03-28 | Done
1538 | UNT Coliseum Concourse |  | 2017-03-28 | 60% Enlarged LTG |  |  | billed |  |  | 2017-03-29 | 2 | 1 | 2017-03-28 | Done
1538 | UNT Coliseum Concourse |  | 2017-03-28 | 60% PWR |  |  | billed |  |  | 2017-03-29 | 2 | 1 | 2017-03-29 | Done
1538 | UNT Coliseum Concourse |  | 2017-03-28 | 60% Enlarged PWR |  |  | billed |  |  | 2017-03-29 | 2 | 1 | 2017-03-29 | Done
1538 | UNT Coliseum Concourse |  | 2017-03-29 | 60 CD Specs |  |  | billed |  |  | 2017-03-29 | 1 | 1 | 2017-03-29 | Done
1538 | UNT Coliseum Concourse |  | 2017-03-29 | 60% CD issue |  |  | billed |  |  | 2017-03-29 | 1 | 1 | 2017-03-29 | Done
1614 | Euless Library |  | 2017-03-28 | SD Narrative |  |  | billed |  |  | 2017-03-30 | 1 | 1 | 2017-03-30 | Done
OPS | Operations |  | 2017-03-14 | Shareholders and Board Mtgs | Add next years when done |  | no |  |  | 2018-01-20 | 2 | 2 | 2018-01-22 | Done
1477 | Eugene McCray Recreation Center |  | 2017-03-24 | CAD SD set |  |  | billed |  |  | 2017-03-30 | 1 | 1 | 2017-03-30 | Done
1342 | Patriot Paws | E170329c | 2017-03-29 | RFI 34 |  |  | billed |  |  | 2017-03-30 | 0.5 | 0.5 | 2017-03-29 | Done
1477 | Eugene McCray Recreation Center |  | 2017-03-29 | Issue SD Set |  |  | billed |  |  | 2017-03-31 | 1 | 0.5 | 2017-03-31 | Done
1478 | Handley Meadowbrook Rec Center |  | 2017-03-29 | Issue SD Set |  |  | billed |  |  | 2017-03-31 | 1 | 0.5 | 2017-03-31 | Done
1638 | 1121 Parker Suite 200 |  | 2017-03-30 | MKT SV |  |  | billed |  |  | 2017-03-31 | 4 | 4 | 2017-03-31 | Done
ops | Operations |  | 2017-03-31 | Clean up Office |  |  | billed |  |  | 2017-03-31 | 2 | 1 | 2017-04-01 | Done
1594 | Pflugerville AS | E170315e, E170329b | 2017-03-15 | City Comments | Got Site, 3/29 got building |  | billed |  |  | 2017-04-01 | 2 | 3 | 2017-04-01 | Done
1538 | UNT Coliseum Concourse | E170313c | 2017-03-13 | CC Mtg |  |  | billed |  |  | 2017-04-03 | 1 | 1.5 | 2017-04-03 | Done
ops | Operations |  | 2017-04-03 | Invoicing |  |  | billed |  |  | 2017-04-03 | 3 | 3 | 2017-04-03 | Done
1631 | Brown Street Church Addition | E170331c | 2017-03-31 | Site Visit |  |  | billed |  |  | 2017-04-04 | 4 | 2 | 2017-04-04 | Done
1624 | Fuego de Dios Church |  | 2017-03-31 | Site Visit | Confirm with Grant |  | billed |  |  | 2017-04-04 | 1 | 2 | 2017-04-04 | Done
1640 | Joyce Dr Changes | E170403c | 2017-04-03 | Prepare proposal |  |  | billed |  |  | 2017-04-05 | 2 | 1 | 2017-04-06 | Done
1538 | UNT Coliseum Concourse |  | 2017-04-05 | Revise 60% set |  |  | billed |  |  | 2017-04-05 | 6 | 6 | 2017-04-05 | Done
1641 | TCBY Irving | E170405f | 2017-04-05 | Proposal |  |  | billed |  |  | 2017-04-06 | 1 | 1 | 2017-04-06 | Done
1642 | Lewisville MOB | E170405f | 2017-04-05 | Proposal |  |  | billed |  |  | 2017-04-06 | 1 | 1 | 2017-04-06 | Done
1643 | Pantheon Construction Haltom City | E170406a | 2017-04-06 | Proposal |  |  | billed |  |  | 2017-04-06 | 1 | 1 | 2017-04-06 | Done
1621 | The Creek Church Phase II | E170329a | 2017-03-29 | Comments |  |  | billed |  |  | 2017-04-07 | 3 | 5 | 2017-04-07 | Done
1621 | The Creek Church Phase II |  | 2017-04-07 | Finish 50 CD |  |  | billed |  |  | 2017-04-08 | 3 | 3 | 2017-04-08 | Done
1621 | The Creek Church Phase II |  | 2017-04-08 | Include notes and LFS cut sheets |  |  | billed |  |  | 2017-04-08 | 1 | 1 | 2017-04-08 | Done
1604 | Botanic Garden Assessment | E170403b | 2017-04-03 | Read meeting minutes |  |  | billed |  |  | 2017-04-10 | 1 | 0.5 | 2017-04-28 | Done
1538 | UNT Coliseum Concourse |  | 2017-03-13 | CC Mtg | Cancelled |  | billed |  |  | 2017-04-10 |  | 0 | 2017-04-10 | Done
1594 | Pflugerville AS | Lewisville MOB | 2017-04-06 | New issue without clouds | Seal and date 4/10 |  | billed |  |  | 2017-04-10 | 1 | 1 | 2017-04-10 | Done
1624 | Fuego de Dios Church |  | 2017-04-10 | Set up project |  |  | billed |  |  | 2017-04-10 | 2 | 2 | 2017-04-15 | Done
1538 | UNT Coliseum Concourse | E170410c | 2017-03-31 | 60% CD review meeting questions |  |  | billed |  |  | 2017-04-10 | 2 | 1 | 2017-04-10 | Done
1577 | WRMC Sales Center | E170411a | 2017-04-12 | ASI 01 |  |  | billed |  |  | 2017-04-11 | 1 | 1 | 2017-04-12 | Done
1577 | WRMC Sales Center | E170412b | 2017-04-12 | FA Submittal |  |  | billed |  |  | 2017-04-12 | 1 | 1 | 2017-04-12 | Done
1480 | Duke Schools Bond Program | E170413a | 2017-04-13 | Voltage conversion issue |  |  | billed |  |  | 2017-04-13 | 1 | 1 | 2017-04-13 | Done
1516 | Hair Stars Salon | E170413c | 2017-04-13 | Revision 2 - Remove water htr |  |  | billed |  |  | 2017-04-13 | 1 | 1 | 2017-04-13 | Done
1538 | UNT Coliseum Concourse |  | 2017-03-13 | CC Mtg |  |  | billed |  |  | 2017-04-17 | 1 | 1 | 2017-04-17 | Done
1624 | Fuego de Dios Church |  | 2017-04-17 | 50% CD |  |  | billed |  |  | 2017-04-17 | 2 | 2 | 2017-04-17 | Done
1392 | UNT Clark Bakery | E170417a | 2017-04-17 | Scott's scope |  |  | billed |  |  | 2017-04-17 | 1 | 1 | 2017-04-18 | Done
1392 | UNT Clark Bakery | E170417c | 2017-04-17 | MP Sheets |  |  | billed |  |  | 2017-04-17 | 1 | 1 | 2017-04-18 | Done
1416 | DCCCD Eastfield Generator | E170405e | 2017-04-05 | 2nd Meeting |  |  | billed |  |  | 2017-04-18 | 3 | 4 | 2017-04-18 | Done
1570 | Forney MOB Tenant Improvement | E170418b | 2017-04-18 | X-Ray documents |  |  | billed |  |  | 2017-04-18 | 1 | 1 | 2017-04-18 | Done
1538 | UNT Coliseum Concourse | E170414a | 2017-04-17 | Schedule SV | 4/24 Sent email | Jackie's answer | billed |  |  | 2017-04-19 | 1 | 1 | 2017-04-24 | Done
1604 | Botanic Garden Assessment |  | 2017-04-17 | Schedule SV |  |  | billed |  |  | 2017-04-19 | 1 | 1 | 2017-04-24 | Done
1392 | UNT Clark Bakery | E170419b | 2017-04-19 | Scott's comments |  |  | billed |  |  | 2017-04-19 | 2 | 1 | 2017-04-19 | Done
1577 | WRMC Sales Center | E170420b | 2017-04-20 | ASI 2 |  |  | billed |  |  | 2017-04-20 | 1 | 1 | 2017-04-20 | Done
1592 | Deer Park Animal Shelter | E170418c | 2017-04-18 | City Comments | Contact City. |  | billed |  |  | 2017-04-20 | 1 | 1 | 2017-04-20 | Done
1443 | Bailey Lake Park | E170420a | 2017-04-20 | Utility form |  |  | billed |  |  | 2017-04-20 | 1 | 0 | 2017-04-20 | Done
1538 | UNT Coliseum Concourse |  | 2017-03-13 | CC Mtg |  |  | billed |  |  | 2017-04-24 | 1 | 1 | 2017-04-24 | Done
1416 | DCCCD Eastfield Generator |  | 2017-04-24 | Prepare bid review q & a |  |  | billed |  |  | 2017-04-25 | 1 | 1 | 2017-04-25 | Done
1577 | WRMC Sales Center | Meeting at JPS | 2017-04-25 | ASI 03 | two emails |  | billed |  |  | 2017-04-25 | 1 | 1/ | 2017-04-25 | Done
1615 | Celeris (2017) |  | 2017-04-25 | Celeris project markups |  |  | billed |  |  | 2017-04-25 | 1 | 1 | 2017-04-26 | Done
1591 | JPS 3rd Floor OR Renovation |  | 2017-04-25 | Meeting at JPS |  |  | billed |  |  | 2017-04-26 | 2.5 | 2 | 2017-04-26 | Done
1518 | Fredericksburg AS | E170425f | 2017-04-25 | Dishwasher issue | ASI |  | billed |  |  | 2017-04-26 | 1 | 0.5 | 2017-04-27 | Done
1546 | Mont Belvieu | E170425f | 2017-04-25 | Dishwasher issue | ASI |  | billed |  |  | 2017-04-26 | 1 | 0.5 | 2017-04-27 | Done
1592 | Deer Park Animal Shelter | E170425f | 2017-04-25 | Dishwasher issue | ASI |  | billed |  |  | 2017-04-26 | 1 | 0.5 | 2017-04-27 | Done
1535 | Cornerstone Baptist Church | E170425c | 2017-04-25 | LTG Submittal |  |  | billed |  |  | 2017-04-27 | 1 | 1 | 2017-04-28 | Done
1621 | The Creek Church Phase II |  | 2017-04-20 | Comments |  |  | billed |  |  | 2017-04-27 | 1 | 1 | 2017-04-27 | Done
1577 | WRMC Sales Center | E170425b | 2017-04-25 | Submittal |  |  | billed |  |  | 2017-04-27 | 1 | 1 | 2017-04-28 | Done
1538 | UNT Coliseum Concourse |  | 2017-04-24 | Site Visit | At 1:00 PM |  | billed |  |  | 2017-04-27 | 2 | 2 | 2017-04-27 | Done
1621 | The Creek Church Phase II |  |  | 90% CD | Final set |  | billed |  |  | 2017-04-27 | 5 | 3 | 2017-04-28 | Done
1621 | The Creek Church Phase II | E170427a | 2017-04-27 | MP Sheets |  |  | billed |  |  | 2017-04-27 | 1 | 1 | 2017-04-27 | Done
1621 | The Creek Church Phase II | E170427b | 2017-04-27 | Updated base files |  |  | billed |  |  | 2017-04-27 | 1 | 1 | 2017-04-27 | Done
1644 | Dallas Church Gym | E170427 | 2017-04-27 | Proposal |  |  | billed |  |  | 2017-04-28 | 1 | 1 | 2017-04-28 | Done
1645 | Watauga Church Narrative | E170428b | 2017-04-28 | Proposal |  |  | billed |  |  | 2017-04-28 | 1 | 0.5 | 2017-04-28 | Done
1615 | Celeris (2017) |  | 2017-04-28 | Seal Toyota Center |  |  | billed |  |  | 2017-04-28 | 0.5 | 0.5 | 2017-04-28 | Done
1646 | Italian Bistro |  | 2017-05-01 | Proposal |  |  | billed |  |  | 2017-05-01 | 1 | 1 | 2017-05-02 | Done
1538 | UNT Coliseum Concourse |  | 2017-03-13 | CC Mtg |  |  | billed |  |  | 2017-05-01 | 1 | 1 | 2017-05-01 | Done
1624 | Fuego de Dios Church | E170428e | 2017-04-28 | Add floor box, alternate, etc | IFC |  | billed |  |  | 2017-05-01 | 2 | 2 | 2017-05-01 | Done
1645 | Watauga Church Narrative |  | 2017-05-02 | Site Visit |  |  | billed |  |  | 2017-05-02 | 4 | 3 | 2017-05-02 | Done
1604 | Botanic Garden Assessment |  | 2017-05-02 | Conservatory Report |  |  | billed |  |  | 2017-05-02 | 1 | 1 | 2017-05-03 | Done
1477 | Eugene McCray Recreation Center |  | 2017-05-02 | Contract v proposal issue |  |  | billed |  |  | 2017-05-02 | 1 | 1 | 2017-05-03 | Done
1495 | UNT Child Development. Lab |  | 2017-05-02 | Record drawings |  |  | billed |  |  | 2017-05-02 | 2 | 2 | 2017-05-03 | Done
1451 | The Door Church | E170502a | 2017-05-02 | Electrical Service Issue |  |  | billed |  |  | 2017-05-02 | 1 | 1 | 2017-05-02 | Done
1591 | JPS 3rd Floor OR Renovation |  | 2017-04-27 | ASA Proposal |  |  | billed |  |  | 2017-05-03 | 1 | 0.5 | 2017-05-03 | Done
1631 | Brown Street Church Addition | E170407a | 2017-04-07 | Set up project |  |  | billed |  |  | 2017-05-03 | 3 | 2 | 2017-05-04 | Done
1631 | Brown Street Church Addition | E170428a | 2017-04-28 | Update base files | Used them to set up the project |  | billed |  |  | 2017-05-03 | 1 | 0 | 2017-05-04 | Done
1538 | UNT Coliseum Concourse |  | 2017-05-03 | LTG Controls with Brenan |  |  | billed |  |  | 2017-05-03 | 2 | 1 | 2017-05-03 | Done
1477 | Eugene McCray Recreation Center | E170503a | 2017-05-03 | Updated base files |  |  | billed |  |  | 2017-05-03 | 1 | 1 | 2017-05-04 | Done
1477 | Eugene McCray Recreation Center | E170428c | 2017-04-28 | Update base files | Superceded |  | billed |  |  | 2017-05-04 | 1 | 0 | 2017-05-04 | Done
1538 | UNT Coliseum Concourse |  | 2017-04-28 | Security meeting |  |  | billed |  |  | 2017-05-05 | 3 | 3 | 2017-05-05 | Done
ops | Operations |  | 2017-05-03 | Invoice UNT CDL |  |  | billed | 1 |  | 2017-05-05 | 1 | 1 | 2017-05-05 | Done
ops | Operations |  | 2017-05-04 | Invoicing |  |  | billed | 1 |  | 2017-05-05 | 2 | 2 | 2017-05-05 | Done
1538 | UNT Coliseum Concourse |  | 2017-05-05 | Revise power plan (office) |  |  | billed | 1 |  | 2017-05-05 | 1 | 1 | 2017-05-06 | Done
1647 | Hope Church Addition |  | 2017-05-05 | Proposal |  |  | billed | 1 |  | 2017-05-05 | 1 | 0.5 | 2017-05-05 | Done
1477 | Eugene McCray Recreation Center | E170428c | 2017-04-28 | DD Comments |  |  | billed |  |  | 2017-05-06 | 3 | 3 | 2017-05-06 | Done
1477 | Eugene McCray Recreation Center | E170505b | 2017-05-05 | Review kitchen cut sheets |  |  | billed |  |  | 2017-05-06 | 0.5 | 0.5 | 2017-05-06 | Done
1478 | Handley Meadowbrook Rec Center | E170505b | 2017-05-05 | Review kitchen cut sheets |  |  | billed |  |  | 2017-05-06 | 0.5 | 0.5 | 2017-05-07 | Done
1478 | Handley Meadowbrook Rec Center | E170428d | 2017-04-28 | DD Comments |  |  | billed |  |  | 2017-05-07 | 3 | 3 | 2017-05-07 | Done
1477 | Eugene McCray Recreation Center | E170428c | 2017-05-06 | Finish DD comments and LTG |  |  | billed |  |  | 2017-05-07 | 2 | 2 | 2017-05-07 | Done
1478 | Handley Meadowbrook Rec Center | E170428d | 2017-04-28 | Update base files | Waiting for files. Got them on 5/8. New AI |  | billed |  |  | 2017-05-08 | 1 | 0 | 2017-05-08 | Done
1538 | UNT Coliseum Concourse |  | 2017-03-13 | CC Mtg |  |  | billed |  |  | 2017-05-08 | 1 | 0.5 | 2017-05-08 | Done
1535 | Cornerstone Baptist Church | E170505c | 2017-05-05 | Lighting Fixture submittal |  |  | billed |  |  | 2017-05-08 | 1 | 1 | 2017-05-09 | Done
ops | Operations |  |  | Send Eastfield generator invoice | Send after ref checking |  | billed |  |  | 2017-05-08 | 0.5 | 0.5 | 2017-05-08 | Done
1538 | UNT Coliseum Concourse |  | 2017-05-08 | Meeting minute review |  |  | billed |  |  | 2017-05-08 | 0.5 | 0.5 | 2017-05-08 | Done
1416 | DCCCD Eastfield Generator | E170505a | 2017-05-05 | Reference calls |  |  | billed |  |  | 2017-05-08 | 2 | 1 | 2017-05-08 | Done
1477 | Eugene McCray Recreation Center |  | 2017-05-07 | QC for 50% CD |  |  | billed |  |  | 2017-05-08 | 1 | 1 | 2017-05-08 | Done
1478 | Handley Meadowbrook Rec Center |  | 2017-05-07 | QC for 50% CD |  |  | billed |  |  | 2017-05-08 | 1 | 1 | 2017-05-08 | Done
1648 | OWT Offices | E170505g | 2017-05-05 | Site Visit |  |  | billed |  |  | 2017-05-09 | 0.5 | 1 | 2017-05-09 | Done
1606 | Tindall Storage Building | E170505g | 2017-05-05 | Site Visit |  |  | billed |  |  | 2017-05-09 | 2 | 2 | 2017-05-09 | Done
1538 | UNT Coliseum Concourse | E170502b | 2017-05-03 | Protection for the LED ribbons | Not needed |  | billed |  |  | 2017-05-10 |  |  | 2017-05-17 | Done
1538 | UNT Coliseum Concourse | E170505f | 2017-05-05 | Revise LTG control spec | Use Brenan's markups as a basis |  | billed |  |  | 2017-05-10 | 1 | 2 | 2017-05-18 | Done
1604 | Botanic Garden Assessment | E170509b | 2017-05-09 | Edit conservatory report |  |  | billed |  |  | 2017-05-10 | 1 | 0.5 | 2017-05-10 | Done
1538 | UNT Coliseum Concourse | E170509c | 2017-05-09 | Update base files |  |  | billed |  |  | 2017-05-10 | 0.5 | 0.5 | 2017-05-10 | Done
1631 | Brown Street Church Addition | Ph Eric | 2017-05-09 | Send LTG cut sheets to Eric |  |  | billed |  |  | 2017-05-10 | 1 | 0.5 | 2017-05-10 | Done
1538 | UNT Coliseum Concourse | E170510a | 2017-05-10 | M Sheet coordination |  |  | billed |  |  | 2017-05-10 | 1 | 2 | 2017-05-10 | Done
1538 | UNT Coliseum Concourse |  | 2017-05-10 | Check 4 v 6' lights on concourse |  |  | billed |  |  | 2017-05-10 | 1 | 2 | 2017-05-10 | Done
1538 | UNT Coliseum Concourse | E170505h | 2017-05-10 | Troy's signs |  |  | billed |  |  | 2017-05-10 | 1 | 1 | 2017-05-10 | Done
1649 | Magnolia Per Resort | E170510d | 2017-05-10 | Proposal |  |  | billed |  |  | 2017-05-10 | 1 | 0.5 | 2017-05-10 | Done
1650 | Fit and Fancy Med Spa | E170510e | 2017-05-10 | Proposal |  |  | billed |  |  | 2017-05-10 | 1 | 0.5 | 2017-05-10 | Done
1648 | OWT Offices |  | 2017-05-22 | IFC Dated 5/23 |  |  | billed | 1 |  | 2017-05-22 | 1 | 1 | 2017-05-22 | Done
1645 | Watauga Church Narrative |  | 2017-05-02 | Narrative | 5/4 need to finish |  | billed | 1 |  | 2017-05-11 | 4 | 3 | 2017-05-15 | Done
1651 | Nidoma Warehouse | E170510f | 2017-05-10 | Proposal |  |  | billed |  |  | 2017-05-11 | 1 | 1 | 2017-05-12 | Done
1538 | UNT Coliseum Concourse |  | 2017-05-10 | Circuit and QC |  |  | billed |  |  | 2017-05-11 | 3 | 3 | 2017-05-11 | Done
1628 | Machine House | E170509a | 2017-05-09 | Preliminary questions to Tim |  |  | billed |  |  | 2017-05-12 | 1 | 1 | 2017-05-16 | Done
1648 | OWT Offices |  |  | IFR |  |  | billed | 1 |  | 2017-05-13 | 4 | 3 | 2017-05-13 | Done
1538 | UNT Coliseum Concourse |  | 2017-03-13 | CC Mtg | Meeting canceled |  | billed |  |  | 2017-05-15 | 0 | 0 | 2017-05-15 | Done
1631 | Brown Street Church Addition |  | 2017-05-15 | LTG layouts |  |  | billed |  |  | 2017-05-15 | 1 | 1 | 2017-05-15 | Done
1631 | Brown Street Church Addition |  | 2017-05-15 | LTG Room defs |  |  | billed |  |  | 2017-05-15 | 0.5 | 0.5 | 2017-05-15 | Done
1535 | Cornerstone Baptist Church | E170516a | 2017-05-16 | LTG Controls Submittal |  |  | billed | 1 |  | 2017-05-16 | 1 | 1 | 2017-05-16 | Done
1591 | JPS 3rd Floor OR Renovation | E170516c | 2017-05-16 | Revise plans | See p10-80 for scope. | Approved proposal | billed | 2 |  |  |  | 1 | 2017-06-06 | Done
1614 | Euless Library |  |  | DD progress meeting |  |  | billed |  |  | 2017-05-22 | 2 | 3 | 2017-05-22 | Done
1615 | Celeris (2017) |  | 2017-05-16 | AR project |  |  | billed |  |  | 2017-05-16 | 0.5 | 0.5 | 2017-05-16 | Done
1501 | Kimbell East Parking | E170516f | 2017-05-16 | LTG Controls Submittal |  |  | billed | 2 |  | 2017-05-16 | 1 | 1 | 2017-05-16 | Done
1628 | Machine House |  | 2017-05-19 | Send Qs to Tim |  |  | billed | 3 |  | 2017-05-22 | 1 | 1 | 2017-05-22 | Done
1621 | The Creek Church Phase II | E170516g | 2017-05-15 | Creek Comments | SECOND SESSION |  | billed | 4 |  | 2017-05-22 | 4 | 3 | 2017-05-23 | Done
1591 | JPS 3rd Floor OR Renovation | E170516d | 2017-05-16 | Update base files |  | Approved proposal | billed | 2 |  |  | 1 | 1 | 2017-06-06 | Done
1631 | Brown Street Church Addition | E170523b | 2017-05-23 | MP Sheets |  |  | billed |  |  | 2017-05-24 | 1 | 1 | 2017-05-24 | Done
1631 | Brown Street Church Addition |  | 2017-05-15 | LTG controls |  |  | billed |  |  | 2017-05-24 | 0.5 | 0.5 | 2017-05-25 | Done
1631 | Brown Street Church Addition |  | 2017-05-15 | LTG Schematics and schedules |  |  | billed |  |  | 2017-05-24 | 0.5 | 0.5 | 2017-05-25 | Done
1631 | Brown Street Church Addition |  | 2017-05-15 | PWR and LV Layouts |  |  | billed |  |  | 2017-05-24 | 1 | 1 | 2017-05-24 | Done
1621 | The Creek Church Phase II | E170516g | 2017-05-15 | Creek Comments |  |  | billed |  |  | 2017-05-22 | 4 | 2 | 2017-05-19 | Done
1648 | OWT Offices | E170516e | 2017-05-16 | Incorporate comments |  |  | billed | low |  | 2017-05-22 | 1 | 1 | 2017-05-19 | Done
1631 | Brown Street Church Addition |  | 2017-05-15 | PWR and LV Schedles |  |  | billed |  |  | 2017-05-24 | 1 | 0.5 | 2017-05-24 | Done
1392 | UNT Clark Bakery | E170314d | 2017-03-15 | UNT comments |  |  | billed | [5 empty] | 2017-04-19 | Done
1421 | KXAS Remodel | S170215s | 2017-02-15 | Fix UPS v Storage room issue | 5/1 No feedback | 2/20 City response | billed | [5 empty] | 2017-05-01 | Done
1451 | The Door Church | V170228v | 2017-02-28 | Schedule rev 10 | 5/1 Not done | input from Tim | billed | [5 empty] | 2017-05-01 | Done
1631 | Brown Street Church Addition |  | 2017-05-15 | EQP defs and schedule |  |  | billed |  |  | 2017-05-24 | 1 | 1 | 2017-05-24 | Done
1631 | Brown Street Church Addition |  | 2017-05-15 | EQP Layouts |  |  | billed |  |  | 2017-05-24 | 0.5 | 0.5 | 2017-05-24 | Done
1621 | The Creek Church Phase II | E170518a | 2017-05-16 | Fix elevator issue | Got information |  | billed |  |  | 2017-05-23 | 0.5 | 0.25 | 2017-05-23 | Done
1631 | Brown Street Church Addition |  | 2017-05-15 | OL diagram, panel defs and conn. |  |  | billed |  |  | 2017-05-24 | 1 | 1 | 2017-05-24 | Done
1631 | Brown Street Church Addition | E170519c | 2017-05-19 | Use Crestron lighting controls | Confirmed |  | billed |  |  | 2017-05-24 |  | 0.5 | 2017-05-25 | Done
1591 | JPS 3rd Floor OR Renovation |  | 2017-05-30 | Corrections |  |  | billed | 1 |  | 2017-05-30 | 1 | 1 | 2017-05-30 | Done
1501 | Kimbell East Parking | E170516f | 2017-05-23 | Mtg on site |  |  | billed |  |  | 2017-05-24 | 2 | 2 | 2017-05-24 | Done
1621 | The Creek Church Phase II |  | 2017-05-23 | Final QC |  |  | billed |  |  | 2017-05-24 | 2 | 3 | 2017-05-25 | Done
1538 | UNT Coliseum Concourse | E170517a | 2017-05-17 | Update base files |  |  | billed |  |  | 2017-05-17 | 1 | 1 | 2017-05-17 | Done
1538 | UNT Coliseum Concourse |  | 2017-05-17 | QC Meeting |  |  | billed |  |  | 2017-05-17 | 3 | 3 | 2017-05-17 | Done
1538 | UNT Coliseum Concourse |  | 2017-05-17 | Markups |  |  | billed |  |  | 2017-05-17 | 3 | 3 | 2017-05-19 | Done
1570 | Forney MOB Tenant Improvement | E170525e | 2017-05-25 | RFI 9 |  |  | billed | 1 |  | 2017-05-25 | 1 | 0.5 | 2017-05-25 | Done
1538 | UNT Coliseum Concourse |  | 2017-05-18 | Issue Specs |  |  | billed |  |  | 2017-05-19 | 1 | 3 | 2017-05-19 | Done
1538 | UNT Coliseum Concourse |  | 2017-05-18 | Installation Details |  |  | billed |  |  | 2017-05-19 | 1 | 1 | 2017-05-19 | Done
1538 | UNT Coliseum Concourse |  | 2017-05-18 | Final QC |  |  | billed |  |  | 2017-05-19 | 8 | 8 | 2017-05-20 | Done
1624 | Fuego de Dios Church | E170525b | 2017-05-25 | Add bollards |  |  | billed | 2 |  | 2017-05-30 | 1 | 1 | 2017-05-30 | Done
1570 | Forney MOB Tenant Improvement | E170518c | 2017-05-18 | ASI 1 |  |  | billed |  |  | 2017-05-19 | 1 | 0.5 | 2017-05-19 | Done
1538 | UNT Coliseum Concourse |  | 2017-05-19 | Add TV wall ltg fixture |  |  | billed |  |  | 2017-05-19 | 1 | 1 | 2017-05-19 | Done
1591 | JPS 3rd Floor OR Renovation | E170523d | 2017-05-23 | Update base files |  |  | billed | 1 |  | 2017-05-26 | 1 | 2 | 2017-05-26 | Done
1591 | JPS 3rd Floor OR Renovation | E170523g | 2017-05-23 | Provide 1-hr rated fixture in corridor |  |  | billed | 1 |  | 2017-05-26 | 0.5 | 1 | 2017-05-26 | Done
1631 | Brown Street Church Addition | 170404 SV | 2017-05-07 | Relocate (e) telecom line |  |  | billed |  |  |  |  | 0.5 | 2017-05-25 | Done
1591 | JPS 3rd Floor OR Renovation |  | 2017-05-23 | See p10-80 for scope |  |  | billed | 1 |  | 2017-05-26 | 1 | 1 | 2017-05-26 | Done
1530 | Brennan Drop-off Changes | E170523a | 2017-05-23 | SBE Affidavit |  |  | billed |  |  | 2017-05-23 | 0.5 | 0.5 | 2017-05-23 | Done
1531 | MLK Drop-off Changes | E170523a | 2017-05-23 | SBE Affidavit |  |  | billed |  |  | 2017-05-23 | 0.5 | 0.5 | 2017-05-23 | Done
1532 | Old Hemphill Drop-off Changes | E170523a | 2017-05-23 | SBE Affidavit |  |  | billed |  |  | 2017-05-23 | 0.5 | 0.5 | 2017-05-23 | Done
1655 | The Joint - Lake Highlands | E170529b | 2017-05-29 | Set up project, IFR |  |  | billed | 3 |  | 2017-05-30 | 1 | 3 | 2017-05-30 | Done
1621 | The Creek Church Phase II | E170523c | 2017-05-23 | MP Sheets | Email has important info |  | billed |  |  | 2017-05-23 | 1 | 1 | 2017-05-23 | Done
1342 | Patriot Paws | E170525c | 2017-05-25 | Punch list SV |  |  | billed | 4 |  | 2017-05-30 | 4 | 4 | 2017-05-30 | Done
1621 | The Creek Church Phase II | E170523e | 2017-05-23 | PWR for magnetic doors |  |  | billed |  |  | 2017-05-23 | 0.5 | 0 | 2017-05-23 | Done
1631 | Brown Street Church Addition | E170517b | 2017-05-17 | Update base files |  |  | billed |  |  |  |  | 1 | 2017-05-25 | Done
1628 | Machine House |  | 2017-05-25 | Electrical sheets on ACAD |  |  | billed | 6 |  | 2017-05-27 | 1 | 1 | 2017-05-27 | Done
1577 | WRMC Sales Center | E170525d | 2017-05-25 | Submittal |  |  | billed | 2 |  | 2017-05-25 | 1 | 0.5 | 2017-05-25 | Done
1621 | The Creek Church Phase II | E170523f | 2017-05-23 | Specs |  |  | billed |  |  | 2017-05-23 | 1.5 | 1 | 2017-05-23 | Done
1621 | The Creek Church Phase II |  | 2017-05-23 | COMCheck |  |  | billed |  |  | 2017-05-23 | 1 | 1 | 2017-05-23 | Done
1621 | The Creek Church Phase II |  | 2017-05-23 | Need updated plan. See rm 110 |  |  | billed |  |  | 2017-05-23 | 1 | 1 | 2017-05-23 | Done
1501 | Kimbell East Parking | E170525f | 2017-05-25 | Cabinet submittal |  |  | billed | 3 |  | 2017-05-25 | 1 | 0.5 | 2017-05-25 | Done
1628 | Machine House |  | 2017-05-26 | Set up project |  |  | billed | 6 |  | 2017-05-27 | 2 | 2 | 2017-05-27 | Done
1631 | Brown Street Church Addition |  | 2017-05-25 | Circuit , graphics, etc. |  |  | billed |  |  | 2017-05-25 | 2 | 2 | 2017-05-25 | Done
1654 | Mineral Wells Head Start | E170525j | 2017-05-25 | Proposal |  |  | billed | 5 |  | 2017-05-30 | 2 | 1 | 2017-05-31 | Done
1648 | OWT Offices | E170525h | 2017-05-25 | Comments |  |  | billed | 4 |  | 2017-05-25 | 1 | 0.5 | 2017-05-25 | Done
1628 | Machine House |  | 2017-05-26 | LTG |  |  | billed | 5 |  | 2017-05-30 | 4 | 4 | 2017-05-31 | Done
1495 | UNT Child Development. Lab | E170525g | 2017-05-25 | Record drawings |  |  | billed | 5 |  | 2017-05-25 | 1 | 0.5 | 2017-05-25 | Done
1620 | City of Weatherford Service Center | E170525a | 2017-05-25 | Prepare for SV |  |  | billed |  |  | 2017-05-31 | 1 | 0.5 | 2017-05-31 | Done
1606 | Tindall Storage Building | E170505e | 2017-05-05 | Update base files |  |  | billed | 5 |  | 2017-06-01 | 1 | 0.5 | 2017-05-27 | Done
1628 | Machine House |  | 2017-05-26 | PWR |  |  | billed | 5 |  | 2017-05-30 | 2 | 1 | 2017-05-31 | Done
1628 | Machine House |  | 2017-05-31 | IFR |  |  | billed |  |  | 2017-06-01 | 2 | 2 | 2017-06-01 | Done
1614 | Euless Library | E170503b | 2017-05-03 | Set up Project and review model |  |  | billed |  |  | 2017-06-01 | 2 | 2 | 2017-06-01 | Done
1631 | Brown Street Church Addition | E170601a | 2017-06-01 | Update base files |  |  | billed |  |  | 2017-06-01 | 1 | 1 | 2017-06-01 | Done
1655 | The Joint - Lake Highlands | E170601b | 2017-06-01 | Comments |  |  | billed |  |  | 2017-06-01 | 2 | 1 | 2017-06-01 | Done
1632 | Upper Trinity Conservation |  | 2017-05-31 | KO Meeting |  |  | billed |  |  | 2017-06-02 | 2 | 1 | 2017-06-02 | Done
1614 | Euless Library | E170605a | 2017-06-01 | LTG: LFS |  |  | billed | 1 |  | 2017-06-05 | 2 | 2 | 2017-06-05 | Done
1620 | City of Weatherford Service Center | E170320f | 2017-03-20 | Site Visit |  | Schematic plan from EoA | billed |  |  | 2017-05-31 | 3 | 3 | 2017-05-31 | Done
1606 | Tindall Storage Building |  | 2017-05-26 | SET |  |  | billed |  |  | 2017-05-29 | 2 | 2 | 2017-05-27 | Done
1614 | Euless Library |  | 2017-06-01 | PWR:Layouts |  |  | billed | 2 |  | 2017-06-05 | 1 | 1 | 2017-06-05 | Done
1628 | Machine House |  | 2017-05-26 | OL |  |  | billed |  |  |  | 1 | 1 | 2017-05-31 | Done
1614 | Euless Library |  | 2017-06-01 | DATA: Layouts |  |  | billed | 3 |  | 2017-06-06 | 0.5 | 0.5 | 2017-06-06 | Done
1614 | Euless Library |  | 2017-06-01 | OL: Riser and Schedules |  |  | billed | 4 |  | 2017-06-06 | 2 | 1 | 2017-06-06 | Done
1614 | Euless Library |  | 2017-06-05 | DEMO |  |  | billed | 5 |  | 2017-06-05 | 2 | 1 | 2017-06-05 | Done
1591 | JPS 3rd Floor OR Renovation |  | 2017-05-26 | Final QC |  |  | billed |  |  | 2017-05-26 | 1 | 1 | 2017-05-26 | Done
1628 | Machine House |  | 2017-05-26 | SET |  |  | billed |  |  | 2017-05-27 | 2 | 2 | 2017-05-27 | Done
1591 | JPS 3rd Floor OR Renovation | E170605f | 2017-06-05 | Update backgrounds and adjust |  |  | billed | 6 |  | 2017-06-05 | 1 | 3 | 2017-06-06 | Done
1478 | Handley Meadowbrook Rec Center | E170605h | 2017-06-05 | Comments |  |  | billed | 7 |  | 2017-06-05 | 0.5 | 0.5 | 2017-06-05 | Done
1342 | Patriot Paws |  | 2017-05-31 | Punch list Report |  |  | billed |  |  | 2017-05-31 | 1 | 1 | 2017-05-31 | Done
1591 | JPS 3rd Floor OR Renovation |  | 2017-05-31 | More changes |  |  | billed |  |  | 2017-05-31 | 1 | 1 | 2017-05-31 | Done
1654 | Mineral Wells Head Start |  | 2017-06-05 | MKT materials to Doug |  |  | billed |  |  | 2017-06-05 | 1 | 1 | 2017-06-05 | Done
1614 | Euless Library | E170606c | 2017-06-01 | LTG: Layouts |  |  | billed |  |  | 2017-06-06 | 3 | 2 | 2017-06-06 | Done
1631 | Brown Street Church Addition | E170525k | 2017-05-25 | Add wall packs plus … | Email has important info |  | billed |  |  | 2017-06-01 | 0.5 | 0.5 | 2017-06-01 | Done
1628 | Machine House | E170605d | 2017-06-05 | Comments | Provide responses |  | billed |  |  | 2017-06-06 | 1 | 1 | 2017-06-07 | Done
1631 | Brown Street Church Addition | E170601c | 2017-06-01 | Wall packs and data outlets |  |  | billed |  |  | 2017-06-01 | 0.5 | 1 | 2017-06-01 | Done
1535 | Cornerstone Baptist Church | E170605g | 2017-06-05 | Fire Alarm submittal |  |  | billed |  |  | 2017-06-06 | 1 | 1 | 2017-06-07 | Done
ops | Operations |  | 2017-06-08 | Billing |  |  | billed | 1 |  | 2017-06-08 | 1 | 1 | 2017-06-08 | Done
1628 | Machine House | E170605b | 2017-06-05 | Add internal lights |  |  | billed |  |  |  | 1 |  | 2017-07-10 | Done
1628 | Machine House | E170605d | 2017-06-07 | Implement comments |  |  | billed |  |  |  | 2 | 2 | 2017-06-21 | Done
1648 | OWT Offices | E170606b | 2017-06-06 | City comments | Done in rev 1 |  | billed |  |  |  |  | 0 | 2017-08-03 | Done
1606 | Tindall Storage Building |  | 2017-05-26 | LTG |  |  | billed |  |  |  | 3 | 2 | 2017-06-15 | Done
1606 | Tindall Storage Building |  | 2017-05-26 | PWR |  |  | billed |  |  |  | 1 | 2 | 2017-06-15 | Done
1606 | Tindall Storage Building | E170529e | 2017-05-26 | EQ | Email has important info |  | billed |  |  |  | 1 | 1 | 2017-06-15 | Done
1606 | Tindall Storage Building |  | 2017-05-26 | OL |  |  | billed |  |  |  | 1 | 1 | 2017-06-15 | Done
1614 | Euless Library |  | 2017-06-08 | Comments |  |  | billed | 1 |  | 2017-06-08 | 2 | 2 | 2017-06-08 | Done
1615 | Celeris (2017) |  | 2017-06-05 | Projects |  |  | billed |  |  | 2017-06-05 | 0.5 | 0.5 | 2017-06-05 | Done
1559 | Southlake MOB Shell |  | 2017-06-05 | ONCOR Form |  |  | billed |  |  | 2017-06-05 | 1 | 1 | 2017-06-05 | Done
1632 | Upper Trinity Conservation |  | 2017-06-07 | Complete set up and print for planning |  |  | billed | 2 |  | 2017-06-08 |  | 3 | 2017-06-13 | Done
1651 | Nidoma Warehouse | E170511a | 2017-05-11 | Email has design criteria | Closed for inactivity | Project Approval | billed | [5 empty] | 2017-09-26 | Done
1632 | Upper Trinity Conservation |  | 2017-06-07 | Electrical Room dimensions |  |  | billed | 2 |  | 2017-06-08 | 1 | 0 | 2017-06-13 | Done
1614 | Euless Library | E170602a | 2017-06-02 | Preliminary M info |  |  | billed |  |  |  | 0.5 | 0.5 | 2017-06-06 | Done
1606 | Tindall Storage Building |  | 2017-06-08 | Complete set up and print for planning |  |  | billed | 3 |  | 2017-06-08 | 1 | 1 | 2017-06-15 | Done
1657 | Cleburne SWAT |  | 2017-06-05 | Proposal |  |  | billed |  |  | 2017-06-05 | 0.5 | 0.5 | 2017-06-05 | Done
1614 | Euless Library |  | 2017-06-05 | QC |  |  | billed |  |  | 2017-06-06 | 2 | 2 | 2017-06-06 | Done
1632 | Upper Trinity Conservation | E170526a | 2017-05-26 | Setup project | Superceded |  | billed | [5 empty] | 2017-06-08 | Done
1631 | Brown Street Church Addition | E170525k | 2017-06-01 | Parking lot alternate? | It is not included in proposal |  | billed | [5 empty] | 2017-06-28 | Done
1614 | Euless Library | E170606d | 2017-06-06 | M sheets and demo base file |  |  | billed |  |  |  |  | 1 | 2017-06-06 | Done
1632 | Upper Trinity Conservation | E170602e | 2017-06-01 | Update base files | Superceded |  | billed | [5 empty] | 2017-06-08 | Done
1614 | Euless Library | E170606h | 2017-06-06 | Ryan's RCP |  |  | billed |  |  | 2017-06-06 | 2 | 2 | 2017-06-06 | Done
1632 | Upper Trinity Conservation | E170605c | 2017-06-05 | Some design criteria | Completed | To be added to IFR | billed | [5 empty] | 2017-07-03 | Done
1544 | The Community At Lake Ridge | E170606a | 2017-06-06 | Update base files |  | Part of IFR work | billed |  |  | 2017-06-15 | 1 | 1 | 2017-06-16 | Done
1632 | Upper Trinity Conservation | E170606e | 2017-06-06 | Update Revit file | Superceded | Part of IFR work | billed |  |  |  | 2 |  | 2017-07-03 | Done
1544 | The Community At Lake Ridge | E170614b | 2017-06-14 | Café gets: coffee makers, frapp blenders, and microwaves. Drink fridge. |  | IFC Work | billed |  |  | 2017-06-30 | 1 | 0 | 2017-07-02 | Done
1656 | Northern Hills Saferoom Addition |  | 2017-06-08 | Prepare for SV |  |  | billed |  |  | 2017-06-09 | 1 | 0.5 | 2017-06-10 | Done
1628 | Machine House |  | 2017-06-15 | Review Information, plan work |  |  | billed |  |  | 2017-06-20 | 1 | 1 | 2017-06-21 | Done
1544 | The Community At Lake Ridge |  | 2017-06-07 | PWR |  | Part of IFR work | billed |  |  | 2017-06-30 | 1 | 2 | 2017-07-02 | Done
1544 | The Community At Lake Ridge |  | 2017-06-07 | MP |  | Part of IFR work | billed |  |  | 2017-06-30 | 1 | 2 | 2017-07-02 | Done
1544 | The Community At Lake Ridge |  | 2017-06-07 | OL |  | Part of IFR work | billed |  |  | 2017-06-30 | 1 | 1 | 2017-07-02 | Done
1658 | Cleanpart Hazardous Materials Room | E170608b | 2017-06-08 | Prepare proposal |  |  | billed |  |  | 2017-06-09 | 1 | 1 | 2017-06-13 | Done
1606 | Tindall Storage Building |  | 2017-06-08 | IFR Work |  |  | billed |  |  | 2017-06-14 | 6 | 1 | 2017-06-15 | Done
1544 | The Community At Lake Ridge |  | 2017-06-08 | IFR Work |  |  | billed |  |  | 2017-06-19 | 3 | 4 | 2017-06-19 | Done
1478 | Handley Meadowbrook Rec Center |  |  | Do we move the utility transformer |  | IFC Work | billed | [5 empty] | 2017-06-20 | Done
1478 | Handley Meadowbrook Rec Center | E170508a | 2017-05-08 | Update base files |  | IFC Work | billed | [5 empty] | 2017-06-20 | Done
1392 | UNT Clark Bakery | E170516b | 2017-05-16 | Rev 1 options | No changes to electrical |  | billed | [5 empty] | 2017-06-15 | Done
1392 | UNT Clark Bakery | E170518b | 2017-05-18 | Update base files |  |  | billed |  |  | 2017-06-16 | 1 | 1 | 2017-06-16 | Done
1628 | Machine House | E170606j | 2017-06-07 | Crane information |  |  | billed |  |  |  | 1 |  | 2017-07-10 | Done
1621 | The Creek Church Phase II |  | 2017-06-08 | Addendum |  |  | billed | 1 |  | 2017-06-08 | 1 | 1 | 2017-06-08 | Done
1614 | Euless Library |  | 2017-06-08 | Check (e) wall packs |  | Site Visit | no |  |  |  |  | 2 | 2018-01-22 | Done
1392 | UNT Clark Bakery | E170608b | 2017-06-08 | Instructions for Rev 1 | No changes to electrical |  | billed |  |  | 2017-06-13 |  |  | 2017-06-15 | Done
1621 | The Creek Church Phase II | E170608c | 2017-06-08 | Addendum 01 |  |  | billed |  |  | 2017-06-08 | 1 | 1 | 2017-06-08 | Done
1421 | KXAS Remodel | E170727c | 2017-07-27 | LTG Submittal |  |  | billed |  |  | 2017-07-27 | 1 | 1 | 2017-07-27 | Done
1659 | The Joint Saginaw |  | 2017-06-11 | IFR |  |  | billed |  |  | 2017-06-11 | 2 | 2 | 2017-06-11 | Done
1659 | The Joint Saginaw |  | 2017-06-12 | IFR |  |  | billed |  |  | 2017-06-13 | 1 | 1 | 2017-06-13 | Done
1656 | Northern Hills Saferoom Addition |  | 2017-06-11 | Site Visit |  |  | billed |  |  | 2017-06-12 | 8 | 8 | 2017-06-12 | Done
1658 | Cleanpart Hazardous Materials Room |  | 2017-06-13 | Prepare proposal |  |  | billed |  |  | 2017-06-13 | 2 | 1 | 2017-06-13 | Done
1632 | Upper Trinity Conservation | E170613c | 2017-06-13 | Projector Information |  |  | billed |  |  | 2017-06-13 | 1 | 0.5 | 2017-06-13 | Done
1632 | Upper Trinity Conservation | E170613d | 2017-06-13 | GFCI locations |  |  | billed |  |  | 2017-06-13 | 1 | 0.5 | 2017-06-13 | Done
1632 | Upper Trinity Conservation | E170613e | 2017-06-13 | Monitor information |  |  | billed |  |  | 2017-06-13 | 1 | 0.5 | 2017-06-14 | Done
1632 | Upper Trinity Conservation | E170614l | 2017-06-14 | Contact Tri County Electric utility | Site: 1855 W. Hwy 199, Springtown, TX 76082 |  | billed |  |  | 2017-06-19 | 1 | 1 | 2017-06-27 | Done
1632 | Upper Trinity Conservation | E170613g | 2017-06-13 | Meeting minute review |  |  | billed |  |  |  |  | 1 | 2017-06-14 | Done
1632 | Upper Trinity Conservation | E170613f | 2017-06-13 | Data layouts |  |  | billed |  |  | 2017-06-13 | 1 | 1 | 2017-06-13 | Done
1632 | Upper Trinity Conservation |  | 2017-06-13 | EQUIP: Layouts, Sched |  |  | billed |  |  |  |  | 1 | 2017-06-14 | Done
1632 | Upper Trinity Conservation |  | 2017-06-13 | PWR: Service disc + meter |  |  | billed |  |  |  |  | 0.5 | 2017-06-14 | Done
1632 | Upper Trinity Conservation |  | 2017-06-13 | IFR work |  |  | billed |  |  | 2017-06-13 | 4 | 4 | 2017-06-13 | Done
1632 | Upper Trinity Conservation |  | 2017-06-14 | IFR work |  |  | billed |  |  | 2017-06-14 | 4 | 2 | 2017-06-14 | Done
1632 | Upper Trinity Conservation |  | 2017-06-14 | Coordinate with Tri County |  | IFC Work | billed | [5 empty] | 2017-07-08 | Done
1478 | Handley Meadowbrook Rec Center | E170605h | 2017-06-14 | Show relocated phone. Coord w/civil |  |  | billed |  |  | 2017-06-16 | 1 | 0.5 | 2017-06-16 | Done
1544 | The Community At Lake Ridge | E170623f | 2017-06-23 | Contact Utility Co. | Info in email |  | billed |  |  | 2017-07-11 |  |  | 2017-07-07 | Done
1604 | Botanic Garden Assessment | E170615a | 2017-06-15 | Create Assessment Schedule |  |  | billed |  |  | 2017-07-11 | 2 | 1 | 2017-07-21 | Done
1628 | Machine House | E170614c | 2017-06-14 | Add note regarding ventilation indicated on email. |  |  | billed |  |  |  |  | 1 | 2017-06-21 | Done
1477 | Eugene McCray Recreation Center | E170614d | 2017-06-14 | Implement markups |  |  | billed |  |  | 2017-06-16 | 2 | 3 | 2017-06-16 | Done
1477 | Eugene McCray Recreation Center | E170614g | 2017-06-14 | Update base files |  |  | billed |  |  | 2017-06-16 | 1 | 2 | 2017-06-16 | Done
1478 | Handley Meadowbrook Rec Center | E170614g | 2017-06-14 | Update base files |  |  | billed |  |  | 2017-06-16 | 1 | 1 | 2017-06-16 | Done
1631 | Brown Street Church Addition | E170615e | 2017-06-15 | Follow up on AV design |  |  | billed |  |  | 2017-06-22 |  |  | 2017-06-22 | Done
1606 | Tindall Storage Building |  | 2017-06-15 | LTG: check energy code schem | Closed for inactivity | IFC Work | billed | [5 empty] | 2017-09-26 | Done
1606 | Tindall Storage Building |  | 2017-06-15 | Add demolition riser | Closed for inactivity | IFC Work | billed | [5 empty] | 2017-09-26 | Done
1606 | Tindall Storage Building |  | 2017-06-15 | LTG egress | Closed for inactivity | IFC Work | billed | [5 empty] | 2017-09-26 | Done
1606 | Tindall Storage Building |  | 2017-06-15 | IFC Work | Closed for inactivity | Schedule | billed | [5 empty] | 2017-09-26 | Done
1544 | The Community At Lake Ridge |  | 2017-06-08 | Complete set up and print for planning |  |  | billed |  |  | 2017-06-17 | 1 | 2 | 2017-06-17 | Done
1392 | UNT Clark Bakery | E170615g | 2017-06-15 | Update RTU-3 |  |  | billed |  |  | 2017-06-15 | 0.5 | 0.5 | 2017-06-15 | Done
1544 | The Community At Lake Ridge |  | 2017-06-07 | LTG |  |  | billed |  |  | 2017-06-17 | 4 | 1 | 2017-06-17 | Done
1392 | UNT Clark Bakery | E170615b | 2017-06-15 | Set dated 6/19/2017 |  |  | billed |  |  | 2017-06-16 | 0.5 | 0.5 | 2017-06-16 | Done
1544 | The Community At Lake Ridge | E170623f | 2017-06-23 | Utility transformer location |  |  | billed | 1 |  | 2017-06-23 | 1 | 0.5 | 2017-06-23 | Done
1538 | UNT Coliseum Concourse | E170623h | 2017-06-23 | Issue Revision 1 |  |  | billed | 2 |  | 2017-06-23 | 2 | 1 | 2017-06-23 | Done
1660 | 1217 8th Avenue | E170615f | 2017-06-15 | Proposal |  |  | billed |  |  | 2017-06-15 | 1 | 0.5 | 2017-06-15 | Done
1654 | Mineral Wells Head Start | E170615g | 2017-06-15 | Received Approval |  |  | billed |  |  | 2017-06-15 | 0 | 0 | 2017-06-15 | Done
1478 | Handley Meadowbrook Rec Center | E170615c | 2017-06-15 | Implement markups |  |  | billed |  |  | 2017-06-16 | 2 | 1 | 2017-06-16 | Done
1392 | UNT Clark Bakery |  | 2017-06-15 | QC Job and Issue |  |  | billed |  |  | 2017-06-17 | 1 | 1 | 2017-06-19 | Done
1544 | The Community At Lake Ridge | E170615h | 2017-06-15 | Copy LFS from The Door |  |  | billed |  |  | 2017-06-17 | 1 | 1 | 2017-06-17 | Done
1478 | Handley Meadowbrook Rec Center | E170616a | 2017-06-16 | M Sheets |  |  | billed |  |  | 2017-06-16 | 1 | 1 | 2017-06-16 | Done
1477 | Eugene McCray Recreation Center | E170614e | 2017-06-16 | Specs |  |  | billed |  |  | 2017-06-19 | 1 | 1 | 2017-06-19 | Done
1477 | Eugene McCray Recreation Center | E170616b | 2017-06-16 | M Sheets |  |  | billed |  |  | 2017-06-17 | 1 | 2 | 2017-06-19 | Done
1477 | Eugene McCray Recreation Center |  | 2017-06-16 | QC |  |  | billed |  |  | 2017-06-17 | 1 | 1/ | 2017-06-19 | Done
1478 | Handley Meadowbrook Rec Center |  | 2017-06-16 | QC |  |  | billed |  |  | 2017-06-17 | 1 | 1 | 2017-06-20 | Done
1544 | The Community At Lake Ridge |  | 2017-06-19 | LTG |  |  | billed |  |  | 2017-06-17 | 2 | 2 | 2017-06-19 | Done
1477 | Eugene McCray Recreation Center |  | 2017-06-19 | Need receptacles in exercise room | Superceded |  | billed |  |  | 2017-08-03 | 1 |  | 2017-08-05 | Done
1544 | The Community At Lake Ridge | E170619a | 2017-06-19 | MP Sheets |  |  | billed |  |  | 2017-06-19 | 2 | 1 | 2017-06-19 | Done
1604 | Botanic Garden Assessment |  | 2017-06-19 | Team Meeting | @1:30 PM |  | billed |  |  | 2017-06-27 | 3 | 2 | 2017-06-27 | Done
1631 | Brown Street Church Addition | E170608a | 2017-06-13 | Update base files | Superceded |  | billed |  |  | 2017-06-28 | 1 |  | 2017-06-27 | Done
1604 | Botanic Garden Assessment | E170629g | 2017-06-29 | Schedule information | Complete plan w/Tim (2) emails |  | billed |  |  | 2017-07-12 | 2 | 1 | 2017-07-21 | Done
1620 | City of Weatherford Service Center | E170623e | 2017-06-23 | Update base files | Superceded |  | billed |  |  | 2017-06-29 | 1 | 0 | 2017-06-30 | Done
1477 | Eugene McCray Recreation Center |  | 2017-06-20 | Final QC |  |  | billed |  |  | 2017-08-03 |  | 1 | 2017-08-06 | Done
1478 | Handley Meadowbrook Rec Center | E170803a | 2017-08-03 | Add demo note to Kiln room | See email |  | billed | 1 |  | 2017-08-03 | 0.5 | 0.5 | 2017-08-04 | Done
1631 | Brown Street Church Addition | E170623a | 2017-06-23 | AVL information |  | IFC Work | billed |  |  | 2017-06-28 | 2 | 2 | 2017-06-28 | Done
1631 | Brown Street Church Addition | E170623b | 2017-06-23 | Update base files |  | IFC Work | billed |  |  | 2017-06-28 | 1 | 1 | 2017-06-28 | Done
1632 | Upper Trinity Conservation | E170623c | 2017-06-23 | Update base files |  | IFC Work | billed |  |  |  |  | 1 | 2017-06-26 | Done
1632 | Upper Trinity Conservation | E170623c | 2017-06-23 | Implement comments | AI in ACAD folder | IFC Work | billed |  |  |  |  | 0 | 2017-07-08 | Done
1538 | UNT Coliseum Concourse | E170623d | 2017-06-23 | Submittal log evaluation |  |  | billed |  |  | 2017-06-23 | 0.5 | 0.5 | 2017-06-23 | Done
1620 | City of Weatherford Service Center |  | 2017-06-27 | IFR Work |  |  | billed |  |  | 2017-06-29 | 4 | 3 | 2017-06-30 | Done
1631 | Brown Street Church Addition |  | 2017-06-29 | Specs |  |  | billed |  |  | 2017-07-06 | 1 | 1 | 2017-07-06 | Done
1544 | The Community At Lake Ridge | E170623g | 2017-06-23 | 50% comments |  | IFC Work | billed |  |  |  |  | 1 | 2017-07-02 | Done
1632 | Upper Trinity Conservation |  | 2017-06-27 | Utility SV | @1 PMT |  | billed |  |  | 2017-07-05 | 3 | 3 | 2017-07-05 | Done
1544 | The Community At Lake Ridge | E170614b | 2017-06-14 | need information on stacked w/d | Place residential side-by-side |  | billed |  |  |  |  | 0 | 2017-07-02 | Done
1538 | UNT Coliseum Concourse | E170705b | 2017-07-05 | Switchgear Submittal |  |  | billed |  |  | 2017-07-11 | 1 | 1 | 2017-07-11 | Done
1544 | The Community At Lake Ridge |  | 2017-06-23 | Coordinate with Utility | Superceded |  | billed | [5 empty] | 2017-08-18 | Done
1632 | Upper Trinity Conservation | E170626a | 2017-06-26 | Issue Progress Set |  |  | billed |  |  | 2017-06-26 | 1 | 1 | 2017-06-26 | Done
1632 | Upper Trinity Conservation | E170626b | 2017-06-26 | Specs |  | IFC Work | billed |  |  | 2017-07-08 | 1 | 1 | 2017-07-08 | Done
1632 | Upper Trinity Conservation | E170626c | 2017-06-26 | Review Arch set for coordination |  | IFC work | billed |  |  |  | 1 | 0.5 | 2017-07-08 | Done
1477 | Eugene McCray Recreation Center | E170626e | 2017-06-26 | Review 95CD set for coordination |  |  | billed |  |  | 2017-08-03 |  |  | 2017-08-06 | Done
1478 | Handley Meadowbrook Rec Center | E170803f | 2017-08-03 | Hood control box |  |  | billed | 2 |  | 2017-08-03 | 0.5 | 0.5 | 2017-08-04 | Done
1620 | City of Weatherford Service Center |  | 2017-06-27 | Send LTG file to Mallori and Tim |  |  | billed |  |  | 2017-06-27 | 1 | 1 | 2017-06-27 | Done
1631 | Brown Street Church Addition |  | 2017-06-27 | QC |  |  | billed |  |  | 2017-06-28 | 2 | 4 | 2017-06-29 | Done
1544 | The Community At Lake Ridge | E170619c | 2017-06-19 | Incorporate John's replies |  | IFC Work | billed | [5 empty] | 2017-08-18 | Done
1631 | Brown Street Church Addition |  | 2017-07-06 | Final QC |  |  | billed |  |  | 2017-07-06 | 2 | 2 | 2017-07-06 | Done
1631 | Brown Street Church Addition |  | 2017-06-28 | MP Sheets |  |  | billed |  |  | 2017-06-28 | 1 | 1 | 2017-06-29 | Done
1631 | Brown Street Church Addition |  | 2017-07-06 | Final COMCheck |  |  | billed |  |  | 2017-07-06 | 1 | 1 | 2017-07-06 | Done
1620 | City of Weatherford Service Center | E170629b | 2017-06-29 | Update abase |  |  | billed |  |  | 2017-06-29 | 1 | 1 | 2017-06-30 | Done
1544 | The Community At Lake Ridge | E170629c | 2017-06-29 | Update RCP and info |  | IFC Work | billed |  |  |  |  | 2 | 2017-07-02 | Done
1632 | Upper Trinity Conservation | E170629d | 2017-06-29 | Prelim Civil Set for Utility coord + | Shared with utility |  | billed |  |  |  |  | 0 | 2017-07-05 | Done
1632 | Upper Trinity Conservation | E170615d | 2017-06-15 | Answers to questions |  |  | billed |  |  | 2017-07-07 | 1 | 0 | 2017-07-08 | Done
1661 | Othello's Restaurant | E170629f | 2017-06-29 | Prelim Information | Review and strategize |  | billed |  |  |  | 1 |  | 2017-09-06 | Done
1632 | Upper Trinity Conservation |  | 2017-06-23 | IFC Work. Final QC |  |  | billed |  |  | 2017-07-07 |  | 1 | 2017-07-08 | Done
1544 | The Community At Lake Ridge |  | 2017-07-02 | Talk to Jim Morrow about K and P fixture | Email thread is ongoing |  | billed | [5 empty] | 2017-08-18 | Done
1544 | The Community At Lake Ridge |  | 2017-07-03 | Issue 50 % CD |  |  | billed |  |  |  |  | 2 | 2017-07-03 | Done
1628 | Machine House | E170629e | 2017-06-29 | Comments | Email has important info |  | billed |  |  | 2017-07-07 | 3 | 3 | 2017-07-10 | Done
1544 | The Community At Lake Ridge | E170703a | 2017-07-03 | Check RCP PDFs | Superceded | IFC Work | billed | [5 empty] | 2017-08-18 | Done
1628 | Machine House | E170705a | 2017-07-05 | Lighting fixture information in email |  |  | billed |  |  | 2017-07-07 |  | 1 | 2017-07-10 | Done
1632 | Upper Trinity Conservation |  | 2017-07-06 | Meter at the south end |  |  | billed |  |  | 2017-07-07 |  | 0 | 2017-07-08 | Done
1604 | Botanic Garden Assessment |  | 2017-07-06 | Zone 7 SV |  |  | billed |  |  | 2017-07-07 | 6 | 3 | 2017-07-07 | Done
1628 | Machine House |  | 2017-07-06 | 100 CD |  |  | billed |  |  | 2017-07-07 | 4 | 2 | 2017-07-10 | Done
1544 | The Community At Lake Ridge | E170705c | 2017-07-05 | Coordinate with Jim Morrow |  | Jim's information | billed | [5 empty] | 2017-08-18 | Done
1544 | The Community At Lake Ridge |  | 2017-06-23 | IFC Work |  |  | billed |  |  | 2017-08-07 |  | 4 | 2017-08-22 | Done
1604 | Botanic Garden Assessment | E170619b | 2017-06-19 | Use format provided by Scott |  |  | billed | [5 empty] | 2017-07-21 | Done
1632 | Upper Trinity Conservation | E170706a | 2017-07-06 | MP Sheets |  |  | billed |  |  | 2017-07-07 | 1 | 1 | 2017-07-08 | Done
1632 | Upper Trinity Conservation | E170706b | 2017-07-06 | Match border |  |  | billed |  |  | 2017-07-07 |  |  | 2017-07-08 | Done
1632 | Upper Trinity Conservation | E170706b | 2017-07-07 | Date 7/12 ISSUE FOR BID |  |  | billed |  |  | 2017-07-07 | 0.5 | 0.5 | 2017-07-08 | Done
MKT | Marketing | E170707b | 2017-07-07 | Resume to Patricia Simms |  |  | billed |  |  | 2017-07-08 |  | 1 | 2017-07-10 | Done
1544 | The Community At Lake Ridge | E170707c | 2017-07-07 | Call to set an appointment | Civil set on AI. See E170623f also |  | billed |  |  | 2017-07-11 | 0.5 | 0.5 | 2017-07-24 | Done
1632 | Upper Trinity Conservation |  | 2017-07-07 | Scan Utility form and fill it out |  |  | billed |  |  | 2017-07-08 | 0.5 | 1 | 2017-07-08 | Done
1632 | Upper Trinity Conservation | E170707a | 2017-07-07 | Update model |  |  | billed |  |  | 2017-07-08 |  | 1 | 2017-07-08 | Done
1632 | Upper Trinity Conservation |  | 2017-07-08 | COMCheck |  |  | billed |  |  | 2017-07-08 | 0.5 | 0.5 | 2017-07-08 | Done
1604 | Botanic Garden Assessment |  | 2017-07-08 | Report for Zone 1 |  |  | billed |  |  | 2017-07-12 | 2 | 6 | 2017-07-21 | Done
1544 | The Community At Lake Ridge | E170707e | 2017-07-10 | Update site plan and adjust lighting |  |  | billed |  |  |  |  | 2 | 2017-07-23 | Done
1544 | The Community At Lake Ridge | E170707f | 2017-07-10 | Add HD to restrooms in commons only |  |  | billed |  |  |  |  | 1 | 2017-07-23 | Done
1544 | The Community At Lake Ridge | E170707f | 2017-07-10 | Send updated site pole locations to John |  |  | billed |  |  | 2017-07-11 | 1 | 1 | 2017-07-12 | Done
1664 | Pool Corporation Warehouse Building |  | 2017-07-11 | Proposal |  |  | billed |  |  |  |  | 0.5 | 2017-07-24 | Done
1628 | Machine House | E170711a | 2017-07-11 | Add owners title block |  |  | billed |  |  |  |  | 1 | 2017-07-14 | Done
1661 | Othello's Restaurant | E170711b | 2017-07-11 | Voltage: 208/120 3ph |  | NTP | billed |  |  |  |  | 0.5 | 2017-09-22 | Done
1661 | Othello's Restaurant | E170711b | 2017-07-11 | Vent hood information |  | NTP | billed |  |  |  |  | 1 | 2017-09-20 | Done
1544 | The Community At Lake Ridge | E170712b | 2017-07-12 | Update site lighting from Jim |  |  | billed |  |  | 2017-07-12 | 1 | 1 | 2017-07-12 | Done
1628 | Machine House | E170712d | 2017-07-12 | Final comments |  |  | billed |  |  |  |  | 1 | 2017-07-14 | Done
1544 | The Community At Lake Ridge | E170712f | 2017-07-12 | Fixture changes |  |  | billed |  |  |  |  | 2 | 2017-07-23 | Done
1544 | The Community At Lake Ridge | E170714a | 2017-07-14 | Utiltiy co. site visit. |  |  | billed |  |  | 2017-08-02 | 4 | 4 | 2017-08-02 | Done
1544 | The Community At Lake Ridge | E170712g | 2017-07-12 | Add sensors to faucets, not to toilets |  |  | billed |  |  |  |  | 1 | 2017-07-23 | Done
1628 | Machine House |  | 2017-07-14 | Add sheet numbers. |  | Sheet numbers | billed |  |  |  |  | 1 | 2017-08-03 | Done
1592 | Deer Park Animal Shelter |  |  | Submittals |  |  | billed |  |  |  | 2 | 2 | 2017-07-17 | Done
1632 | Upper Trinity Conservation | E170717a | 2017-07-17 | Addendum # 1 |  |  | billed |  |  | 2017-07-17 | 1 | 1 | 2017-07-18 | Done
1544 | The Community At Lake Ridge | E170719a | 2017-07-19 | Address comments |  |  | billed |  |  |  |  | 1 | 2017-07-23 | Done
1572 | 350 Belknap | E170719b | 2017-07-19 | New data and power locations |  |  | billed | [5 empty] | 2017-07-23 | Done
1572 | 350 Belknap | E170719c | 2017-07-19 | Submittals |  |  | billed |  |  | 2017-07-20 | 1 | 1 | 2017-07-21 | Done
1604 | Botanic Garden Assessment |  | 2017-07-21 | Plan Zone 2 SVs |  |  | billed |  |  | 2017-07-28 | 0.5 | 0.5 | 2017-08-01 | Done
1572 | 350 Belknap |  | 2017-07-21 | Revision 1 |  |  | billed |  |  |  |  | 2 | 2017-07-21 | Done
1544 | The Community At Lake Ridge | E170720a | 2017-07-20 | Use concealed emergency fixtures |  |  | billed |  |  | 2017-07-23 |  | 1 | 2017-07-23 | Done
1544 | The Community At Lake Ridge | E170721b | 2017-07-21 | Contact AVL consultant | Email has contact info | AVL to call back on 7/31 | billed | [5 empty] | 2017-08-10 | Done
1477 | Eugene McCray Recreation Center | E170721c | 2017-07-21 | Incorporate 95% CD markups |  |  | billed |  |  | 2017-08-03 | 4 | 1 | 2017-08-05 | Done
1478 | Handley Meadowbrook Rec Center | E170803d | 2017-08-03 | More comments | TVs on weight room |  | billed | 3 |  | 2017-08-03 | 0.5 | 0.5 | 2017-08-04 | Done
1544 | The Community At Lake Ridge | E170721d | 2017-07-21 | Update Revit file |  |  | billed |  |  |  |  | 1 | 2017-07-23 | Done
1572 | 350 Belknap | E170720b | 2017-07-21 | Revision 1 |  |  | billed |  |  | 2017-07-21 | 2 | 2 | 2017-07-23 | Done
1544 | The Community At Lake Ridge |  | 2017-07-23 | Check Jim's LFS |  |  | billed |  |  | 2017-07-23 | 1 | 1 | 2017-07-23 | Done
1544 | The Community At Lake Ridge | E170723a | 2017-07-23 | Coordinate with Tim before issue |  |  | billed |  |  | 2017-07-24 |  | 1 | 2017-07-24 | Done
1544 | The Community At Lake Ridge |  | 2017-07-24 | COMCheck | Not needed according to John | Actual need | billed |  |  | 2017-08-08 |  |  | 2017-09-26 | Done
1478 | Handley Meadowbrook Rec Center | E170728e | 2017-07-28 | 95% CD Comments |  |  | billed | 4 |  | 2017-08-03 | 1 | 1 | 2017-08-04 | Done
1592 | Deer Park Animal Shelter | E170725a | 2017-07-25 | Misc Submittal |  |  | billed |  |  | 2017-07-25 | 1 | 1 | 2017-07-27 | Done
1544 | The Community At Lake Ridge | E170725b | 2017-07-25 | Deal with Incito info from Jim. | Add inverter to common areas |  | billed |  |  | 2017-08-07 |  |  | 2017-08-22 | Done
1620 | City of Weatherford Service Center | E170725c | 2017-07-25 | Implement comments |  |  | billed |  |  | 2017-07-25 | 2 | 2 | 2017-07-26 | Done
1621 | The Creek Church Phase II | E170725d | 2017-07-25 | Permit Comments | Comments addressed | Feedback from OWT | billed | [5 empty] | 2017-09-26 | Done
1624 | Fuego de Dios Church | E170725e | 2017-07-25 | Pole information |  |  | billed |  |  |  | 0.5 | 0.5 | 2017-07-25 | Done
1648 | OWT Offices | E170726a | 2017-07-26 | Revision 1 |  |  | billed |  |  | 2017-07-26 | 0.5 | 0.5 | 2017-07-26 | Done
1317 | Joyce Dr PD Station | E170726b | 2017-07-26 | Bidding Questions | Include Tim's change |  | billed |  |  | 2017-07-26 | 1 | 1 | 2017-07-27 | Done
1416 | DCCCD Eastfield Generator | E170726c | 2017-07-26 | Generator Submittal | Superceded | Sharon's approval | billed | [5 empty] | 2017-07-31 | Done
1317 | Joyce Dr PD Station | E170726e | 2017-07-26 | LTG Submittal |  |  | billed |  |  | 2017-07-26 | 1 | 1 | 2017-07-27 | Done
1544 | The Community At Lake Ridge | E170727b | 2017-07-27 | Update model | Superceded |  | billed |  |  | 2017-08-07 |  |  | 2017-08-10 | Done
1544 | The Community At Lake Ridge | E170727b | 2017-07-27 | Check 90% set for items | Will check model |  | billed |  |  | 2017-08-07 |  |  | 2017-08-10 | Done
1421 | KXAS Remodel | E170821d | 2017-08-21 | RFI # 12 |  |  | billed |  |  | 2017-08-22 |  | 0.5 | 2017-08-24 | Done
1544 | The Community At Lake Ridge | E170727c | 2017-07-27 | change concealed fixture to link |  |  | billed |  |  | 2017-08-07 |  | 1 | 2017-08-10 | Done
1478 | Handley Meadowbrook Rec Center | E170724a | 2017-07-24 | More electrical. See email. |  |  | billed | 5 |  | 2017-08-03 | 0.5 | 0.5 | 2017-08-04 | Done
1620 | City of Weatherford Service Center |  | 2017-07-31 | Add hood connections |  | Final comments | billed | [5 empty] | 2017-08-29 | Done
1477 | Eugene McCray Recreation Center | E170728b | 2017-07-28 | Verify RCP |  |  | billed |  |  | 2017-08-03 |  | 0.5 | 2017-08-05 | Done
1477 | Eugene McCray Recreation Center | E170728c | 2017-07-28 | 95% CD Comments |  |  | billed |  |  | 2017-08-03 |  | 1 | 2017-08-05 | Done
1478 | Handley Meadowbrook Rec Center | E170728d | 2017-07-28 | Verify RCP |  |  | billed |  |  | 2017-08-03 | 0.5 | 0.5 | 2017-08-03 | Done
1478 | Handley Meadowbrook Rec Center | E170721c | 2017-07-21 | Incorporate 95% CD markups |  |  | billed | 6 |  | 2017-08-03 | 2 | 1 | 2017-08-04 | Done
1604 | Botanic Garden Assessment | E170731a | 2017-07-31 | Incorporate Zone 1 comments |  |  | billed | ` |  | 2017-08-03 | 1 | 1 | 2017-08-03 | Done
1416 | DCCCD Eastfield Generator | E170731b | 2017-07-31 | Generator Submittal | 8/2 Got Sharon's approval |  | billed |  |  | 2017-08-03 | 2 | 2 | 2017-08-07 | Done
1544 | The Community At Lake Ridge | E170801a | 2017-08-01 | Update Revit file | Superceded |  | billed |  |  | 2017-08-07 |  |  | 2017-08-10 | Done
ops | Operations | E170802a | 2017-08-02 | NCTRCA renewal |  |  | billed |  |  | 2017-08-06 | 2 | 2 | 2017-08-07 | Done
1477 | Eugene McCray Recreation Center | E170801b | 2017-08-01 | Update site plan |  |  | billed |  |  | 2017-08-03 |  | 0.5 | 2017-08-05 | Done
1478 | Handley Meadowbrook Rec Center | E170801b | 2017-08-01 | Update site plan |  |  | billed | 2 |  | 2017-08-03 | 1 | 0.5 | 2017-08-03 | Done
1478 | Handley Meadowbrook Rec Center | E170802b | 2017-08-02 | Update Revit file | See title block file |  | billed | 1 |  | 2017-08-03 | 1 | 1 | 2017-08-03 | Done
1544 | The Community At Lake Ridge |  | 2017-08-02 | Utility coordination report to John |  |  | billed |  |  |  |  | 0.5 | 2017-08-03 | Done
1477 | Eugene McCray Recreation Center | E170802c | 2017-08-02 | Update Revit file |  |  | billed |  |  | 2017-08-03 |  | 0.5 | 2017-08-05 | Done
1631 | Brown Street Church Addition | E170802d | 2017-08-02 | RFI 13 - Panel H4 feed |  |  | billed |  |  | 2017-08-02 | 1 | 0.5 | 2017-08-02 | Done
1592 | Deer Park Animal Shelter | E170802e | 2017-08-02 | Generator Submittal |  |  | billed |  |  | 2017-08-03 |  | 0.5 | 2017-08-05 | Done
1604 | Botanic Garden Assessment | E170802f | 2017-08-02 | Revise Zone 1 report |  |  | billed |  |  | 2017-08-03 | 1 | 1 | 2017-08-03 | Done
1604 | Botanic Garden Assessment | E170802g | 2017-08-02 | Assess site 11 - boardwalk (zone 3) | See Renate's email and picture | Zone 3 assessment | billed | [5 empty] | 2017-09-26 | Done
1478 | Handley Meadowbrook Rec Center | E170728a | 2017-07-28 | MP Sheets | Info in email |  | billed | 7 |  | 2017-08-03 | 1 | 1 | 2017-08-04 | Done
1538 | UNT Coliseum Concourse | E170803b | 2017-08-03 | Panel Resubmittal |  |  | billed |  |  | 2017-08-04 | 1 | 0.5 | 2017-08-05 | Done
1477 | Eugene McCray Recreation Center | E170803d | 2017-08-03 | More comments | Double + Triple head in parking lot. |  | billed |  |  | 2017-08-03 |  | 0.5 | 2017-08-05 | Done
1538 | UNT Coliseum Concourse | E170803c | 2017-08-03 | LTG Submittal |  |  | billed |  |  | 2017-08-04 |  | 0.5 | 2017-08-05 | Done
1478 | Handley Meadowbrook Rec Center | E170626f | 2017-06-26 | Review 95CD set for coordination |  |  | billed | 8 |  | 2017-08-03 | 1 |  | 2017-08-06 | Done
1477 | Eugene McCray Recreation Center | E170803e | 2017-08-03 | MP Sheets | Info in email |  | billed |  |  | 2017-08-03 |  | 1 | 2017-08-05 | Done
1478 | Handley Meadowbrook Rec Center |  | 2017-06-20 | Final QC |  |  | billed | 9 |  | 2017-08-03 | 3 | 1 | 2017-08-06 | Done
1604 | Botanic Garden Assessment |  | 2017-08-03 | Zone 2 SV 1 |  |  | billed |  |  | 2017-08-08 |  | 2 | 2017-08-08 | Done
1544 | The Community At Lake Ridge | E170803g | 2017-08-03 | Update Revit file w/LTG sheets | Revit is superceded. Add LTG |  | billed |  |  | 2017-08-07 |  | 2 | 2017-08-21 | Done
1604 | Botanic Garden Assessment |  | 2017-08-04 | Quick SV in Zone 1 |  |  | billed |  |  | 2017-08-04 | 2 | 2 | 2017-08-04 | Done
1544 | The Community At Lake Ridge |  | 2017-08-04 | Follow up on AV design |  |  | billed |  |  | 2017-08-07 |  |  | 2017-08-07 | Done
1477 | Eugene McCray Recreation Center |  | 2017-08-04 | HVAC controls by P2 |  |  | billed |  |  | 2017-08-04 |  |  | 2017-08-05 | Done
1538 | UNT Coliseum Concourse | E170804b | 2017-08-04 | Check submittals vs guidelines. |  |  | billed |  |  | 2017-08-04 | 2 | 2 | 2017-08-05 | Done
1477 | Eugene McCray Recreation Center | E170724a | 2017-08-04 | More reqs |  |  | billed |  |  |  |  | 1 | 2017-08-05 | Done
1544 | The Community At Lake Ridge | E170805a | 2017-08-05 | AVL requirements | See email |  | billed |  |  | 2017-08-07 |  | 2 | 2017-08-18 | Done
1478 | Handley Meadowbrook Rec Center | E170805c | 2017-08-05 | Add reference to sheet M3.x |  |  | billed |  |  | 2017-08-06 |  |  | 2017-08-06 | Done
1477 | Eugene McCray Recreation Center | E170805c | 2017-08-05 | Locate CP-1 |  |  | billed |  |  | 2017-08-06 |  |  | 2017-08-06 | Done
ops | Operations | IFW | 2017-08-06 | Send Lesson 5 |  |  | billed |  |  | 2017-08-06 |  |  | 2017-08-06 | Done
1477 | Eugene McCray Recreation Center |  | 2017-08-06 | COMCheck |  |  | billed |  |  |  |  | 0.5 | 2017-08-06 | Done
1478 | Handley Meadowbrook Rec Center |  | 2017-08-06 | COMCheck |  |  | billed |  |  |  |  | 0.5 | 2017-08-06 | Done
1477 | Eugene McCray Recreation Center |  | 2017-08-06 | Final Documents |  |  | billed |  |  |  |  | 0.5 | 2017-08-06 | Done
1478 | Handley Meadowbrook Rec Center |  | 2017-08-06 | Final Documents |  |  | billed |  |  |  |  | 0.5 | 2017-08-06 | Done
1659 | The Joint Saginaw | E170807a | 2017-08-07 | Revise fixtures b and c |  |  | billed |  |  | 2017-08-07 | 0.5 | 0.5 | 2017-08-07 | Done
1572 | 350 Belknap | E170726c | 2017-08-07 | LTG Submittal |  |  | billed |  |  | 2017-08-07 |  | 0.5 | 2017-08-07 | Done
1394 | UNT Bruce Hall | E170807b | 2017-08-07 | LTG Submittal |  |  | billed |  |  | 2017-08-07 |  | 0.5 | 2017-08-07 | Done
1604 | Botanic Garden Assessment |  | 2017-08-08 | Zone 2 SV 2 |  |  | billed |  |  | 2017-08-09 | 3 | 3 | 2017-08-09 | Done
1544 | The Community At Lake Ridge | E170808a | 2017-08-08 | Update Revit model | Superceded |  | billed |  |  | 2017-08-09 |  |  | 2017-08-18 | Done
1544 | The Community At Lake Ridge | E170808a | 2017-08-08 | Update Site plan | Superceded |  | billed |  |  | 2017-08-09 |  |  | 2017-08-18 | Done
1544 | The Community At Lake Ridge | E170808a | 2017-08-08 | Incorporate comments |  |  | billed |  |  |  |  | 1 | 2017-08-21 | Done
1582 | Northern Hills Elementary Safe Room | E170808c | 2017-08-08 | NTP | See email for additional reqs | IFC Work | no | [5 empty] | 2018-01-21 | Done
1604 | Botanic Garden Assessment | E170808d | 2017-08-08 | Update Zone 2 names |  |  | billed |  |  | 2017-08-08 | 0.5 | 0.5 | 2017-08-08 | Done
1544 | The Community At Lake Ridge | E170811a | 2017-08-11 | New Schedule |  |  | billed | [5 empty] | 2017-08-18 | Done
1544 | The Community At Lake Ridge | E170811a | 2017-08-11 | 100 % CD Delivery | Due 8/21 -> 8/23 |  | billed |  |  | 2017-08-23 |  | 1 | 2017-08-22 | Done
1604 | Botanic Garden Assessment |  | 2017-04-17 | Schedule SV | 42906 |  | billed |  |  | 2017-06-20 |  |  | 2017-04-17 | Done
1632 | Upper Trinity Conservation | 1691 | 2017-06-08 | IFC | 42928 |  | billed |  |  | 2017-07-10 |  |  | 2017-07-12 | Done
1544 | The Community At Lake Ridge | Voltage: 208/120 3ph | 2017-05-29 | 90% CD | 42940 |  | billed |  |  | 2017-07-23 |  |  | 2017-07-23 | Done
1477 | Eugene McCray Recreation Center | E170614e | 2017-03-15 | IFC | 42955 |  | billed |  |  | 2017-08-07 |  |  | 2017-08-07 | Done
1478 | Handley Meadowbrook Rec Center | E170614e | 2017-03-15 | IFC | 42955 |  | billed |  |  | 2017-08-07 |  |  | 2017-08-07 | Done
1620 | City of Weatherford Service Center |  | 2017-07-25 | IFR | 42943 |  | billed |  |  | 2017-07-26 |  |  | 2017-07-26 | Done
1648 | OWT Offices |  | 2017-07-26 | Revision 1 | 42942 |  | billed |  |  | 2017-07-26 |  |  | 2017-07-26 | Done
1416 | DCCCD Eastfield Generator |  | 2017-08-07 | Submittal review | 42954 |  | billed |  |  | 2017-08-07 |  |  | 2017-08-07 | Done
1544 | The Community At Lake Ridge | Zone 1 final report | 2017-05-29 | 100% CD | Superceded by E170811a |  | billed |  |  | 2017-08-14 |  |  | 2017-08-11 | Done
1544 | The Community At Lake Ridge | E170731b | 2017-05-29 | IFC | Due 9/5 |  | billed |  |  | 2017-09-05 |  | 1 | 2017-09-05 | Done
1582 | Northern Hills Elementary Safe Room | E170614k | 2017-06-14 | 80% CD to the board | Superceded: E170811b |  | billed |  |  | 2017-08-15 |  |  | 2017-08-11 | Done
1563 | COFW Brennan Body Shop | ops | 2017-01-16 | SV | Closed for inactivity | Approval | billed | [5 empty] | 2017-09-26 | Done
1620 | City of Weatherford Service Center |  | 2017-08-11 | IFC |  | Review comments | billed | [5 empty] | 2017-08-29 | Done
1628 | Machine House |  | 2017-06-21 | IFC | Due 8/3 |  | billed |  |  | 2017-08-03 |  | 0.5 | 2017-08-03 | Done
1604 | Botanic Garden Assessment |  | 2017-07-31 | Zone 1 final report | 42951 |  | billed |  |  | 2017-08-04 |  | 0.5 | 2017-08-04 | Done
1392 | UNT Clark Bakery |  | 2017-08-07 | Submittals | Due:8/7/2017 |  | billed |  |  | 2017-08-07 |  | 0.5 | 2017-08-07 | Done
1572 | 350 Belknap |  | 2017-08-07 | Submittals | 42954 |  | billed |  |  | 2017-08-07 |  | 0.5 | 2017-08-07 | Done
1604 | Botanic Garden Assessment | E170629g | 2017-08-11 | Zone 2 Draft Report |  |  | billed |  |  | 2017-08-18 | 4 | 4 | 2017-08-18 | Done
1538 | UNT Coliseum Concourse | E170831e | 2017-08-31 | Grounding Submittal |  |  | billed | 4 |  | 2017-09-06 | 1 | 0.5 | 2017-09-06 | Done
1538 | UNT Coliseum Concourse | E170831f | 2017-08-31 | Cable Submittal |  |  | billed | 4 |  | 2017-09-06 | 1 | 0.5 | 2017-09-06 | Done
1604 | Botanic Garden Assessment | E170629g | 2017-08-11 | Zone 3 Final Report | E171019b |  | billed |  |  | 2017-10-19 | 1 | 1 | 2017-10-19 | Done
1654 | Mineral Wells Head Start | E170905c | 2017-09-05 | Update base files | 11/20 Project Cancelled | New Scope | billed | 8 |  | 2017-09-27 |  |  | 2017-11-20 | Done
1544 | The Community At Lake Ridge | E171002a | 2017-10-02 | AVL final set revisions | Rev 2 - Addendum 2. See email |  | billed |  |  | 2017-10-04 |  | 1 | 2017-11-22 | Done
1667 | Modern Acupunture - Plano | E171103e | 2017-11-03 | Set up project |  |  | billed |  |  | 2017-11-08 |  | 1 | 2017-11-11 | Done
1667 | Modern Acupunture - Plano |  | 2017-11-07 | Review Set Due |  |  | billed |  |  | 2017-11-10 |  | 6 | 2017-11-13 | Done
1594 | Pflugerville AS | E170809a | 2017-08-09 | Update brackgrounds |  |  | billed |  |  | 2017-08-14 | 1 | 0.5 | 2017-08-14 | Done
1594 | Pflugerville AS | E1708011c | 2017-08-11 | Remove gate |  |  | billed |  |  | 2017-08-14 | 1 | 0.5 | 2017-08-14 | Done
1594 | Pflugerville AS | E170809a | 2017-08-14 | Re-issue IFC | Dated 8/15 |  | billed |  |  | 2017-08-14 |  | 0.5 | 2017-08-14 | Done
1544 | The Community At Lake Ridge | E170810a | 2017-08-14 | Update site plan |  |  | billed |  |  |  |  | 0.5 | 2017-08-18 | Done
1662 | Heritage Glenn Office Park | E170812a | 2017-08-14 | Project Files |  |  | billed |  |  |  |  | 1 | 2017-08-15 | Done
1666 | The Joint - Glade Parks | E170812b | 2017-08-14 | Project files | CAD and PDF |  | billed |  |  | 2017-08-14 | 1 | 2 | 2017-08-14 | Done
1654 | Mineral Wells Head Start | E170814a | 2017-08-14 | Study Schematic |  |  | billed |  |  |  |  | 0 | 2017-08-28 | Done
1582 | Northern Hills Elementary Safe Room | E170814b | 2017-08-14 | Existing files |  | IFC Work | no | [5 empty] | 2018-01-21 | Done
1662 | Heritage Glenn Office Park |  | 2017-08-15 | IFC work |  | Border | billed |  |  | 2017-08-15 | 2 | 2 | 2017-08-15 | Done
1666 | The Joint - Glade Parks |  | 2017-08-15 | IFC work | Left over | Tim's MP sheets | no | [5 empty] | 2018-01-28 | Done
1661 | Othello's Restaurant |  | 2017-08-15 | IFC Work |  | DWG files | billed |  |  |  |  | 3 | 2017-09-22 | Done
1613 | Norman Hotel | E170815a | 2017-08-15 | SV |  |  | billed |  |  | 2017-08-16 | 6 | 8 | 2017-08-16 | Done
1582 | Northern Hills Elementary Safe Room |  | 2017-08-15 | Review design guidelines |  | IFC Work | no | [5 empty] | 2018-01-21 | Done
1538 | UNT Coliseum Concourse | E170815b | 2017-08-15 | Follow up on horizontal conduits |  |  | billed |  |  | 2017-08-16 |  | 1 | 2017-08-16 | Done
1661 | Othello's Restaurant | E170815c | 2017-08-15 | Kitchen work |  | Project files | billed |  |  |  |  | 3 | 2017-09-20 | Done
1544 | The Community At Lake Ridge | E170816a | 2017-08-16 | Update Revit file |  |  | billed |  |  | 2017-08-17 |  | 1 | 2017-08-18 | Done
1544 | The Community At Lake Ridge | E170816a | 2017-08-16 | Check changes |  |  | billed |  |  | 2017-08-17 |  | 2 | 2017-08-21 | Done
1666 | The Joint - Glade Parks |  | 2017-08-18 | IFR Work | Include MP Sheets |  | billed |  |  | 2017-08-18 | 1 | 1 | 2017-08-18 | Done
1662 | Heritage Glenn Office Park |  | 2017-08-18 | Project files | Project set up | Need border, RCP and markups | billed |  |  |  |  | 4 | 2017-09-05 | Done
1662 | Heritage Glenn Office Park |  | 2017-08-18 | Review Set work |  |  | billed |  |  | 2017-08-23 | 6 | 4 | 2017-09-05 | Done
1544 | The Community At Lake Ridge |  | 2017-08-18 | Confirm 1-hr rating of elect room |  |  | billed |  |  | 2017-08-21 |  | 0 | 2017-08-21 | Done
1544 | The Community At Lake Ridge | E170821a | 2017-08-21 | Updated MP sheets |  |  | billed |  |  | 2017-08-21 |  | 1 | 2017-08-22 | Done
1592 | Deer Park Animal Shelter | E170821b | 2017-08-21 | RFI # 2 |  |  | billed |  |  | 2017-08-21 | 0.5 | 0.5 | 2017-08-21 | Done
1538 | UNT Coliseum Concourse | E170821c | 2017-08-21 | Div 28 Submittal |  |  | billed |  |  | 2017-08-22 |  | 1 | 2017-08-24 | Done
1421 | KXAS Remodel | E170822b | 2017-08-22 | Review power and data plans |  |  | billed |  |  | 2017-08-23 | 1 | 1 | 2017-08-23 | Done
1668 | Johnson Equipment | E170906c | 2017-09-06 | Prepare proposal |  |  | billed | 2 |  | 2017-09-06 | 0.5 | 0.5 | 2017-09-06 | Done
1631 | Brown Street Church Addition | E170901a | 2017-09-06 | Prepare ASA |  |  | billed | 1 |  | 2017-09-06 | 0.5 | 0.5 | 2017-09-06 | Done
1582 | Northern Hills Elementary Safe Room | E170821e | 2017-08-21 | 50% CD Meeting | 9/27 Asked Tim for new schedule Need a new schedule | New Schedule | no | 7 |  | 2017-09-28 |  |  | 2018-01-21 | Done
1582 | Northern Hills Elementary Safe Room | E170821e | 2017-08-21 | Revised 50% CD due |  | New Schedule | billed |  |  | 2017-10-02 |  |  | 2018-01-21 | Done
1544 | The Community At Lake Ridge | E171003a | 2017-10-03 | Permit Comments | See email for instructions on generic comments |  | billed |  |  | 2017-10-04 |  | 1 | 2017-11-22 | Done
1631 | Brown Street Church Addition | E171017b | 2017-10-17 | LTG Resubmittal |  |  | billed |  |  | 2017-10-19 | 1 | 1 | 2017-10-19 | Done
1572 | 350 Belknap | E170822a | 2017-08-22 | Revision 2 |  | Revision number | billed |  |  | 2017-08-23 | 1 | 1 | 2017-08-23 | Done
1421 | KXAS Remodel | E170905a | 2017-09-05 | LTG Controls Submittal |  |  | billed |  |  | 2017-09-05 | 1 | 1 | 2017-09-05 | Done
1620 | City of Weatherford Service Center | E170823a | 2017-08-23 | Final set |  | Mallori's comments | billed | [5 empty] | 2017-08-29 | Done
1416 | DCCCD Eastfield Generator | E170824d | 2017-08-24 | Gear Submittal |  |  | billed |  |  | 2017-08-25 |  | 1 | 2017-08-30 | Done
1559 | Southlake MOB Shell | p11-11 | 2017-08-28 | Revised pole detail |  |  | billed |  |  | 2017-08-28 | 0.5 | 0.5 | 2017-08-28 | Done
1654 | Mineral Wells Head Start |  | 2017-08-28 | SV 2 |  |  | billed |  |  | 2017-08-28 | 4 | 4 | 2017-08-28 | Done
1615 | Celeris (2017) |  | 2017-08-28 | Review Panel Schedules |  |  | billed |  |  | 2017-08-28 | 1 | 1 | 2017-08-28 | Done
1615 | Celeris (2017) |  | 2017-08-28 | Review ATT 17-9998 |  |  | billed |  |  | 2017-08-28 | 1 | 1 | 2017-08-28 | Done
1620 | City of Weatherford Service Center | E170823a | 2017-08-29 | IFC |  |  | billed |  |  | 2017-08-29 | 1 | 2 | 2017-08-29 | Done
1659 | The Joint Saginaw | E170829a | 2017-08-29 | RTU Data |  |  | billed |  |  | 2017-08-29 |  | 0.5 | 2017-08-29 | Done
1659 | The Joint Saginaw | E170828a | 2017-08-29 | Comments |  |  | billed |  |  | 2017-08-29 |  | 2 | 2017-08-29 | Done
1666 | The Joint - Glade Parks | E170828b | 2017-08-29 | Comments |  |  | billed |  |  | 2017-08-29 |  | 2 | 2017-08-30 | Done
1544 | The Community At Lake Ridge | E170823b | 2017-08-29 | Update Site Plan | Superceded |  | billed | [5 empty] | 2017-09-04 | Done
1544 | The Community At Lake Ridge | E170823c | 2017-08-29 | Update Revit File | Superceded |  | billed | [5 empty] | 2017-09-04 | Done
1632 | Upper Trinity Conservation | E170825a | 2017-08-29 | Electrical Submittal |  |  | billed |  |  |  |  | 2 | 2017-08-31 | Done
1590 | Prairie Plaza |  | 2017-09-06 | Verify proposal is still good |  |  | billed | 3 |  | 2017-09-06 | 0.5 | 0.5 | 2017-09-06 | Done
1544 | The Community At Lake Ridge | E170828d | 2017-08-29 | Set for review by owner |  |  | billed | [5 empty] | 2017-09-04 | Done
1600 | Gun Experience | E170828f | 2017-08-29 | KO Meeting | @2 PM |  | billed |  |  | 2017-08-30 |  | 2 | 2017-08-30 | Done
1544 | The Community At Lake Ridge | E170829b | 2017-08-29 | Add viewport for NBS on E2.1 |  |  | billed |  |  |  |  | 0.5 | 2017-09-04 | Done
1544 | The Community At Lake Ridge | E170829b | 2017-08-29 | Add TV locations | In AVL package | John's info | billed | [5 empty] | 2017-11-22 | Done
1544 | The Community At Lake Ridge |  | 2017-08-31 | Final house lighting layout |  |  | billed |  |  |  |  | 1 | 2017-11-22 | Done
1544 | The Community At Lake Ridge | E170830a | 2017-08-31 | Update site plan |  |  | billed |  |  |  |  | 1 | 2017-09-04 | Done
1544 | The Community At Lake Ridge | E170831a | 2017-08-31 | move iwh-2 | See email |  | billed |  |  |  |  | 0.5 | 2017-09-04 | Done
1544 | The Community At Lake Ridge | E170831b | 2017-08-31 | Update Revit file |  |  | billed |  |  |  |  | 1 | 2017-09-04 | Done
1538 | UNT Coliseum Concourse | E170831d | 2017-08-31 | Fire Alarm submittal review |  |  | billed |  |  | 2017-08-31 | 0.5 | 0.5 | 2017-08-31 | Done
1662 | Heritage Glenn Office Park |  | 2017-09-06 | LTG |  |  | billed | 5 |  | 2017-09-06 | 4 | 6 | 2017-09-08 | Done
1657 | Cleburne SWAT |  | 2017-09-06 | Set up project |  |  | billed | 1 |  | 2017-09-09 |  | 3 | 2017-09-09 | Done
1544 | The Community At Lake Ridge | E170831g | 2017-08-31 | Specifications |  |  | billed |  |  | 2017-09-01 |  | 1 | 2017-09-05 | Done
1544 | The Community At Lake Ridge | E170831a | 2017-08-31 | Add disposal | See email |  | billed |  |  |  |  | 0.5 | 2017-09-04 | Done
1544 | The Community At Lake Ridge | E170901b | 2017-09-01 | Updated site lighting fixture locations |  |  | billed |  |  |  |  | 0.5 | 2017-09-04 | Done
1538 | UNT Coliseum Concourse | E170904a | 2017-09-04 | No-horizontal-conduit revision | Item has been resolved | Debbie's instructions | billed | [5 empty] | 2017-09-25 | Done
1544 | The Community At Lake Ridge | E170904b | 2017-09-04 | M Sheets |  |  | billed |  |  |  |  | 1 | 2017-09-04 | Done
1544 | The Community At Lake Ridge | E170904b | 2017-09-04 | P Sheets |  |  | billed |  |  |  |  | 1 | 2017-09-04 | Done
1620 | City of Weatherford Service Center |  | 2017-09-05 | PWR and IT Coord Mtg |  | Date Confirmation | billed |  |  | 2017-09-11 |  |  | 2017-08-29 | Done
1421 | KXAS Remodel | E170906g | 2017-09-06 | RFI # 13 |  |  | billed | 1 |  | 2017-09-06 |  | 0.5 | 2017-09-06 | Done
1662 | Heritage Glenn Office Park |  | 2017-09-06 | PWR |  |  | billed |  |  | 2017-09-07 |  | 1 | 2017-09-08 | Done
1662 | Heritage Glenn Office Park |  | 2017-09-06 | OL |  |  | billed |  |  | 2017-09-07 |  | 1 | 2017-09-08 | Done
1654 | Mineral Wells Head Start | E170905d | 2017-09-05 | Review design guidelines | Closed: project cancelled | IFC Work | billed | [5 empty] | 2017-11-21 | Done
1544 | The Community At Lake Ridge | E170905e | 2017-09-05 | LTG Revisions per John |  |  | billed |  |  |  |  | 1 | 2017-09-05 | Done
1604 | Botanic Garden Assessment | E170629g | 2017-08-11 | Zone 2 Final Report |  |  | billed | 2 |  | 2017-09-09 |  | 1 | 2017-09-10 | Done
1604 | Botanic Garden Assessment | E170905b | 2017-09-05 | Zone 2 Corrections |  | Correction work | billed |  |  | 2017-09-09 | 1 | 1 | 2017-09-09 | Done
1600 | Gun Experience |  | 2017-09-06 | DD Work |  |  | billed |  |  | 2017-09-11 | 8 | 5 | 2017-09-11 | Done
1582 | Northern Hills Elementary Safe Room | E170828c | 2017-08-29 | Preliminary floor plan | Need to set up for SV |  | billed |  |  | 2017-09-12 |  | 0.5 | 2017-09-12 | Done
1530 | Brennan Drop-off Changes | E170926f | 2017-09-26 | Review meeting minutes for Design Criteria |  | IFC Work | billed | 5 |  | 2017-09-27 |  | 1 | 2017-10-13 | Done
1582 | Northern Hills Elementary Safe Room | E170821e | 2017-08-21 | SD Meeting | Didn’t happen |  | billed |  |  | 2017-09-13 | 6 |  | 2017-09-26 | Done
1604 | Botanic Garden Assessment | E170629g | 2017-08-11 | Zone 3 Draft Report |  |  | billed |  |  | 2017-09-19 |  | 2 | 2017-09-22 | Done
1582 | Northern Hills Elementary Safe Room | E170821e | 2017-08-21 | 50% CD due | Superceded | New schedule | no |  |  | 2017-09-20 |  |  | 2018-01-21 | Done
1538 | UNT Coliseum Concourse | E170906d | 2017-09-06 | Revised FA Submittal |  |  | billed | 6 |  | 2017-09-06 |  | 0.5 | 2017-09-06 | Done
1538 | UNT Coliseum Concourse | E170906e | 2017-09-06 | Raceways Submittal |  |  | billed | 6 |  | 2017-09-06 |  | 0.5 | 2017-09-06 | Done
1538 | UNT Coliseum Concourse | E170906f | 2017-09-06 | Identification Submittal |  |  | billed | 6 |  | 2017-09-06 |  | 0.5 | 2017-09-06 | Done
1421 | KXAS Remodel | E170906h | 2017-09-06 | RFI # 14 |  |  | billed | 2 |  | 2017-09-06 |  | 1.5 | 2017-09-06 | Done
1421 | KXAS Remodel | E170911f | 2017-09-11 | Revision 3 |  |  | billed |  |  | 2017-09-12 | 1 | 0.5 | 2017-09-12 | Done
1621 | The Creek Church Phase II | E170907c | 2017-09-07 | Rev 2 | See 170725 |  | billed | 3 |  | 2017-09-09 |  | 1 | 2017-09-10 | Done
1530 | Brennan Drop-off Changes |  | 2017-09-06 | KO Meeting | @1PM at EoA offices |  | billed |  |  | 2017-09-18 |  | 1 | 2017-09-18 | Done
1657 | Cleburne SWAT | E170907a | 2017-09-07 | Answers to questions |  |  | billed |  |  | 2017-09-10 |  | 0.5 | 2017-09-10 | Done
1648 | OWT Offices | E170907b | 2017-09-07 | Revision 2 |  |  | billed |  |  | 2017-09-07 | 1 | 1 | 2017-09-07 | Done
ops | Operations |  |  | Submit Lesson # 5 |  |  | billed | 4 |  | 2017-09-09 |  | 1 | 2017-09-10 | Done
ops | Operations |  | 2017-09-08 | Lunch with Tiner | Call to confirm date |  | billed |  |  | 2017-09-18 |  |  | 2017-09-18 | Done
1662 | Heritage Glenn Office Park | E170909a | 2017-09-08 | M Sheets |  |  | billed |  |  | 2017-09-08 |  | 1 | 2017-09-08 | Done
1600 | Gun Experience |  | 2017-09-08 | Set up project |  |  | billed | 5 |  | 2017-09-09 |  | 3 | 2017-09-11 | Done
1661 | Othello's Restaurant | E170906a | 2017-09-06 | Set up project | Superceded |  | billed | 6 |  | 2017-09-09 |  |  | 2017-09-11 | Done
1661 | Othello's Restaurant | E170907d | 2017-09-09 | Incorporate info on lights | Info in email | IFR Work | billed |  |  |  |  | 0.5 | 2017-09-21 | Done
1572 | 350 Belknap | E170907e | 2017-09-09 | LTG control Submittal |  |  | billed |  |  | 2017-09-10 |  | 1 | 2017-09-12 | Done
1416 | DCCCD Eastfield Generator | E170824d | 2017-09-09 | FP on change order | 9/14 Sent Signed RCO to Sharon 9/14 Got RCO from Christian 9/13 Sent offcial form to Christian for signature 9/12 CO approved (see E170912c) 9/11 Sent email to Michael for approval |  | billed |  |  | 2017-09-14 |  | 1 | 2017-09-14 | Done
1600 | Gun Experience |  | 2017-09-28 | Site Photometrics |  |  | billed |  |  | 2017-09-29 |  |  | 2017-09-30 | Done
ops | Operations |  | 2017-09-09 | Send money to Jose |  |  | billed | 1 |  | 2017-09-14 |  |  | 2017-09-13 | Done
1572 | 350 Belknap | E170908a | 2017-09-09 | Revision 3 | Talk to Tim to set issue date. Rev done, ready to PDF |  | billed |  |  | 2017-09-11 |  |  | 2017-09-12 | Done
1621 | The Creek Church Phase II | E170908b | 2017-09-09 | MP Sheets | See email for additional reqs | Rev 2 work | billed | [5 empty] | 2017-09-12 | Done
1669 | Sleep In Hotel | Update files. | 2017-09-09 | Prepare proposal |  |  | billed |  |  | 2017-09-09 |  | 1 | 2017-09-10 | Done
1600 | Gun Experience |  | 2017-09-09 | One-line diagram |  |  | billed |  |  | 2017-09-10 |  | 2 | 2017-09-12 | Done
1662 | Heritage Glenn Office Park | E170909a | 2017-09-10 | Update base files | Superceded | Architectural | billed | [5 empty] | 2017-09-26 | Done
1572 | 350 Belknap | E170908a | 2017-09-09 | Revision 3 |  | Tim's input | billed |  |  |  |  | 1 | 2017-09-13 | Done
1621 | The Creek Church Phase II |  | 2017-09-10 | Deliver Rev 02 |  |  | billed |  |  | 2017-09-11 |  | 0.5 | 2017-09-12 | Done
1572 | 350 Belknap |  | 2017-09-10 | Deliver Rev 3 |  |  | billed |  |  | 2017-09-11 |  | 1 | 2017-09-12 | Done
1657 | Cleburne SWAT |  | 2017-09-10 | IFC Work |  |  | billed |  |  | 2017-09-10 |  | 3 | 2017-09-10 | Done
1600 | Gun Experience | E170831c | 2017-09-10 | Lighting Site Plan |  |  | billed |  |  |  |  | 1 | 2017-09-12 | Done
1600 | Gun Experience | E171116b | 2017-11-16 | Update Revit File |  |  | billed | 1 |  | 2017-11-16 |  | 1 | 2017-11-16 | Done
1538 | UNT Coliseum Concourse | E170911c | 2017-09-11 | LTG control Submittal |  |  | billed |  |  | 2017-09-12 |  | 0.5 | 2017-09-12 | Done
1670 | Brookhaven Generator | E170911d | 2017-09-11 | Fp on mkt meeting with Sharon |  |  | billed |  |  | 2017-09-13 |  |  | 2017-09-12 | Done
1654 | Mineral Wells Head Start | E170911e | 2017-09-11 | Review approved PDFs | Closed: project cancelled | New Scope | billed | 8 |  | 2017-09-27 |  |  | 2017-11-21 | Done
1661 | Othello's Restaurant | E170906a | 2017-09-11 | Update files. | Email has important info |  | billed |  |  | 2017-09-18 |  | 2 | 2017-09-18 | Done
1421 | KXAS Remodel | E170927b | 2017-09-27 | Review Conduit Submittal |  |  | billed |  |  | 2017-09-27 |  | 1 | 2017-09-27 | Done
1600 | Gun Experience | E170911b | 2017-09-11 | Send LTG file to Tim |  |  | billed |  |  | 2017-09-12 |  | 0.5 | 2017-09-12 | Done
1615 | Celeris (2017) |  | 2017-09-11 | Call Gabe to talk about cables |  |  | billed |  |  | 2017-09-12 |  | 1 | 2017-09-12 | Done
1670 | Brookhaven Generator | E170911d | 2017-09-12 | Proposal Meeting | See email for directions |  | billed |  |  | 2017-09-18 | 3 | 3 | 2017-09-19 | Done
1582 | Northern Hills Elementary Safe Room | E170912a | 2017-09-12 | Alternate ideas |  |  | no |  |  | 2018-01-21 |  | 1 | 2018-01-21 | Done
1631 | Brown Street Church Addition | E170912b | 2017-09-12 | Implement VE items | Update revit file |  | billed |  |  | 2017-09-18 |  | 1 | 2017-09-19 | Done
1600 | Gun Experience |  | 1902-06-30 | Finish and issue DD set |  |  | billed |  |  |  |  | 2 | 2017-09-12 | Done
1600 | Gun Experience |  | 2017-09-12 | MP Sheets |  |  | billed |  |  | 2017-09-12 |  | 1 | 2017-09-12 | Done
1657 | Cleburne SWAT |  | 2017-09-12 | Modify floor plan |  | new base file | billed |  |  |  |  | 1 | 2017-09-19 | Done
1657 | Cleburne SWAT |  | 2017-09-12 | MP Sheets |  | MP sheets | billed |  |  |  |  | 1 | 2017-09-19 | Done
1538 | UNT Coliseum Concourse | E170912d | 2017-09-12 | FA resubmittal |  |  | billed |  |  | 2017-09-12 | 1 | 0.5 | 2017-09-12 | Done
1538 | UNT Coliseum Concourse | E170912e | 2017-09-12 | LTG control Submittal | Duplicate see E170911c |  | billed |  |  | 2017-09-12 | 1 |  | 2017-09-12 | Done
1654 | Mineral Wells Head Start | E170913a | 2017-09-13 | Update base files | Closed: project cancelled | IFC Work | billed | [5 empty] | 2017-11-21 | Done
1661 | Othello's Restaurant | E170906a | 2017-09-13 | Additional power reqs | See email for information | IFC Work | billed |  |  |  |  | 1 | 2017-09-21 | Done
1654 | Mineral Wells Head Start | E170928b | 2017-09-28 | Add equipment to design | Closed: project cancelled | New Scope | billed |  |  | 2017-09-29 |  |  | 2017-11-21 | Done
1600 | Gun Experience | E170913c | 2017-09-13 | Implement L gun range ltg info |  |  | billed |  |  | 2017-09-14 |  | 1 | 2017-09-14 | Done
1582 | Northern Hills Elementary Safe Room | E170913d | 2017-09-13 | DD Set due |  |  | billed |  |  | 2017-09-22 |  | 1 | 2017-09-25 | Done
1662 | Heritage Glenn Office Park | E170913e | 2017-09-13 | Update base files |  |  | billed |  |  | 2017-09-18 |  | 2 | 2017-09-25 | Done
1654 | Mineral Wells Head Start | E170913f | 2017-09-13 | Update base files | Closed: project cancelled | IFC Work | billed | [5 empty] | 2017-11-21 | Done
1600 | Gun Experience | E170914a | 2017-09-14 | Preliminary transformer size |  |  | billed |  |  |  |  | 0.5 | 2017-09-14 | Done
1530 | Brennan Drop-off Changes | E170914b | 2017-09-14 | Schedule coordination |  |  | billed |  |  |  |  | 0.5 | 2017-09-14 | Done
1530 | Brennan Drop-off Changes | E170914d | 2017-09-14 | Review SD package for KO Mtg |  |  | billed |  |  | 2017-09-18 |  |  | 2017-09-18 | Done
1531 | MLK Drop-off Changes | E170914d | 2017-09-14 | Review SD package for KO Mtg |  |  | billed |  |  | 2017-09-18 |  |  | 2017-09-18 | Done
1532 | Old Hemphill Drop-off Changes | E170914d | 2017-09-14 | Review SD package for KO Mtg |  |  | billed |  |  | 2017-09-18 |  |  | 2017-09-18 | Done
1624 | Fuego de Dios Church | E170914e | 2017-09-14 | Update site plan |  |  | billed |  |  | 2017-09-14 | 0.5 | 0.5 | 2017-09-14 | Done
ops | Operations |  | 2017-09-21 | Lesson # 7. |  |  | billed |  |  | 2017-10-08 |  |  | 2017-10-08 | Done
1421 | KXAS Remodel | E170927b | 2017-09-27 | Receptacle resubmittal |  |  | billed |  |  | 2017-09-28 |  | 0.5 | 2017-10-06 | Done
1544 | The Community At Lake Ridge | E171116c | 2017-11-16 | Update Revit model | See changes in PDF |  | billed |  |  | 2017-11-20 |  | 1 | 2017-11-22 | Done
1661 | Othello's Restaurant |  | 2017-09-27 | IFC | Dated 10/10/17. Due Monday 10/9 |  | billed |  |  | 2017-10-05 |  | 0.5 | 2017-10-09 | Done
1592 | Deer Park Animal Shelter | E171107a | 2017-11-07 | RFI 8 - Door strikes |  |  | billed |  |  | 2017-11-07 | 1 | 0.5 | 2017-11-07 | Done
1600 | Gun Experience | E171117d | 2017-11-19 | Faucet/dryer requirements |  |  | billed |  |  | 2017-11-29 |  | 1 | 2017-11-29 | Done
mkt | Marketing |  | 2017-10-16 | MKT Description for DFW engineers |  |  | billed |  |  | 2017-10-17 |  | 1 | 2017-10-17 | Done
1604 | Botanic Garden Assessment |  | 2017-11-07 | Prepare and send Zone 5 draft to Tim |  |  | billed |  |  | 2017-11-07 | 1 | 1 | 2017-11-07 | Done
1600 | Gun Experience | E171118a | 2017-11-19 | New LFS |  |  | billed |  |  | 2017-11-24 |  | 4 | 2017-11-25 | Done
1600 | Gun Experience | E170915a | 2017-09-15 | Implement comments |  |  | billed |  |  | 2017-09-17 |  | 1 | 2017-09-17 | Done
1600 | Gun Experience | E170916a | 2017-09-16 | Update base files |  |  | billed |  |  | 2017-09-17 |  | 1 | 2017-09-17 | Done
1600 | Gun Experience | E170916a | 2017-09-16 | MP Sheets |  |  | billed |  |  | 2017-09-17 |  | 1 | 2017-09-17 | Done
1600 | Gun Experience | E170915b | 2017-09-16 | Implement comments | Email has important info |  | billed |  |  | 2017-09-17 |  | 1 | 2017-09-17 | Done
1657 | Cleburne SWAT | E170915c | 2017-09-15 | Update base files |  |  | billed |  |  | 2017-09-17 |  | 0.5 | 2017-09-18 | Done
1657 | Cleburne SWAT |  | 2017-09-17 | MP Sheets |  |  | billed |  |  | 2017-09-18 |  | 1 | 2017-09-18 | Done
1631 | Brown Street Church Addition | E170916a | 2017-09-18 | VE Item Revision |  |  | billed |  |  | 2017-09-19 |  | 1 | 2017-09-19 | Done
1572 | 350 Belknap |  | 2017-09-18 | RFI 5 | Replied directly to email |  | billed |  |  | 2017-09-18 |  | 0.5 | 2017-09-18 | Done
1671 | CE DFW Conference Room | E170918b | 2017-09-18 | Proposal |  |  | billed |  |  | 2017-09-18 |  | 0.5 | 2017-09-18 | Done
1657 | Cleburne SWAT | E170919a | 2017-09-19 | Graphics |  |  | billed |  |  | 2017-09-19 | 1 | 1 | 2017-09-19 | Done
1416 | DCCCD Eastfield Generator | E170915d | 2017-09-19 | Progress Meeting |  |  | billed |  |  | 2017-09-21 | 3 | 3 | 2017-09-21 | Done
1416 | DCCCD Eastfield Generator | E170915d | 2017-09-19 | Review pay app prior to meeting |  |  | billed |  |  | 2017-09-20 | 0.5 | 0.5 | 2017-09-21 | Done
1582 | Northern Hills Elementary Safe Room | E170913d | 2017-09-15 | Update base files |  | Design work | billed |  |  |  |  | 1 | 2017-09-24 | Done
1654 | Mineral Wells Head Start | E170918c | 2017-09-18 | Review kitchen concept | Closed: project cancelled | Design work | billed | [5 empty] | 2017-11-21 | Done
1654 | Mineral Wells Head Start | E170919b | 2017-09-19 | Review Site Plan | Closed: project cancelled | Design work | billed | [5 empty] | 2017-11-21 | Done
1582 | Northern Hills Elementary Safe Room | E170918d | 2017-09-18 | Do not include millwork in DD set | Done in prior issue | Design work | no | [5 empty] | 2018-01-21 | Done
1670 | Brookhaven Generator | E170919c | 2017-09-19 | Prepare proposal | Send by 9/25 |  | billed | 1 |  | 2017-09-26 | 2 | 1 | 2017-09-26 | Done
1582 | Northern Hills Elementary Safe Room | E170919d | 2017-09-19 | Include design reqs in email |  | Design Work | billed |  |  |  |  | 1 | 2017-09-24 | Done
1416 | DCCCD Eastfield Generator | E170919e | 2017-09-19 | Review revised gear submittal |  |  | billed |  |  | 2017-09-19 |  | 0.5 | 2017-09-19 | Done
1670 | Brookhaven Generator | E170919f | 2017-09-19 | Contact Will Herber | See E170921b |  | billed |  |  | 2017-09-20 |  | 0.5 | 2017-09-21 | Done
1661 | Othello's Restaurant | E170919g | 2017-09-19 | Place shallow downlight |  | Design work | billed |  |  |  |  | 2 | 2017-09-20 | Done
1661 | Othello's Restaurant |  | 2017-09-19 | Finish review set |  |  | billed |  |  | 2017-09-20 |  | 2 | 2017-09-22 | Done
1672 | FBC Watauga - Phase 1 | E170919h | 2017-09-19 | Proposal |  |  | billed |  |  | 2017-09-19 |  | 0.5 | 2017-09-19 | Done
1673 | 3330 Matlock Pizzeria | E170919i | 2017-09-19 | Proposal |  |  | billed |  |  |  |  | 0.5 | 2017-09-19 | Done
1544 | The Community At Lake Ridge | E170921a | 2017-09-21 | Addendum 1 - FA voice notification |  |  | billed |  |  | 2017-09-22 |  | 1 | 2017-09-25 | Done
1670 | Brookhaven Generator | E170921b | 2017-09-21 | Get proposal from Will |  |  | billed |  |  | 2017-09-25 |  |  | 2017-09-24 | Done
1661 | Othello's Restaurant | E170916c | 2017-09-21 | FA specifications | See email | Design Work | billed |  |  | 2017-09-28 |  | 1 | 2017-10-04 | Done
1538 | UNT Coliseum Concourse | E171002b | 2017-10-02 | Fixture K submittal |  |  | billed |  |  | 2017-10-04 |  | 1 | 2017-10-04 | Done
1662 | Heritage Glenn Office Park | 170922 | 2017-09-22 | Update base files |  |  | billed |  |  | 2017-09-23 |  | 1 | 2017-09-22 | Done
1582 | Northern Hills Elementary Safe Room |  | 2017-09-24 | DD Work |  |  | billed |  |  |  |  | 2 | 2017-09-24 | Done
1544 | The Community At Lake Ridge | E170925a | 2017-09-25 | Site update |  |  | billed |  |  | 2017-09-25 | 1 | 1 | 2017-09-25 | Done
1659 | The Joint Saginaw | E170925b | 2017-09-25 | Re issue IFC set |  |  | billed |  |  | 2017-09-25 | 1 | 1 | 2017-09-26 | Done
1657 | Cleburne SWAT | E170926a | 2017-06-26 | IFC |  |  | billed |  |  |  |  | 2 | 2017-09-26 | Done
1662 | Heritage Glenn Office Park |  | 2017-09-25 | Revise set with new base files |  |  | billed |  |  |  |  | 4 | 2017-09-25 | Done
1662 | Heritage Glenn Office Park |  | 2017-09-25 | Revise set with new base files |  |  | billed |  |  |  |  | 4 | 2017-09-26 | Done
1631 | Brown Street Church Addition | E170922a | 2017-09-22 | LTG Submittal |  |  | billed | 2 |  | 2017-09-26 | 1 | 1 | 2017-09-27 | Done
1416 | DCCCD Eastfield Generator | E170926b | 2017-09-26 | Payment Request |  |  | billed |  |  |  |  | 0.5 | 2017-09-26 | Done
1661 | Othello's Restaurant | E170926c | 2017-09-26 | Change 1 service to 2 panels | Info in email | IFC Work | billed |  |  | 2017-09-28 |  | 1 | 2017-10-06 | Done
1538 | UNT Coliseum Concourse | E170926d | 2017-09-26 | Review LTG checklist |  |  | billed |  |  |  |  | 0.5 | 2017-09-26 | Done
ops | Operations |  | 2017-09-26 | Provide master certificate to GSBS |  |  | billed |  |  |  |  | 0.5 | 2017-09-26 | Done
1535 | Cornerstone Baptist Church | E170913b | 2017-09-13 | Kitchen outlets for ice machine | 11/21 Deleted due to inaction 9/27 Tim will ask Eric next week 9/26 Need update from Tim | Tim's input. Delete by 10/31 | billed | 7 |  |  |  |  | 2017-11-21 | Done
1477 | Eugene McCray Recreation Center | E171107b | 2017-11-07 | Update site plan | No site changes |  | billed |  |  | 2017-11-07 |  | 0 | 2017-11-07 | Done
1535 | Cornerstone Baptist Church | E171201a | 2017-12-01 | Fixture K issue. | 12/6 Sent report 12/6 SV took measurements. Need report. 12/4 second SV scheduled for 12/6 @ 8 AM 12/1 Had a meeting with the Owner and contractor. |  | billed | 1 |  | 2017-12-06 |  | 4 | 2017-12-06 | Done
ops | Operations |  | 2017-09-26 | Send money to Jose |  |  | no |  |  | 2018-01-14 |  |  | 2018-01-13 | Done
ops | Operations |  | 2017-09-26 | Send money to Jose |  |  | no |  |  | 2018-02-14 |  |  | 2018-02-14 | Done
ops | Operations |  | 2017-09-26 | Send money to Jose |  |  | no |  |  | 2018-03-14 |  |  | 2018-03-13 | Done
ops | Operations |  | 2017-09-26 | Send money to Jose |  |  | no |  |  | 2018-04-14 |  |  | 2018-04-13 | Done
ops | Operations |  | 2017-09-26 | Send money to Jose |  |  | no |  |  | 2018-05-14 |  |  | 2018-05-14 | Done
ops | Operations |  | 2017-09-26 | Send money to Jose |  |  | no |  |  | 2018-06-14 |  |  | 2018-06-14 | Done
ops | Operations |  | 2017-09-26 | Send money to Jose |  |  | no |  |  | 2018-07-14 |  |  | 2018-07-13 | Done
ops | Operations |  | 2017-09-26 | Send money to Jose | Lump Sum payment on 7/15 |  | no |  |  | 2018-08-17 |  |  | 2018-07-15 | Done
ops | Operations |  | 2017-09-26 | Send money to Jose | Lump Sum payment on 7/15 |  | no |  |  | 2018-09-14 |  |  | 2018-07-15 | Done
ops | Operations |  | 2017-09-26 | Send money to Jose | Lump Sum payment on 7/15 |  | no |  |  | 2018-10-14 |  |  | 2018-07-15 | Done
ops | Operations |  | 2017-09-26 | Send money to Jose | Lump Sum payment on 7/15 |  | no |  |  | 2018-11-14 |  |  | 2018-07-15 | Done
1416 | DCCCD Eastfield Generator | E170926e | 2017-09-26 | Generator slab submittal |  |  | billed |  |  |  |  | 0.5 | 2017-09-26 | Done
ops | Operations |  | 2017-09-09 | Set up lunch with Mark Tiner | Friday 10/6. Call Friday morning |  | billed |  |  | 2017-10-06 |  |  | 2017-10-13 | Done
1544 | The Community At Lake Ridge | E170926g | 2017-09-26 | received rev 01 from OWT | No action requied |  | billed |  |  |  |  | 0 | 2017-09-26 | Done
1661 | Othello's Restaurant | E170926h | 2017-09-26 | Reduce lights in kitchen | Email has info | IFC Work | billed |  |  | 2017-09-28 |  | 1 | 2017-10-05 | Done
1538 | UNT Coliseum Concourse | E170926j | 2017-09-26 | Review bldg controls submittal |  |  | billed | 3 |  | 2017-09-26 |  | 0.5 | 2017-09-27 | Done
1604 | Botanic Garden Assessment |  | 2017-09-26 | Plan Zone 4 SVs | Friday 10/6 |  | billed |  |  | 2017-09-28 |  | 0.5 | 2017-10-02 | Done
1604 | Botanic Garden Assessment |  | 2017-09-26 | Zone 3 SV |  |  | billed |  |  |  |  | 4 | 2017-09-20 | Done
1530 | Brennan Drop-off Changes |  | 2017-09-26 | Schedule SVs |  |  | billed | 6 |  | 2017-09-28 |  |  | 2017-09-29 | Done
1416 | DCCCD Eastfield Generator | E170919e | 2017-09-26 | Review revised gear submittal |  |  | billed | 4 |  | 2017-09-27 |  | 1 | 2017-09-27 | Done
1600 | Gun Experience | E170927a | 2017-09-27 | Photometrics Study | 9/27 - Ran photometrics. Need to finish sheet. |  | billed |  |  | 2017-09-28 | 2 | 7 | 2017-10-02 | Done
1421 | KXAS Remodel | E171005a | 2017-10-05 | Review change orders |  |  | billed |  |  | 2017-10-05 |  | 0.5 | 2017-10-05 | Done
1421 | KXAS Remodel | E171025a | 2017-10-25 | RFI 22 |  |  | billed |  |  |  |  | 1 | 2017-10-25 | Done
1530 | Brennan Drop-off Changes | E170929a | 2017-09-29 | SV 1 |  |  | billed |  |  | 2017-10-05 | 1.5 | 1 | 2017-10-05 | Done
1662 | Heritage Glenn Office Park |  | 2017-09-27 | IFC | Date it 9/29. Need to fix "small" items |  | billed |  |  | 2017-09-28 |  | 1 | 2017-09-28 | Done
1662 | Heritage Glenn Office Park |  | 2017-09-28 | COMCheck |  |  | billed |  |  | 2017-09-28 |  | 1 | 2017-09-28 | Done
1662 | Heritage Glenn Office Park | E170928a | 2017-09-28 | Updated site plan |  |  | billed |  |  | 2017-09-28 |  | 1 | 2017-09-28 | Done
1531 | MLK Drop-off Changes | E170929a | 2017-09-29 | SV 1 |  |  | billed |  |  | 2017-10-05 | 1.5 | 1 | 2017-10-05 | Done
1532 | Old Hemphill Drop-off Changes | E170929a | 2017-09-29 | SV 1 |  |  | billed |  |  | 2017-10-05 | 1.5 | 1 | 2017-10-05 | Done
1604 | Botanic Garden Assessment |  | 2017-10-02 | SV Zone 4 night |  |  | billed |  |  | 2017-10-05 |  | 3 | 2017-10-06 | Done
1604 | Botanic Garden Assessment | P11-13 | 2017-10-02 | SV Zone 4 |  |  | billed |  |  | 2017-10-06 |  | 3 | 2017-10-06 | Done
1678 | The Joint - Timberland | p11-29 | 2017-10-18 | IFC Work |  |  | billed |  |  | 2017-10-19 | 3 | 2.5 | 2017-10-19 | Done
1604 | Botanic Garden Assessment | E170629g | 2017-08-11 | Zone 4 Draft Report |  |  | billed |  |  | 2017-10-13 |  | 4 | 2017-10-13 | Done
1654 | Mineral Wells Head Start | E170929b | 2017-09-29 | Incorporate site plan | Closed: project cancelled | New Scope | billed |  |  | 2017-09-29 |  |  | 2017-11-21 | Done
1661 | Othello's Restaurant | E170929c | 2017-09-29 | Additional POS locations |  | IFC Work | billed |  |  |  |  | 0.5 | 2017-10-05 | Done
1674 | The Dove Church in Southlake | E170929d | 2017-09-29 | Prepare proposal |  |  | billed |  |  | 2017-09-29 |  | 0.5 | 2017-10-01 | Done
1675 | Cornerstone Church Rowlett | E170929e | 2017-09-29 | Prepare proposal |  |  | billed |  |  | 2017-09-29 |  | 0.5 | 2017-10-01 | Done
1661 | Othello's Restaurant | E170929e | 2017-10-02 | Add outlet by pit, pit starter | Where is the pit? | IFC Work | billed |  |  |  |  | 0.5 | 2017-10-06 | Done
1615 | Celeris (2017) |  | 2017-09-15 | Projects for the month |  |  | billed |  |  | 2017-09-15 |  | 4 | 2017-09-15 | Done
ops | Operations |  | 2017-09-26 | Send money to Jose |  |  | billed |  |  | 2017-10-14 |  |  | 2017-10-12 | Done
1530 | Brennan Drop-off Changes | E170914b | 2017-09-14 | 75% CD due |  |  | billed |  |  | 2017-10-16 |  | 4 | 2017-10-14 | Done
1531 | MLK Drop-off Changes | E170914b | 2017-09-14 | 75% CD due |  |  | billed |  |  | 2017-10-16 |  | 1 | 2017-10-14 | Done
1532 | Old Hemphill Drop-off Changes | E170914b | 2017-09-14 | 75% CD due |  |  | billed |  |  | 2017-10-16 |  | 1 | 2017-10-14 | Done
1530 | Brennan Drop-off Changes | E171002d | 2017-10-02 | Provide site sign |  | Cut sheet info | billed |  |  |  |  | 0.5 | 2017-01-14 | Done
1531 | MLK Drop-off Changes | E171002d | 2017-10-02 | Provide site sign |  | Cut sheet info | billed |  |  |  |  | 0.5 | 2017-01-14 | Done
1532 | Old Hemphill Drop-off Changes | E171002d | 2017-10-02 | Provide site sign |  | Cut sheet info | billed |  |  |  |  | 0.5 | 2017-01-14 | Done
1582 | Northern Hills Elementary Safe Room |  | 2017-10-02 | Add design guidelines to specifications |  |  | no |  |  | 2017-10-03 |  | 1 | 2018-01-21 | Done
1530 | Brennan Drop-off Changes | E170926f | 2017-10-02 | Implement requirements | See file in folder | IFC Work | billed |  |  |  |  | 1 | 2017-01-14 | Done
1531 | MLK Drop-off Changes | E170926f | 2017-10-02 | Implement requirements | See file in folder | IFC Work | billed |  |  |  |  | 0 | 2017-01-14 | Done
1532 | Old Hemphill Drop-off Changes | E170926f | 2017-10-02 | Implement requirements | See file in folder | IFC Work | billed |  |  |  |  | 0 | 2017-01-14 | Done
1679 | New Yoga Studio | E171019a | 2017-10-19 | Proposal |  |  | billed |  |  | 2017-10-19 |  | 0.5 | 2017-10-19 | Done
1600 | Gun Experience | E171004a | 2017-10-04 | Update Revit files | Superceded | IFC Work | billed |  |  |  |  | 0 | 2017-11-16 | Done
1530 | Brennan Drop-off Changes | E171004b | 2017-10-04 | Include sign information. | 10/20 Waiting for final location 10/04 Sign is 240V need to verify voltages | IFC Work | billed |  |  |  |  | 1 | 2017-11-20 | Done
1661 | Othello's Restaurant | E171004c | 2017-10-04 | Provide Heaters |  | IFC Work | billed |  |  |  |  | 0.5 | 2017-10-06 | Done
1592 | Deer Park Animal Shelter | E171004d | 2017-10-04 | Review utility location changes |  |  | billed |  |  | 2017-10-04 |  | 1 | 2017-10-04 | Done
1661 | Othello's Restaurant | E171004e | 2017-10-04 | New canopy lighting layout | Update base file | IFC Work | billed |  |  |  |  | 1 | 2017-10-06 | Done
1670 | Brookhaven Generator | E170919c | 2017-10-04 | NTP |  |  | billed |  |  |  |  | 0 | 2017-10-04 | Done
1421 | KXAS Remodel | E171026c | 2017-10-26 | RFI 23 |  |  | billed |  |  | 2017-10-26 | 1 | 1 | 2017-10-26 | Done
1621 | The Creek Church Phase II | E171005b | 2017-10-05 | Revision 3 | Work complete. Waiting for issue date | Issue date | billed |  |  | 2017-10-05 |  | 1 | 2017-10-13 | Done
1676 | National Indoor RV Building | E171005c | 2017-10-05 | Proposal |  |  | billed |  |  | 2017-10-05 |  | 0.5 | 2017-10-05 | Done
1661 | Othello's Restaurant | E170926h | 2017-09-26 | Relocate equipment condensers |  | IFC Work | billed |  |  |  |  | 0.5 | 2017-10-06 | Done
1661 | Othello's Restaurant | E171008a | 2017-10-08 | Coordinate MP sheets |  |  | billed |  |  | 2017-10-08 |  | 1 | 2017-10-08 | Done
1661 | Othello's Restaurant |  | 2017-10-08 | Final QC |  |  | billed |  |  |  |  | 2 | 2017-10-09 | Done
1582 | Northern Hills Elementary Safe Room | E171005d | 2017-10-05 | Instructions for IFC | Superceded | marching orders from James | no | [5 empty] | 2018-01-21 | Done
1631 | Brown Street Church Addition | E171005e | 2017-10-05 | Submittal |  |  | billed |  |  | 2017-10-10 | 1 | 1.5 | 2017-10-10 | Done
1677 | Kansas City Railroad Mexico | E171010a | 2017-10-10 | Proposal |  |  | billed |  |  | 2017-10-10 | 2 | 1.5 | 2017-10-10 | Done
ops | Operations |  | 2017-10-10 | Send payment to Abuelos |  |  | no |  |  | 2018-01-01 |  |  | 2018-01-03 | Done
1535 | Cornerstone Baptist Church | LTG Resubmittal | 2017-10-12 | Comment on fixtures G and H | Handled thru phone call to Eric |  | billed |  |  |  |  | 1 | 2017-10-12 | Done
1530 | Brennan Drop-off Changes | E171019d | 2017-10-19 | Update base files |  |  | billed |  |  | 2017-10-19 |  | 0.5 | 2017-10-19 | Done
1530 | Brennan Drop-off Changes | E171012c | 2017-10-12 | MP Sheets |  |  | billed |  |  |  |  | 1 | 2017-10-13 | Done
1621 | The Creek Church Phase II | E171013a | 2017-10-13 | Change date to rev 03 |  |  | billed |  |  | 2017-10-13 |  | 0.5 | 2017-10-13 | Done
1604 | Botanic Garden Assessment |  | 2017-10-16 | Zone 5 SV |  |  | billed |  |  | 2017-10-13 |  | 2 | 2017-10-13 | Done
1600 | Gun Experience |  | 2017-10-16 | Design Meeting |  |  | billed |  |  | 2017-10-16 | 2 | 3 | 2017-10-16 | Done
1580 | Rental One - Denton | E171012d | 2017-10-16 | Washbay revision |  |  | billed |  |  | 2017-10-17 |  | 2 | 2017-10-17 | Done
1544 | The Community At Lake Ridge | E171012b | 2017-10-12 | VE items and City Comment revision due |  |  | billed |  |  | 2017-10-24 |  | 1 | 2017-11-22 | Done
1538 | UNT Coliseum Concourse | E171016a | 2017-10-16 | RFI 58 - Additional receptacles |  |  | billed |  |  | 2017-10-16 | 1 | 1 | 2017-10-17 | Done
1615 | Celeris (2017) | p11-29 | 2017-10-17 | Jones Stadium Proposal |  |  | billed |  |  | 2017-10-17 | 0.5 | 0.5 | 2017-10-17 | Done
1531 | MLK Drop-off Changes | E171019d | 2017-10-19 | Update base files |  |  | billed |  |  | 2017-10-19 |  | 0.5 | 2017-10-19 | Done
1532 | Old Hemphill Drop-off Changes | E171019d | 2017-10-19 | Update base files |  |  | billed |  |  | 2017-10-19 |  | 0.5 | 2017-10-19 | Done
1530 | Brennan Drop-off Changes | E171019e | 2017-10-19 | Implement site comments | Include gate and CR. See email |  | billed |  |  | 2017-10-19 |  | 1 | 2017-10-19 | Done
1531 | MLK Drop-off Changes | E171019e | 2017-10-19 | Implement site comments | Include gate and CR. See email |  | billed |  |  | 2017-10-19 |  | 1 | 2017-10-19 | Done
1680 | ATP Arlington Hangar | E171019c | 2017-10-19 | Proposal |  |  | billed |  |  |  |  | 0.5 | 2017-10-19 | Done
1532 | Old Hemphill Drop-off Changes | E171019e | 2017-10-19 | Implement site comments | Include gate and CR. See email |  | billed |  |  | 2017-10-19 |  | 1 | 2017-10-19 | Done
1600 | Gun Experience | E171017a | 2017-10-17 | Update Revit file |  |  | billed |  |  | 2017-10-20 | 1 | 1 | 2017-10-20 | Done
1678 | The Joint - Timberland |  | 2017-10-20 | Send review set and update RTU |  |  | billed |  |  | 2017-10-20 | 2 | 1.5 | 2017-10-20 | Done
1530 | Brennan Drop-off Changes | E171019e | 2017-10-20 | Send review set to Scott |  |  | billed |  |  | 2017-10-20 | 0.5 | 0.5 | 2017-10-20 | Done
1531 | MLK Drop-off Changes | E171019e | 2017-10-20 | Send review set to Scott |  |  | billed |  |  | 2017-10-20 | 0.5 | 0.5 | 2017-10-20 | Done
1532 | Old Hemphill Drop-off Changes | E171019e | 2017-10-20 | Send review set to Scott | Implement QC marks |  | billed |  |  | 2017-10-20 | 1 | 1 | 2017-10-20 | Done
ops | Operations | E171002e | 2017-10-02 | Provide NCTRCA certificate | 10/17 Sent email to NCTRCA 10/2 Follow up 10/6 |  | billed |  |  | 2017-10-25 |  | 0.5 | 2017-10-31 | Done
1582 | Northern Hills Elementary Safe Room | E170821e | 2017-08-21 | 95% CD Set due | Superceded | Information from James | no |  |  | 2017-10-25 |  |  | 2018-01-21 | Done
1604 | Botanic Garden Assessment | E170629g | 2017-08-11 | Zone 4 Final Report |  |  | billed |  |  | 2017-10-27 |  | 1 | 2017-10-31 | Done
1582 | Northern Hills Elementary Safe Room | E170821e | 2017-08-21 | 95% CD meeting | Seuperceded | Info from James | no |  |  | 2017-10-30 |  |  | 2018-01-21 | Done
1600 | Gun Experience | E171020a | 2017-10-20 | LTG to OWT |  |  | billed |  |  | 2017-10-20 | 2 | 2 | 2017-10-20 | Done
1600 | Gun Experience | 171017 | 2017-10-20 | Implement meeting notes |  |  | billed |  |  | 2017-10-23 | 3 | 2 | 2017-10-23 | Done
1530 | Brennan Drop-off Changes | E171024a | 2017-10-24 | Updated SPCs |  |  | billed |  |  |  |  | 2 | 2017-10-24 | Done
1530 | Brennan Drop-off Changes | E171023a | 2017-10-23 | Review 75% CD Set |  | IFC Work | billed | [5 empty] | 2017-11-20 | Done
1531 | MLK Drop-off Changes | E171023a | 2017-10-23 | Review 75% CD Set |  | IFC Work | billed | [5 empty] | 2017-11-20 | Done
1532 | Old Hemphill Drop-off Changes | E171023a | 2017-10-23 | Review 75% CD Set |  | IFC Work | billed | [5 empty] | 2017-11-20 | Done
1421 | KXAS Remodel | E171103c | 2017-11-03 | vestibule lighting proposal | 171106 - Talked to Scott. Need to send ltg file |  | billed |  |  | 2017-11-07 |  | 1 | 2017-11-07 | Done
1604 | Botanic Garden Assessment | E171025b | 2017-10-25 | Statements for no work/deficiencies | See email for exact text | Final report | billed | [5 empty] | 2018-03-13 | Done
1478 | Handley Meadowbrook Rec Center | E171107b | 2017-11-07 | Update site plan | No site changes |  | billed |  |  | 2017-11-07 |  | 0 | 2017-11-07 | Done
1600 | Gun Experience | E171026a | 2017-10-26 | Update revit file |  |  | billed |  |  | 2017-10-26 | 1 | 1 | 2017-10-26 | Done
1600 | Gun Experience | E171026b | 2017-10-26 | MP Sheets |  |  | billed |  |  | 2017-10-26 | 1 | 1 | 2017-10-26 | Done
1421 | KXAS Remodel | E171103a | 2017-11-03 | Find cover plate for twist lock outlets |  |  | billed |  |  | 2017-11-06 |  | 0.5 | 2017-11-06 | Done
1600 | Gun Experience |  | 2017-10-26 | IFC Work |  |  | billed |  |  |  |  | 4 | 2017-10-26 | Done
1544 | The Community At Lake Ridge | E171026d | 2017-10-26 | Add outlets to café | See email | Next issue | billed |  |  |  |  | 0.5 | 2017-11-22 | Done
1530 | Brennan Drop-off Changes | E170914b | 2017-09-14 | 100% CD to EoA | Superceded by E171205b |  | billed |  |  | 2017-12-27 |  |  | 2017-12-18 | Done
1530 | Brennan Drop-off Changes | E170914b | 2017-09-14 | 100% CD to City | duplicate see E171205b |  | no |  |  | 2018-01-05 |  |  | 2018-01-05 | Done
1531 | MLK Drop-off Changes | E170914b | 2017-09-14 | 100% CD to EoA | Superceded by E171205b |  | billed |  |  | 2017-12-27 |  |  | 2017-12-18 | Done
1531 | MLK Drop-off Changes | E170914b | 2017-09-14 | 100% CD to City | duplicate see E171205b |  | no |  |  | 2018-01-05 |  |  | 2018-01-05 | Done
1532 | Old Hemphill Drop-off Changes | E170914b | 2017-09-14 | 100% CD to EoA | Superceded by E171205b |  | billed |  |  | 2017-12-27 |  |  | 2017-12-18 | Done
1532 | Old Hemphill Drop-off Changes | E170914b | 2017-09-14 | 100% CD to City | duplicate see E171205b |  | no |  |  | 2018-01-05 |  |  | 2018-01-05 | Done
1631 | Brown Street Church Addition | E171027b | 2017-10-27 | Add Riser room - Update Revit file |  | Revision information | billed | [5 empty] | 2017-10-30 | Done
1604 | Botanic Garden Assessment | E171027c | 2017-10-27 | Implement EoA comments on Zone 4 |  |  | billed |  |  | 2017-10-30 |  | 3 | 2017-10-31 | Done
1681 | McKinney Office Building | E171031d | 2017-10-27 | Proposal |  |  | billed |  |  | 2017-10-27 | 1 | 1 | 2017-10-30 | Done
1631 | Brown Street Church Addition | E171030a | 2017-10-30 | Revision 5. Add new riser room |  |  | billed |  |  | 2017-10-30 | 1 | 1 | 2017-10-30 | Done
1631 | Brown Street Church Addition | E171030a | 2017-10-30 | Rev 5. HVAC changes |  |  | billed |  |  | 2017-10-30 | 1 | 0.5 | 2017-10-30 | Done
1604 | Botanic Garden Assessment | E170629g | 2017-08-11 | Zone 5 Draft Report |  |  | billed |  |  | 2017-11-10 |  | 2 | 2017-11-10 | Done
1582 | Northern Hills Elementary Safe Room | E171030b | 2017-10-30 | 50% CD Set due | 171103f-Cancelled |  | billed |  |  | 2017-11-13 |  |  | 2017-11-06 | Done
ops | Operations | E171108b | 2017-11-08 | Renew AutoCAD |  |  | billed |  |  | 2017-12-08 |  | 1 | 2017-12-11 | Done
1604 | Botanic Garden Assessment | E171031a | 2017-10-31 | Fix Zone 1 report |  |  | billed |  |  | 2017-10-31 |  | 1 | 2017-10-31 | Done
1501 | Kimbell East Parking | E171031b | 2017-10-31 | Remote driver question |  |  | billed |  |  | 2017-10-31 |  | 0.5 | 2017-10-31 | Done
1582 | Northern Hills Elementary Safe Room | E171030b | 2017-10-31 | New scope |  |  | no |  |  | 2018-01-21 |  | 1 | 2018-01-21 | Done
1678 | The Joint - Timberland | E171031c | 2017-10-31 | IFC |  |  | billed |  |  | 2017-10-31 | 1 | 1.5 | 2017-10-31 | Done
1682 | Clarus Interior Renovation | E171031d | 2017-10-31 | Proposal |  |  | billed |  |  | 2017-10-31 |  | 1 | 2017-10-31 | Done
1615 | Celeris (2017) |  | 2017-10-31 | Projects for the month |  |  | billed |  |  |  |  | 1 | 2017-10-31 | Done
1613 | Norman Hotel | E171102a | 2017-11-02 | Evaluation Site Visit |  | Approval and date | billed | [5 empty] | 2017-11-09 | Done
1477 | Eugene McCray Recreation Center | E171102b | 2017-11-02 | M Equip Revision | Need addendum information |  | billed |  |  | 2017-11-06 |  | 1 | 2017-11-06 | Done
1478 | Handley Meadowbrook Rec Center | E171102b | 2017-11-02 | M Equip Revision | Need addendum information |  | billed |  |  | 2017-11-06 |  | 1 | 2017-11-06 | Done
1600 | Gun Experience | E171102c | 2017-11-02 | Revise Photometrics |  |  | billed |  |  | 2017-11-02 |  | 1 | 2017-11-02 | Done
1594 | Pflugerville AS | E171107c | 2017-11-07 | LTG Submittal |  |  | billed |  |  | 2017-11-10 |  | 1 | 2017-11-13 | Done
1676 | National Indoor RV Building | E171102d | 2017-11-02 | Project Approved |  |  | billed | [5 empty] | 2017-11-02 | Done
1421 | KXAS Remodel | E171116a | 2017-11-16 | Revision 4 |  |  | billed |  |  | 2017-11-16 |  | 1 | 2017-11-16 | Done
1477 | Eugene McCray Recreation Center | E171103b | 2017-11-03 | Review Permit Comments |  |  | billed |  |  | 2017-11-06 |  | 0.5 | 2017-11-06 | Done
1478 | Handley Meadowbrook Rec Center | E171103b | 2017-11-03 | Review Permit Comments |  |  | billed |  |  | 2017-11-06 |  | 0.5 | 2017-11-06 | Done
1594 | Pflugerville AS | E171107d | 2017-11-07 | PWR Submittal |  |  | billed |  |  | 2017-11-10 |  | 1 | 2017-11-13 | Done
1667 | Modern Acupunture - Plano | E171103d | 2017-11-03 | NTP |  |  | billed |  |  |  |  | 0 | 2017-11-03 | Done
1667 | Modern Acupunture - Plano | E171109b | 2017-11-10 | MP Sheets | See email for information |  | billed |  |  | 2017-11-10 |  | 1 | 2017-11-11 | Done
1613 | Norman Hotel | E171103g | 2017-11-06 | Call 580.380.2895 athakkar |  |  | billed |  |  | 2017-11-06 |  | 1 | 2017-11-06 | Done
1600 | Gun Experience | E171106a | 2017-11-06 | Spec go by available |  |  | billed |  |  | 2017-11-29 |  | 1 | 2017-11-30 | Done
1615 | Celeris (2017) |  | 2017-11-06 | Projects |  |  | billed |  |  | 2017-11-06 |  | 1 | 2017-11-06 | Done
1684 | Angelina's Restaurant | E171106b | 2017-11-06 | Proposal |  |  | billed |  |  |  |  | 0.5 | 2017-11-06 | Done
1604 | Botanic Garden Assessment |  | 2017-11-06 | Zone 5 SV |  |  | billed |  |  | 2017-11-07 | 3 | 3 | 2017-11-07 | Done
1538 | UNT Coliseum Concourse | E171110a | 2017-11-10 | LTG Controls Meeting | Meeting 11/13 @ 3PM |  | billed |  |  | 2017-11-13 |  | 1 | 2017-11-13 | Done
1600 | Gun Experience | E171116b | 2017-11-16 | Gun Range HVAC equipment |  |  | billed | 2 |  | 2017-11-16 |  | 1 | 2017-11-16 | Done
ops | Operations |  | 2017-09-26 | Send money to Jose |  |  | billed |  |  | 2017-11-15 |  |  | 2017-11-13 | Done
1604 | Botanic Garden Assessment | E171119a | 2017-11-19 | Zone 5 Comments from Scott |  |  | billed |  |  | 2017-11-22 |  | 3 | 2017-11-30 | Done
1535 | Cornerstone Baptist Church | E171108a | 2017-11-08 | RFI 39 |  |  | billed |  |  |  |  | 1 | 2017-11-08 | Done
ops | Operations | E171101a | 2017-11-06 | Check Titan's PDH |  |  | billed |  |  | 2017-11-24 |  |  | 2017-11-28 | Done
1451 | The Door Church | E171109a | 2017-11-09 | Closeout Documents |  |  | billed |  |  | 2017-11-10 |  | 1 | 2017-11-10 | Done
1613 | Norman Hotel |  | 2017-11-08 | Site Visit |  |  | billed |  |  | 2017-11-09 | 6 | 7 | 2017-11-09 | Done
1600 | Gun Experience | E171115b | 2017-10-25 | 100 Coordination set |  |  | billed |  |  | 2017-11-17 |  | 8 | 2017-11-17 | Done
1582 | Northern Hills Elementary Safe Room | E171030b | 2017-10-30 | 50% CD Meeting | Cancelled |  | billed |  |  | 2017-11-17 |  |  | 2017-11-17 | Done
1530 | Brennan Drop-off Changes | E170914b | 2017-09-14 | 95% CD to EoA |  |  | billed |  |  | 2017-11-20 |  |  | 2017-11-20 | Done
1531 | MLK Drop-off Changes | E170914b | 2017-09-14 | 95% CD to EoA |  |  | billed |  |  | 2017-11-20 |  |  | 2017-11-20 | Done
1532 | Old Hemphill Drop-off Changes | E170914b | 2017-09-14 | 95% CD to EoA |  |  | billed |  |  | 2017-11-20 |  |  | 2017-11-20 | Done
1530 | Brennan Drop-off Changes | E171111a | 2017-11-11 | Provide data conduit for sign and CR |  | IFC Work | billed | [5 empty] | 2017-11-20 | Done
1531 | MLK Drop-off Changes | E171111a | 2017-11-11 | Provide data conduit for sign and CR |  | IFC Work | billed |  |  |  |  | 1 | 2017-11-20 | Done
1532 | Old Hemphill Drop-off Changes | E171111a | 2017-11-11 | Provide data conduit for sign and CR |  | IFC Work | billed |  |  |  |  | 1 | 2017-11-20 | Done
1600 | Gun Experience | E171122a | 2017-11-16 | Need location of soda machine | Location in comments |  | billed |  |  | 2017-11-29 |  | 1 | 2017-11-29 | Done
1600 | Gun Experience | E171114a | 2017-11-14 | Updated RCP |  | Superceded | billed |  |  | 2017-11-15 |  |  | 2017-11-16 | Done
1535 | Cornerstone Baptist Church | E171113b | 2017-11-13 | Bug Eye Issue |  |  | billed |  |  |  |  | 2 | 2017-11-15 | Done
1535 | Cornerstone Baptist Church |  | 2017-11-15 | Sanctuary Letter |  |  | billed |  |  | 2017-11-15 |  | 1 | 2017-11-15 | Done
1600 | Gun Experience | E171114b | 2017-11-14 | Updated photometrics. |  |  | billed |  |  | 2017-11-15 |  | 1 | 2017-11-15 | Done
1600 | Gun Experience |  | 2017-11-15 | Need Gunsmithing equipment information | Using max allowable |  | billed | [5 empty] | 2017-11-29 | Done
1477 | Eugene McCray Recreation Center | E171115a | 2017-11-15 | Bid Addendum | Due noon on 11/17 |  | billed |  |  | 2017-11-16 | 1 | 1 | 2017-11-16 | Done
1478 | Handley Meadowbrook Rec Center | E171115a | 2017-11-15 | Bid Addendum | Due noon on 11/17 |  | billed |  |  | 2017-11-16 | 1 | 1 | 2017-11-16 | Done
1544 | The Community At Lake Ridge | E171114c | 2017-11-14 | Update site plan for revision |  | Additional revision items | billed |  |  |  |  | 1.5 | 2017-11-22 | Done
1604 | Botanic Garden Assessment | E170629g | 2017-08-11 | Zone 5 Final Report |  |  | billed |  |  | 2017-12-01 |  | 1 | 2017-12-03 | Done
1421 | KXAS Remodel | E171130d | 2017-11-30 | Vestibule lighting fixture change |  |  | billed |  |  | 2017-11-30 |  | 0.5 | 2017-11-30 | Done
1600 | Gun Experience |  | 2017-11-16 | Revise lighting vs RCP |  |  | billed | 3 |  | 2017-11-16 |  | 2 | 2017-11-16 | Done
1600 | Gun Experience |  | 2017-11-16 | Revise power vs background |  |  | billed | 4 |  | 2017-11-16 |  | 1 | 2017-11-16 | Done
1600 | Gun Experience | E170831c | 2017-09-10 | Include illuminated sign | Single Circuit |  | billed | 5 |  | 2017-11-16 |  |  | 2017-11-29 | Done
1600 | Gun Experience | E171110b | 2017-11-10 | Update Revit file + answers | See fire place info in folder |  | billed | 6 |  | 2017-11-16 |  | 3 | 2017-11-16 | Done
1600 | Gun Experience |  | 2017-11-16 | Circuit , graphics, etc. |  |  | billed | 7 |  | 2017-11-16 |  | 1 | 2017-11-16 | Done
1530 | Brennan Drop-off Changes | E170914b | 2017-09-14 | 95% CD to City | Update: E171121e |  | billed |  |  | 2017-11-22 |  | 1 | 2017-11-22 | Done
1531 | MLK Drop-off Changes | E170914b | 2017-09-14 | 95% CD to City | Update: E171121e |  | billed |  |  | 2017-11-22 |  | 1 | 2017-11-22 | Done
1530 | Brennan Drop-off Changes | E171117a | 2017-11-17 | Update site plan |  |  | billed |  |  | 2017-11-19 |  | 1 | 2017-11-20 | Done
1531 | MLK Drop-off Changes | E171117a | 2017-11-17 | Update site plan |  |  | billed |  |  | 2017-11-19 |  | 1 | 2017-11-20 | Done
1532 | Old Hemphill Drop-off Changes | E171117a | 2017-11-17 | Update site plan |  |  | billed |  |  | 2017-11-19 |  |  | 2017-11-20 | Done
1600 | Gun Experience |  | 2017-11-17 | MP Sheets |  |  | billed |  |  |  |  | 1 | 2017-11-17 | Done
1538 | UNT Coliseum Concourse | E171117b | 2017-11-17 | Photometrics Study |  |  | billed |  |  |  |  | 2 | 2017-11-17 | Done
1667 | Modern Acupunture - Plano | E171117c | 2017-11-17 | Lana's comments | Email has comments |  | billed |  |  | 2017-11-17 |  | 2 | 2017-11-17 | Done
1667 | Modern Acupunture - Plano |  | 2017-11-19 | IFC |  | Comments on store front | billed |  |  | 2017-11-20 |  |  | 2017-12-01 | Done
1530 | Brennan Drop-off Changes | E171116d | 2017-11-19 | Implement comments |  |  | billed |  |  | 2017-11-19 |  |  | 2017-11-20 | Done
1531 | MLK Drop-off Changes | E171116d | 2017-11-19 | Implement comments |  |  | billed |  |  | 2017-11-19 |  |  | 2017-11-20 | Done
1532 | Old Hemphill Drop-off Changes | E171116d | 2017-11-19 | Implement comments |  |  | billed |  |  | 2017-11-19 |  | 1 | 2017-11-20 | Done
1667 | Modern Acupunture - Plano |  | 2017-11-19 | QC |  |  | billed |  |  | 2017-11-19 |  | 1 | 2017-11-20 | Done
1532 | Old Hemphill Drop-off Changes | E170914b | 2017-09-14 | 95% CD to City | Update: E171121e |  | billed |  |  | 2017-11-22 |  | 1 | 2017-11-22 | Done
1530 | Brennan Drop-off Changes | E171117e | 2017-11-19 | Reader Board Reqs |  |  | billed |  |  | 2017-11-20 |  |  | 2017-11-20 | Done
1531 | MLK Drop-off Changes | E171117e | 2017-11-19 | Reader Board Reqs |  |  | billed |  |  | 2017-11-20 |  |  | 2017-11-20 | Done
1532 | Old Hemphill Drop-off Changes | E171117e | 2017-11-19 | Reader Board Reqs |  |  | billed |  |  | 2017-11-20 |  |  | 2017-11-20 | Done
1661 | Othello's Restaurant | E171130c | 2017-11-30 | Implement changes |  |  | billed |  |  | 2017-12-05 |  | 1 | 2017-12-05 | Done
1600 | Gun Experience | E171115b | 2017-11-15 | Issue for Bid | Updated: E171121c |  | billed |  |  | 2017-11-30 |  | 1 | 2017-11-30 | Done
1531 | MLK Drop-off Changes | E171120a | 2017-11-20 | Specifications |  |  | billed |  |  | 2017-11-20 |  | 2 | 2017-11-20 | Done
1530 | Brennan Drop-off Changes |  | 2017-11-20 | Change Type A fixture to Metalux | 24GR LD5 48 A125 UNV CD (34.9W) |  | billed |  |  | 2017-11-21 |  | 1 | 2017-11-20 | Done
1544 | The Community At Lake Ridge |  | 2017-11-21 | Addendum 2 | Needs final QC |  | billed |  |  | 2017-11-30 |  |  | 2017-11-30 | Done
1613 | Norman Hotel | E171120b | 2017-11-21 | Design Site Visit | Tentative Dates:12/5, 12/6 | Richard's input | billed | [5 empty] | 2018-04-29 | Done
1678 | The Joint - Timberland | E171121a | 2017-11-21 | Revision 1 |  |  | billed |  |  | 2017-11-21 |  | 1 | 2017-11-21 | Done
1544 | The Community At Lake Ridge | E171121b | 2017-11-21 | MP Sheets |  |  | billed |  |  | 2017-11-21 |  | 1 | 2017-11-22 | Done
1600 | Gun Experience | E171121c | 2017-11-22 | Remove "bidding" from dwg warning |  |  | billed | [5 empty] | 2017-11-22 | Done
1600 | Gun Experience | E171122a | 2017-11-22 | Coordination Meeting | 11/27 @ 1:45 - 3:15 |  | billed |  |  | 2017-11-27 | 3 | 3 | 2017-11-27 | Done
1600 | Gun Experience | E171121d | 2017-11-22 | Send Specs TOC |  |  | billed |  |  | 2017-11-22 |  | 1 | 2017-11-22 | Done
1538 | UNT Coliseum Concourse | E171122c | 2017-11-22 | CA SV | Scheduled for 11/28 afternoon |  | billed |  |  | 2017-11-28 | 4 | 3 | 2017-11-28 | Done
1604 | Botanic Garden Assessment |  | 2017-11-22 | Send Zone 5 map to Scott |  |  | billed |  |  | 2017-11-22 |  | 0.5 | 2017-11-22 | Done
1686 | Ludelle Warehouse Narrative | p11-41 | 2017-11-22 | Proposal |  |  | billed |  |  |  |  | 0.5 | 2017-11-22 | Done
1544 | The Community At Lake Ridge | E171122d | 2017-11-22 | Update site plan |  |  | billed |  |  | 2017-11-22 |  | 1 | 2017-11-22 | Done
1416 | DCCCD Eastfield Generator | E171122b | 2017-11-22 | Payment Request | Review progress on 11/27 |  | billed |  |  | 2017-11-27 | 3 | 3 | 2017-11-27 | Done
1530 | Brennan Drop-off Changes | E171127a | 2017-11-27 | Comments from Scott |  |  | billed |  |  | 2017-11-29 |  | 1 | 2017-11-27 | Done
1531 | MLK Drop-off Changes | E171127a | 2017-11-27 | Comments from Scott |  |  | billed |  |  | 2017-11-29 |  | 1 | 2017-11-27 | Done
1532 | Old Hemphill Drop-off Changes | E171127a | 2017-11-27 | Comments from Scott |  |  | billed |  |  | 2017-11-29 |  | 1 | 2017-11-27 | Done
1604 | Botanic Garden Assessment | E171119a | 2017-11-28 | Edit Zone 5 for Scott |  |  | billed |  |  | 2017-12-01 |  |  | 2017-11-30 | Done
1600 | Gun Experience | E171121c | 2017-11-28 | Verify locations of Dyson faucets |  |  | billed |  |  | 2017-11-29 |  |  | 2017-11-27 | Done
1416 | DCCCD Eastfield Generator | E171128a | 2017-11-28 | Process Pay App |  |  | billed |  |  | 2017-11-29 |  | 1 | 2017-11-30 | Done
1687 | Crowley MOB | E171128b | 2017-11-28 | Prepare proposal |  |  | billed |  |  | 2017-11-28 |  |  | 2017-11-28 | Done
1535 | Cornerstone Baptist Church | E171128c | 2017-11-28 | Punch List SV |  |  | billed |  |  | 2017-12-01 | 4 | 8 | 2017-12-01 | Done
1600 | Gun Experience | E171128d | 2017-11-28 | Review Façade lighting |  |  | billed |  |  | 2017-11-29 |  | 1 | 2017-11-29 | Done
1600 | Gun Experience | E171128e | 2017-11-28 | Review Morrow's markups |  |  | billed |  |  | 2017-11-29 |  | 1 | 2017-11-29 | Done
1600 | Gun Experience | E171128f | 2017-11-28 | Update Revit file |  |  | billed |  |  | 2017-11-29 |  | 1 | 2017-11-29 | Done
1600 | Gun Experience | E171128g | 2017-11-28 | Implement Morrow's LFS changes |  |  | billed |  |  | 2017-11-29 |  | 1 | 2017-11-29 | Done
1600 | Gun Experience | E171128h | 2017-11-28 | MP Sheets | See email |  | billed |  |  | 2017-11-29 |  | 2 | 2017-11-30 | Done
1600 | Gun Experience | E171128j | 2017-11-28 | Implement OWT comments |  |  | billed |  |  | 2017-11-29 |  | 1 | 2017-11-29 | Done
1530 | Brennan Drop-off Changes | E171128k | 2017-11-28 | Add XE fixture |  |  | billed |  |  | 2017-11-28 |  | 0.5 | 2017-11-28 | Done
1531 | MLK Drop-off Changes | E171128k | 2017-11-28 | Add XE fixture |  |  | billed |  |  | 2017-11-28 |  | 0.5 | 2017-11-28 | Done
1532 | Old Hemphill Drop-off Changes | E171128k | 2017-11-28 | Add XE fixture |  |  | billed |  |  | 2017-11-28 |  | 0.5 | 2017-11-28 | Done
1600 | Gun Experience | E171129a | 2017-11-29 | Security Camera locations |  |  | billed |  |  | 2017-11-29 |  | 1 | 2017-11-29 | Done
1600 | Gun Experience | E171129b | 2017-11-29 | Add ceiling fans |  |  | billed |  |  | 2017-11-29 |  | 1 | 2017-11-29 | Done
1662 | Heritage Glenn Office Park | E171129d | 2017-11-29 | City comments |  |  | billed |  |  | 2017-11-30 |  | 2 | 2017-12-05 | Done
1667 | Modern Acupunture - Plano | E171129e | 2017-11-29 | New Furniture Plan |  |  | billed |  |  | 2017-11-30 |  | 1 | 2017-12-04 | Done
1544 | The Community At Lake Ridge | E171129f | 2017-11-29 | Addendum 2 | AVL final sizes |  | billed |  |  | 2017-11-30 |  | 1 | 2017-11-30 | Done
1600 | Gun Experience | E171129g | 2017-11-29 | Controls | Not using them |  | billed |  |  | 2017-11-30 |  | 0 | 2017-11-30 | Done
1600 | Gun Experience | E171129h | 2017-11-29 | Change CP-1 size to 270W |  |  | billed |  |  | 2017-11-30 |  | 0.5 | 2017-11-30 | Done
1600 | Gun Experience | E171129i | 2017-11-29 | Gun Range HVAC equipment | Again |  | billed |  |  | 2017-11-30 |  | 0.5 | 2017-11-30 | Done
1600 | Gun Experience |  | 2017-11-30 | QC |  |  | billed |  |  | 2017-11-30 |  | 1 | 2017-11-30 | Done
1544 | The Community At Lake Ridge | E171130a | 2017-11-30 | X2 fixtures |  |  | billed |  |  | 2017-11-30 |  | 1 | 2017-11-30 | Done
1535 | Cornerstone Baptist Church |  | 2017-11-30 | Punch List SV |  |  | billed |  |  | 2017-12-01 |  | 4 | 2017-12-01 | Done
1535 | Cornerstone Baptist Church |  | 2017-12-04 | SV to determine power and lumens | 12/6 @ 8 AM with Michael Eslinger |  | billed |  |  | 2017-12-06 | 3 | 2 | 2017-12-06 | Done
1421 | KXAS Remodel |  | 2017-12-03 | Rev 4 - with A2 fixures |  |  | billed |  |  | 2017-12-04 |  | 1 | 2017-12-04 | Done
ops | Operations |  | 2017-09-26 | Send money to Jose |  |  | billed |  |  | 2017-12-14 |  | 0.5 | 2017-12-14 | Done
1582 | Northern Hills Elementary Safe Room | E171202a | 2017-12-02 | Recalculate fee for new scope | 12/4 Agreed to keep original fee. 12/2 Talk to Tim on 12/3 |  | billed |  |  | 2017-12-03 |  | 1 | 2017-12-04 | Done
1421 | KXAS Remodel | E171206b | 2017-12-06 | Revision 4 added scope | 12/6 Asked about compensation |  | billed |  |  | 2017-12-07 |  | 1 | 2017-12-07 | Done
1671 | CE DFW Conference Room | E171204a | 2017-12-04 | Recalculate fee for new scope |  |  | billed |  |  | 2017-12-04 |  | 1 | 2017-12-04 | Done
1582 | Northern Hills Elementary Safe Room | E171030b | 2017-10-30 | 95% CD review mtg | To be confirmed. Cancelled. |  | billed |  |  | 2017-12-18 |  |  | 2017-12-18 | Done
1451 | The Door Church | E171204b | 2017-12-04 | Preliminary ltg layout for phase 2 |  |  | billed |  |  |  |  | 1 | 2017-12-04 | Done
1661 | Othello's Restaurant | E171205a | 2017-12-05 | Update bar layout |  |  | billed |  |  | 2017-12-05 | 1 | 2 | 2017-12-05 | Done
1530 | Brennan Drop-off Changes | E171205b | 2017-12-05 | 100% QC Set due to EoA |  |  | billed |  |  | 2017-12-27 |  | 1 | 2017-12-27 | Done
1531 | MLK Drop-off Changes | E171205b | 2017-12-05 | 100% QC Set due to EoA |  |  | billed |  |  | 2017-12-27 |  | 1 | 2017-12-27 | Done
1532 | Old Hemphill Drop-off Changes | E171205b | 2017-12-05 | 100% QC Set due to EoA |  |  | billed |  |  | 2017-12-27 |  | 1 | 2017-12-27 | Done
1421 | KXAS Remodel | E171201b | 2017-12-07 | Rev 4 instructions |  |  | billed |  |  | 2017-12-07 |  | 1 | 2017-12-04 | Done
1421 | KXAS Remodel | E171207e | 2017-12-07 | More instructions |  |  | billed |  |  | 2017-12-07 |  |  | 2017-12-04 | Done
1421 | KXAS Remodel | E171207g | 2017-12-07 | Update abase |  |  | billed |  |  | 2017-12-07 |  | 0.5 | 2017-12-04 | Done
1477 | Eugene McCray Recreation Center |  |  | Bidding |  |  | billed |  |  | 2017-11-15 |  |  | 2017-11-15 | Done
1478 | Handley Meadowbrook Rec Center |  |  | Bidding |  |  | billed | [5 empty] | 2017-11-15 | Done
1600 | Gun Experience |  | 2017-12-05 | Change MP to 1200 A |  |  | billed | 1 |  | 2017-12-07 |  | 0 | 2017-12-12 | Done
1416 | DCCCD Eastfield Generator |  | 2017-11-15 | Payment Request | Placeholder for billing |  | billed | [5 empty] | 2017-11-15 | Done
1615 | Celeris (2017) |  | 2017-12-06 | Projects |  |  | billed |  |  | 2017-12-06 |  | 0.5 | 2017-12-06 | Done
1535 | Cornerstone Baptist Church |  | 2017-12-06 | Email regarding ltg controls |  |  | billed |  |  | 2017-12-06 |  | 1 | 2017-12-06 | Done
1631 | Brown Street Church Addition | E171206a | 2017-12-06 | revision 7 dated 12/6 |  |  | billed |  |  |  |  | 1 | 2017-12-06 | Done
1421 | KXAS Remodel |  | 2017-12-07 | Add switch to hall 1070 |  |  | billed |  |  | 2017-12-07 |  | 0.5 | 2017-12-04 | Done
1538 | UNT Coliseum Concourse | E171206c | 2017-12-06 | RR lighting calculations |  |  | billed |  |  | 2017-12-06 |  | 2 | 2017-12-07 | Done
1670 | Brookhaven Generator |  | 2017-12-06 | Send contract to Sharon |  |  | billed |  |  | 2017-12-06 |  | 1 | 2017-12-06 | Done
1688 | Parkwood Cycling Center | E171206d | 2017-12-06 | Proposal |  |  | billed |  |  |  |  | 0.5 | 2017-12-07 | Done
1583 | 7 City Church | E171207a | 2017-12-07 | Review docs and plan DD submittal |  |  | billed | 6 |  | 2017-12-08 |  | 1 | 2017-12-18 | Done
1615 | Celeris (2017) | p11-46 | 2017-12-07 | Blanco note wording |  |  | billed |  |  | 2017-12-07 |  | 1 | 2017-12-07 | Done
1421 | KXAS Remodel | E171207g | 2017-12-08 | Comments |  |  | billed |  |  | 2017-12-08 |  | 1 | 2017-12-08 | Done
1671 | CE DFW Conference Room | E171207b | 2017-12-07 | Design Site Visit |  |  | billed |  |  | 2017-12-08 | 3 | 3 | 2017-12-08 | Done
1421 | KXAS Remodel | E171206b | 2017-12-08 | Ceiling revisions proposal to Scott |  |  | billed |  |  | 2017-12-08 |  | 1 | 2017-12-10 | Done
1614 | Euless Library | E171207f | 2017-12-07 | DD instructions | 12/8 Talked to Tim. He will propose the end of Jan Print and review DD set and assess 50% CD by 1/8 |  | billed |  |  | 2017-12-07 |  |  | 2017-12-08 | Done
1421 | KXAS Remodel | E171211a | 2017-12-11 | Chief's office surface lighting |  |  | billed |  |  | 2017-12-11 |  | 0.5 | 2017-12-11 | Done
1421 | KXAS Remodel | E180103a | 2018-01-03 | Change order assessment |  |  | no |  |  | 2018-01-03 |  | 1 | 2018-01-03 | Done
1421 | KXAS Remodel | E180105f | 2018-01-05 | LTG in Hall 1030 |  |  | no |  |  |  |  | 0.5 | 2018-01-05 | Done
1671 | CE DFW Conference Room |  | 2017-12-08 | Design Narrative and LTG design |  |  | no |  |  | 2017-12-27 | 2 | 4 | 2018-01-09 | Done
1421 | KXAS Remodel | E171206b | 2018-01-09 | Revision 5? | 7/3 Old Item. Follow up on scope. | Scott's | no | 5 |  | 2018-01-10 |  |  | 2018-07-04 | Done
1676 | National Indoor RV Building |  | 2017-12-08 | Recalculate fee for new scope |  |  | billed |  |  | 2017-12-08 |  | 0.5 | 2017-12-10 | Done
1421 | KXAS Remodel |  | 2018-01-09 | Revision 4 | For billing purposes |  | billed | [5 empty] | 2017-12-06 | Done
1661 | Othello's Restaurant | E171212a | 2017-12-12 | COMCheck |  |  | billed | 2 |  | 2017-12-12 |  | 1 | 2017-12-12 | Done
1640 | Joyce Dr Changes | E171212b | 2017-12-12 | Revision 1 | See email for information |  | billed | 4 |  | 2017-12-12 |  | 1 | 2017-12-14 | Done
1631 | Brown Street Church Addition | E171212c | 2017-12-12 | Revision 8 | See email for information |  | billed | 3 |  | 2017-12-12 |  | 2 | 2017-12-14 | Done
1583 | 7 City Church |  | 2017-12-13 | Set up files |  |  | billed |  |  |  |  | 4 | 2017-12-13 | Done
1615 | Celeris (2017) |  | 2017-12-13 | Projects |  |  | billed |  |  |  |  | 0.5 | 2017-12-13 | Done
1614 | Euless Library | E171214a | 2017-12-14 | 50% CD deadline |  |  | billed |  | 2018-02-05 | 2018-02-05 |  | 1 | 2018-02-05 | Done
1614 | Euless Library | E171214a | 2017-12-14 | 100% CD deadline |  |  | billed |  | 2018-03-12 | 2018-03-12 |  |  | 2018-03-10 | Done
1583 | 7 City Church |  | 2017-12-14 | LTG |  |  | billed |  |  | 2017-12-14 |  | 4 | 2017-12-14 | Done
1583 | 7 City Church |  | 2017-12-14 | PWR |  |  | billed |  |  | 2017-12-15 |  | 3 | 2017-12-15 | Done
1421 | KXAS Remodel | E180110b | 2018-01-10 | FA Submittal |  |  | no |  |  | 2018-01-17 |  | 1 | 2018-01-18 | Done
1583 | 7 City Church | E171214b | 2017-12-14 | Place electrical equip in Storage 108 |  |  | billed |  |  | 2017-12-15 |  | 1 | 2017-12-18 | Done
1689 | Jasco Security Gate |  | 2017-12-15 | Proposal |  |  | billed |  |  |  |  | 0.5 | 2017-12-15 | Done
1615 | Celeris (2017) |  | 2017-12-15 | Projects |  |  | billed |  |  |  |  | 1 | 2017-12-15 | Done
1583 | 7 City Church | E171218b | 2017-12-17 | M Sheets |  |  | billed |  |  | 2017-12-18 | 1 | 2 | 2017-12-18 | Done
1583 | 7 City Church |  | 2017-12-18 | Design Site Visit | @10 AM |  | billed |  |  | 2017-12-19 | 3 | 3 | 2017-12-19 | Done
1600 | Gun Experience | E171218a | 2017-12-18 | Bid questions |  |  | billed |  |  | 2017-12-18 | 1 | 1 | 2017-12-18 | Done
1583 | 7 City Church |  | 2017-12-18 | 50% DD set | Due EOB 12/18 |  | billed |  |  |  |  | 1 | 2017-12-18 | Done
1530 | Brennan Drop-off Changes | E171205b | 2017-12-05 | IFC due to COFW | Superceded | Final confirmation | no |  |  | 2018-01-19 |  |  | 2018-07-22 | Done
1530 | Brennan Drop-off Changes | E171218b | 2017-12-18 | Comments |  |  | billed |  |  | 2017-12-27 |  |  | 2017-12-27 | Done
1683 | Weatherford RR Remodel | E171219a | 2017-12-19 | Update Revit model |  |  | no |  |  | 2017-12-28 |  | 2 | 2018-01-04 | Done
1317 | Joyce Dr PD Station | E171219b | 2017-12-19 | ONCOR Form |  |  | billed |  |  | 2017-12-19 |  | 1 | 2017-12-19 | Done
1671 | CE DFW Conference Room | E171219c | 2017-12-19 | Update base files | Superceded |  | no |  |  | 2017-12-27 |  | 0 | 2018-01-03 | Done
1582 | Northern Hills Elementary Safe Room | E171218c | 2017-12-19 | 50% CDs due | Due on 1/22/18 by noon |  | no |  |  | 2018-01-21 |  | 1 | 2018-01-21 | Done
1582 | Northern Hills Elementary Safe Room | E171218c | 2017-12-19 | 50% CD review meeting | On 1/26 @ 7 AM. Superceded |  | no |  | 2018-01-26 | 2018-01-26 |  |  | 2018-01-22 | Done
1582 | Northern Hills Elementary Safe Room | E171218c | 2017-12-19 | Final sets due | Superceeded E180209b |  | no |  |  | 2018-02-26 |  |  | 2018-02-14 | Done
1683 | Weatherford RR Remodel | E171219d | 2017-12-19 | Site Visit |  |  | billed |  |  | 2017-12-20 | 3 | 3 | 2017-12-20 | Done
1538 | UNT Coliseum Concourse | E171219d | 2017-12-19 | Revise lighting vs RCP | See E171206c |  | no |  |  | 2017-12-27 | 2 | 2 | 2018-01-02 | Done
1661 | Othello's Restaurant | E171220b | 2017-12-20 | Health Department Review | 12/20 - No direct electrical comments. Need to update background. | New backgrounds | billed | [5 empty] | 2018-03-13 | Done
1691 | Sushi Restaurant Dallas | E171220c | 2017-12-20 | Proposal |  |  | billed |  |  |  |  | 0.5 | 2017-12-20 | Done
1416 | DCCCD Eastfield Generator |  | 2017-12-21 | Startup site visit |  |  | billed |  |  |  |  | 4 | 2017-12-21 | Done
1621 | The Creek Church Phase II | E171222a | 2017-12-22 | Revision 4 to the revisions |  |  | billed |  |  | 2017-12-22 | 1 | 1 | 2017-12-22 | Done
1477 | Eugene McCray Recreation Center | E171222b | 2017-12-22 | Invoice bidding |  |  | billed |  |  | 2017-12-22 | 1 | 1 | 2017-12-22 | Done
1661 | Othello's Restaurant | E171222c | 2017-12-22 | Revision 2 |  |  | billed |  |  | 2017-12-22 | 1 | 1 | 2017-12-22 | Done
1615 | Celeris (2017) |  | 2017-12-22 | Dallas DAS |  |  | billed |  |  | 2017-12-27 |  | 1.5 | 2017-12-27 | Done
1530 | Brennan Drop-off Changes | E171213a | 2017-12-25 | New sign locations |  |  | billed |  |  | 2017-12-27 |  |  | 2017-12-27 | Done
1531 | MLK Drop-off Changes | E171213a | 2017-12-25 | New sign locations |  |  | billed |  |  | 2017-12-27 |  |  | 2017-12-27 | Done
1532 | Old Hemphill Drop-off Changes | E171213a | 2017-12-25 | New sign locations |  |  | billed |  |  | 2017-12-27 |  |  | 2017-12-27 | Done
1615 | Celeris (2017) |  | 2017-12-26 | Projects |  |  | billed |  |  |  |  | 0.5 | 2017-12-26 | Done
1530 | Brennan Drop-off Changes | E171226a | 2017-12-27 | Update site base file |  |  | billed |  |  | 2017-12-27 |  |  | 2017-12-27 | Done
1531 | MLK Drop-off Changes | E171226a | 2017-12-27 | Update site base file |  |  | billed |  |  | 2017-12-27 |  |  | 2017-12-27 | Done
1532 | Old Hemphill Drop-off Changes | E171226a | 2017-12-27 | Update site base file |  |  | billed |  |  | 2017-12-27 |  |  | 2017-12-27 | Done
1631 | Brown Street Church Addition | E171227b | 2017-12-27 | RFI 41 |  |  | billed |  |  | 2017-12-27 |  | 0.5 | 2017-12-27 | Done
1615 | Celeris (2017) |  | 2017-12-27 | Projects |  |  | billed |  |  |  |  | 1 | 2017-12-27 | Done
1671 | CE DFW Conference Room | E171228a | 2018-01-02 | Update base files |  |  | no |  |  | 2018-01-02 | 2 | 4 | 2018-01-03 | Done
1530 | Brennan Drop-off Changes | 171218b | 2018-01-02 | Move Card reader to passenger side |  |  | no |  |  | 2018-01-03 |  | 0.5 | 2018-01-03 | Done
1531 | MLK Drop-off Changes | 171218b | 2018-01-02 | Move Card reader to passenger side |  |  | no |  |  | 2018-01-03 |  | 0.5 | 2018-01-03 | Done
1532 | Old Hemphill Drop-off Changes | 171218b | 2018-01-02 | Move Card reader to passenger side |  |  | no |  |  | 2018-01-03 |  | 0.5 | 2018-01-03 | Done
1421 | KXAS Remodel | E180111a | 2018-01-14 | Revision 5 |  |  | no |  |  | 2018-01-14 |  | 1 | 2018-01-15 | Done
1317 | Joyce Dr PD Station | E180103b | 2018-01-03 | Add data to revision |  |  | no |  |  | 2018-01-03 |  | 1 | 2018-01-03 | Done
1693 | The Table Church | E180103c | 2018-01-03 | Proposal |  |  | no |  |  |  |  | 0.5 | 2018-01-03 | Done
1694 | Event Venue in Carrollton | E180103d | 2018-01-03 | Proposal |  |  | no |  |  |  |  | 0.5 | 2018-01-03 | Done
1671 | CE DFW Conference Room | E180104a | 2018-01-04 | Update base files |  |  | no |  |  | 2018-01-05 |  | 1 | 2018-01-09 | Done
1683 | Weatherford RR Remodel |  | 2018-01-04 | LTG PWR DEMO |  |  | no |  |  |  |  | 3 | 2018-01-04 | Done
1317 | Joyce Dr PD Station | E180105a | 2018-01-05 | Follow up on mechanical submittals |  |  | no |  |  | 2018-01-09 |  |  | 2018-01-10 | Done
1501 | Kimbell East Parking | E180105b | 2018-01-05 | Punch List SV | Scheduled at 9 AM |  | billed |  |  | 2018-01-11 |  | 2 | 2018-01-11 | Done
1683 | Weatherford RR Remodel |  | 2018-01-05 | Issue for Review |  |  | no |  |  | 2018-01-05 |  | 3 | 2018-01-05 | Done
1582 | Northern Hills Elementary Safe Room | E180105c | 2018-01-05 | 50% CD review meeting | At 7 AM @ EPS Admin Center, 1001 W. Danforth |  | no |  |  | 2018-01-26 | 5 | 6 | 2018-01-26 | Done
1582 | Northern Hills Elementary Safe Room | E180105d | 2018-01-05 | 100% CDs due | Superceded Drawings and spces due on 2/26/18 |  | billed |  |  | 2018-02-26 |  |  | 2018-03-01 | Done
1317 | Joyce Dr PD Station | E180105e | 2018-01-05 | LTG Submittal |  |  | no |  |  | 2018-01-05 |  | 1 | 2018-01-08 | Done
1421 | KXAS Remodel | E180112b | 2018-01-14 | Review Change request | No comments |  | no |  |  | 2018-01-17 |  |  | 2018-01-18 | Done
1696 | EPIROC Headquarters | E180108a | 2018-01-08 | Proposal |  |  | no |  |  | 2018-01-08 |  | 1 | 2018-01-08 | Done
1614 | Euless Library | E180108b | 2018-01-08 | Update Revit file |  |  | no |  |  | 2018-01-11 |  | 1 | 2018-01-11 | Done
ops | Operations |  | 2018-01-08 | Billing |  |  | no |  |  | 2018-01-08 |  | 1 | 2018-01-09 | Done
1538 | UNT Coliseum Concourse | E180108c | 2018-01-08 | Construction Meeting and SV |  |  | billed |  |  | 2018-01-12 | 4 | 4 | 2018-01-12 | Done
1697 | Moss Insurance Office Addition | p11-56 | 2018-01-09 | Proposal | See also E180109b |  | no | 2 |  | 2018-01-10 | 1 | 1 | 2018-01-10 | Done
1676 | National Indoor RV Building | p11-56 | 2018-01-09 | Elect Room Layout |  |  | no | 3 |  | 2018-01-10 | 2 | 1 | 2018-01-11 | Done
1538 | UNT Coliseum Concourse | E180105g | 2018-01-09 | Check Brian's recommendations |  |  | no |  |  | 2018-01-11 | 1 | 0.5 | 2018-01-11 | Done
1614 | Euless Library | E180108e | 2018-01-09 | Design Meeting | @2PM |  | no |  |  | 2018-01-12 | 3 | 2 | 2018-01-12 | Done
1676 | National Indoor RV Building | E180108f | 2018-01-09 | Add to design criteria | See also E180109c. Cancelled | Design work | billed |  |  | 2018-01-22 |  |  | 2018-03-06 | Done
1676 | National Indoor RV Building | E180109a | 2018-01-09 | Set up project | Cancelled | Design work | billed |  |  | 2018-01-22 |  |  | 2018-03-06 | Done
1421 | KXAS Remodel | E180118b | 2018-01-18 | IT Power | 7/4 Old item | Scott's decision on how to implement | no | [5 empty] | 2018-07-04 | Done
1604 | Botanic Garden Assessment |  | 2018-01-09 | For billing purposes |  |  | billed | [5 empty] | 2017-12-15 | Done
1530 | Brennan Drop-off Changes | E180315d | 2018-03-19 | Easment and conduits | Superceded | IFC Work | no | [5 empty] | 2018-07-22 | Done
1671 | CE DFW Conference Room |  | 2018-01-10 | PWR, EQUIP |  |  | no | 6 |  | 2018-01-10 | 3 | 3 | 2018-01-11 | Done
1317 | Joyce Dr PD Station | E180110a | 2018-01-10 | Revision 2 |  |  | no |  |  | 2018-01-10 |  | 1 | 2018-01-10 | Done
1692 | Celeris (2018) | C180110a | 2018-01-10 | Dallas CC Review |  |  | no |  |  | 2018-01-10 |  | 1 | 2018-01-10 | Done
1421 | KXAS Remodel | E180122e | 2018-01-22 | ASA proposal for site visits |  |  | no |  |  | 2018-01-23 |  | 1 | 2018-01-23 | Done
1686 | Ludelle Warehouse Narrative | E180110d | 2018-01-10 | Narrative | 1/23 Deadline is the end of the month. Tim to follow up on materials 1/22 Need to fp on date | Tim's input | no |  |  | 2018-01-23 |  |  | 2018-03-13 | Done
1531 | MLK Drop-off Changes | E171205b | 2017-12-05 | IFC due to COFW | Superceded | Final confirmation | no |  |  | 2018-01-19 |  |  | 2018-07-22 | Done
1628 | Machine House | E180111b | 2018-01-11 | Issue for Construction |  |  | no |  |  | 2018-01-11 |  | 1 | 2018-01-11 | Done
1670 | Brookhaven Generator | E180111c | 2018-01-11 | KO Meeting |  |  | no |  | 2018-01-29 | 2018-01-29 | 3 | 3 | 2018-01-29 | Done
1501 | Kimbell East Parking |  | 2018-01-13 | Punch list Report |  |  | no | 2 |  | 2018-01-14 |  | 1 | 2018-01-14 | Done
1671 | CE DFW Conference Room |  | 2018-01-13 | OL, LTG Switch, Energy |  |  | no | 3 |  | 2018-01-14 |  | 2 | 2018-01-14 | Done
1671 | CE DFW Conference Room |  | 2018-01-13 | QC and IFC |  |  | billed | 3 |  | 2018-01-14 |  | 1 | 2018-01-14 | Done
1692 | Celeris (2018) |  | 2018-01-14 | Dallas CC Seal |  |  | billed |  |  | 2018-01-14 |  | 0.5 | 2018-01-14 | Done
1538 | UNT Coliseum Concourse | E180112h | 2018-01-14 | SV Report |  |  | billed | 4 |  | 2018-01-14 |  | 1 | 2018-01-14 | Done
1697 | Moss Insurance Office Addition | E180109b | 2018-01-14 | Design Site Visit | 9:00 AM |  | no |  |  | 2018-01-19 | 3 | 2 | 2018-01-19 | Done
1421 | KXAS Remodel | E180122h | 2018-01-22 | Submittal log review |  |  | no |  |  | 2018-01-23 |  | 1 | 2018-01-23 | Done
1582 | Northern Hills Elementary Safe Room | E180112a | 2018-01-14 | LTG information forthcoming | Not received prior to 50% Set. |  | no |  |  | 2018-01-19 |  |  | 2018-01-21 | Done
1421 | KXAS Remodel | E180126d | 2018-01-28 | Talk to Tim about DDC submittal | done | Talk to Tim | no | [5 empty] | 2018-07-04 | Done
1317 | Joyce Dr PD Station | E180112c | 2018-01-14 | PWR Dist Submittal |  |  | no |  |  | 2018-01-18 |  | 0.5 | 2018-01-18 | Done
1538 | UNT Coliseum Concourse | E180112d | 2018-01-14 | Revision # 8. | See notes plus email for power. Sent for review under E180115c |  | no |  |  | 2018-01-15 |  | 5 | 2018-01-15 | Done
1531 | MLK Drop-off Changes | E180315d | 2018-03-19 | Easment and conduits | Superceded | IFC Work | no | [5 empty] | 2018-07-22 | Done
1317 | Joyce Dr PD Station | E180112f | 2018-01-14 | RFI # 8 | 1/14 Requires a SV. (proposed 1/18) |  | no | 1 |  | 2018-01-19 |  | 0 | 2018-01-19 | Done
1538 | UNT Coliseum Concourse | E180112g | 2018-01-14 | Reference only. | Email has link to Box site. |  | no |  |  |  |  | 1 | 2018-01-14 | Done
1613 | Norman Hotel |  | 2018-01-14 | Review new docs for additional scope | 1/24 SV postponed to week of 2/5 1/23 Need confirmation for SV |  | no |  |  | 2018-02-05 |  |  | 2018-02-05 | Done
ops | Operations |  | 2018-01-14 | Fix Remaining column in Master List |  |  | no |  |  | 2018-01-20 |  |  | 2018-01-22 | Done
1582 | Northern Hills Elementary Safe Room | E180115a | 2018-01-15 | Update base files |  |  | no |  |  | 2018-01-18 |  | 1 | 2018-01-18 | Done
1538 | UNT Coliseum Concourse | E180122d | 2018-01-15 | Issue Revision 6 |  |  | no |  |  | 2018-01-19 |  | 3 | 2018-01-22 | Done
1578 | WRMC Street Lighting | E180115b | 2018-01-15 | Reduced scope IFC | follow up on date | Architectural | billed |  |  | 2018-01-19 |  |  | 2018-03-13 | Done
1691 | Sushi Restaurant Dallas | E180116a | 2018-01-16 | Site Visit |  |  | no |  |  | 2018-01-17 | 3 | 3 | 2018-01-17 | Done
1582 | Northern Hills Elementary Safe Room | E180116c | 2018-01-16 | SPECS |  |  | no |  |  | 2018-01-21 |  | 1 | 2018-01-21 | Done
1538 | UNT Coliseum Concourse | E180116d | 2018-01-16 | RFI 77 |  |  | no |  |  | 2018-01-16 | 1 | 1 | 2018-01-16 | Done
1582 | Northern Hills Elementary Safe Room | E180116e | 2018-01-16 | LTG level recommendations |  |  | no |  |  | 2018-01-16 | 1 | 1 | 2018-01-16 | Done
1697 | Moss Insurance Office Addition | E170105d | 2018-01-16 | Process base files. Set up project |  |  | no |  |  | 2018-01-24 |  | 1.5 | 2018-01-24 | Done
1583 | 7 City Church | E180115e | 2018-01-17 | Review LTG calcs from Morrow |  |  | no |  |  | 2018-01-17 |  | 1 | 2018-01-17 | Done
1317 | Joyce Dr PD Station | E180117b | 2018-01-17 | FA Question |  |  | no |  |  | 2018-01-17 |  | 0.5 | 2018-01-17 | Done
1696 | EPIROC Headquarters | [5 empty] | no |  |  |  |  | 0.5 | 2018-01-17 | Done
1692 | Celeris (2018) |  | 2018-01-17 | POTTER 14294363 REV 1 IFC CDs 01-17-18 |  |  | no |  |  |  |  | 0.5 | 2018-01-17 | Done
1631 | Brown Street Church Addition | E180118a | 2018-01-18 | Fixture D Question |  |  | no |  |  |  |  | 0.5 | 2018-01-18 | Done
1671 | CE DFW Conference Room |  | 2018-01-18 | Issue for Construction |  |  | billed |  |  | 2018-01-18 | 1 | 3 | 2018-01-18 | Done
1532 | Old Hemphill Drop-off Changes | E171205b | 2017-12-05 | IFC due to COFW | Superceded | Final confirmation | no |  |  | 2018-01-19 |  |  | 2018-07-22 | Done
1582 | Northern Hills Elementary Safe Room | E180117a | 2018-01-18 | Add power and data in millwork as in earlier project |  |  | no |  |  | 2018-01-19 |  | 1 | 2018-01-21 | Done
1582 | Northern Hills Elementary Safe Room | E180118c | 2018-01-18 | Add basement to scope. | See email. |  | no |  |  | 2018-01-19 |  | 0.5 | 2018-01-20 | Done
1692 | Celeris (2018) |  | 2018-01-18 | MCLENNAN 14218771 CDs REV 2 IFC 01-18-18 |  |  | no |  |  |  |  | 0.5 | 2018-01-18 | Done
1317 | Joyce Dr PD Station | E180112f | 2018-01-18 | Revision 3 |  |  | no |  |  | 2018-01-19 |  | 1 | 2018-01-19 | Done
1702 | 3-story Office Building-Fort Worth | E180118d | 2018-01-18 | Proposal |  |  | No |  |  | 2018-01-18 |  | 0.5 | 2018-01-18 | Done
1692 | Celeris (2018) |  | 2018-01-18 | Review Brandon's docs |  |  | no |  |  | 2018-01-19 |  | 1 | 2018-01-22 | Done
1614 | Euless Library | E180119b | 2018-01-19 | Under carpet raceway system links | for reference |  | no | [5 empty] | 2018-01-19 | Done
1582 | Northern Hills Elementary Safe Room | E180119c | 2018-01-19 | Update border |  |  | no |  |  | 2018-01-19 |  | 1 | 2018-01-20 | Done
1538 | UNT Coliseum Concourse |  | 2018-01-19 | LTG meeting at EoA |  |  | no |  |  | 2018-01-19 | 2 | 2 | 2018-01-19 | Done
1582 | Northern Hills Elementary Safe Room | E180119d | 2018-01-20 | Coordinate MP sheets |  |  | no |  |  | 2018-01-20 |  | 1 | 2018-01-20 | Done
1582 | Northern Hills Elementary Safe Room | e180116e | 2018-01-21 | Update LTG definitions |  |  | no |  |  | 2018-01-21 |  | 1 | 2018-01-21 | Done
1703 | Aledo Retail | E180122a | 2018-01-22 | Proposal |  |  | no |  |  |  |  | 0.5 | 2018-01-22 | Done
1704 | Knights Inn Willow Park | E180122b | 2018-01-22 | Proposal |  |  | no |  |  |  |  | 0.5 | 2018-01-22 | Done
1532 | Old Hemphill Drop-off Changes | E180315d | 2018-03-19 | Easment and conduits | Superceded | IFC Work | no | [5 empty] | 2018-07-22 | Done
1705 | North Fort Worth Baptist Church | E180122c | 2018-01-22 | Proposal | 1/22 Need Tims SF input |  | no |  |  | 2018-01-23 |  | 0.5 | 2018-01-23 | Done
1421 | KXAS Remodel | E180126c | 2018-01-28 | Research shunt trip on elevator. | Update |  | no |  |  | 2018-01-29 |  | 0.5 | 2018-01-28 | Done
1701 | Celeris New Office | E180119e | 2018-01-22 | Prepare proposal |  |  | no |  |  | 2018-01-22 |  | 1 | 2018-01-22 | Done
1691 | Sushi Restaurant Dallas | E180119f | 2018-01-22 | Set up project |  | Kitchen Equipment | no |  |  | 2018-01-30 |  | 2 | 2018-02-15 | Done
1317 | Joyce Dr PD Station | E180119g | 2018-01-22 | LTG Submittal |  |  | no |  |  | 2018-01-22 |  | 1 | 2018-01-22 | Done
1583 | 7 City Church | E180120a | 2018-01-22 | Implement comments |  |  | no |  |  | 2018-01-30 |  | 1 | 2018-01-31 | Done
1578 | WRMC Street Lighting | E180122f | 2018-01-22 | Update DWGs and plan for new scope |  |  | billed |  | 2018-01-25 | 2018-01-24 |  | 1 | 2018-01-24 | Done
1621 | The Creek Church Phase II | E180122g | 2018-01-22 | Elevator Shop Drawings |  |  | no |  |  | 2018-01-23 |  | 1 | 2018-01-23 | Done
1421 | KXAS Remodel | E180126g | 2018-01-28 | Review Change orders |  |  | no |  |  | 2018-01-30 |  | 0.5 | 2018-01-30 | Done
1530 | Brennan Drop-off Changes | E180122j | 2018-01-22 | Update site plan | Respond to Scott about sched |  | no |  |  | 2018-01-23 |  | 0.5 | 2018-01-23 | Done
1531 | MLK Drop-off Changes | E180122j | 2018-01-22 | Update site plan | Respond to Scott about sched |  | no |  |  | 2018-01-23 |  | 0.5 | 2018-01-23 | Done
1532 | Old Hemphill Drop-off Changes | E180122j | 2018-01-22 | Update site plan | Respond to Scott about sched |  | no |  |  | 2018-01-23 |  | 0.5 | 2018-01-23 | Done
1530 | Brennan Drop-off Changes | E180122j | 2018-01-22 | Issue new review set |  |  | no |  | 2018-01-26 | 2018-01-23 |  |  | 2018-01-23 | Done
1531 | MLK Drop-off Changes | E180122j | 2018-01-22 | Issue new review set |  |  | no |  | 2018-01-26 | 2018-01-23 |  |  | 2018-01-23 | Done
1532 | Old Hemphill Drop-off Changes | E180122j | 2018-01-22 | Issue new review set |  |  | no |  | 2018-01-26 | 2018-01-23 |  |  | 2018-01-23 | Done
1613 | Norman Hotel |  | 2018-01-22 | Site Visit | 2/5 Conformed: 2/6 @ 10am 1/24 Confirm date |  | no |  | 2018-02-06 | 2018-02-06 | 6 | 6 | 2018-02-06 | Done
1692 | Celeris (2018) |  | 2018-01-22 | Add panel schedules to ATC |  |  | no |  |  | 2018-01-23 |  | 1 | 2018-01-23 | Done
ops | Operations |  | 2018-01-22 | Shareholders and Board Mtgs | Transferred to To do List |  | no |  |  | 2019-01-15 |  |  | 2019-01-07 | Done
1697 | Moss Insurance Office Addition |  | 2018-01-22 | Send XTB to Tim |  |  | no |  |  | 2018-01-22 |  | 0.5 | 2018-01-22 | Done
1676 | National Indoor RV Building | p11-64 | 2018-01-23 | Deadline is Mid February | Cancelled | Tim's confirmation | billed | [5 empty] | 2018-03-06 | Done
1583 | 7 City Church | p11-64 | 2018-01-23 | Deadline | Week of 1/29-2/2 |  | billed |  |  | 2018-01-31 |  | 0.5 | 2018-01-31 | Done
1697 | Moss Insurance Office Addition | p11-64 | 2018-01-23 | Need information on NW room. | 1/24 It is a storage room 1/23 Sent email to pierce |  | no |  |  | 2018-01-24 |  | 0.5 | 2018-01-24 | Done
1706 | The Joint Windsong Ranch | p11-64 | 2018-01-23 | Review Set | E180124b |  | no |  | 2018-01-29 | 2018-01-24 |  | 1 | 2018-01-24 | Done
1631 | Brown Street Church Addition | E180123a | 2018-01-23 | RFI 49 | Was for AVL, sent to Eric |  | no |  |  |  |  | 0.5 | 2018-01-23 | Done
1706 | The Joint Windsong Ranch | E180123b | 2018-01-23 | Set up project |  |  | no |  |  | 2018-01-24 |  | 2 | 2018-01-24 | Done
1707 | Ryan Schools | E180123e | 2018-01-23 | Prepare proposal |  |  | no |  |  | 2018-01-24 |  | 0.5 | 2018-01-24 | Done
1416 | DCCCD Eastfield Generator | E180123d | 2018-01-23 | Final walk through | 1/24 Set for 1/29 at 1 PM 1/23 Proposed Monday 1/29 |  | no |  |  | 2018-01-29 |  | 3 | 2018-01-29 | Done
1559 | Southlake MOB Shell | E180123f | 2018-01-23 | Panel Submittal |  |  | no |  |  | 2018-01-24 |  | 1 | 2018-01-24 | Done
1317 | Joyce Dr PD Station | E180123g | 2018-01-23 | Review Change Order | Not needed |  | no |  |  | 2018-01-24 |  |  | 2018-01-24 | Done
1701 | Celeris New Office |  | 2018-01-24 | Review Set |  |  | no |  | 2018-02-07 | 2018-02-07 |  | 4 | 2018-02-07 | Done
1701 | Celeris New Office |  | 2018-01-24 | Set up project |  |  | no |  |  | 2018-01-24 |  | 1.5 | 2018-01-24 | Done
1697 | Moss Insurance Office Addition |  | 2018-01-24 | Review Set |  |  | no |  |  | 2018-01-28 |  | 3 | 2018-01-28 | Done
1532 | Old Hemphill Drop-off Changes | E180513a | 2018-05-17 | Monument sign revision | superceded | Scott's Approval | no | [5 empty] | 2018-07-22 | Done
1582 | Northern Hills Elementary Safe Room |  | 2018-01-24 | Prepare for SV | Superseded |  | no |  |  | 2018-02-05 |  |  | 2018-02-05 | Done
1538 | UNT Coliseum Concourse | E180220b | 2018-02-20 | Add F lights to west soffit | Done by email | Revision Work | no | [5 empty] | 2018-07-22 | Done
1548 | Precision Hayes | E180125c | 2018-01-25 | Provide CAD files |  |  | no |  |  | 2018-01-30 |  | 1 | 2018-01-29 | Done
1538 | UNT Coliseum Concourse | E180125b | 2018-01-25 | RFI 77 Clarification |  |  | no |  |  |  |  | 0.5 | 2018-01-25 | Done
1708 | Velma Schools | E180125d | 2018-01-25 | LTG Selection |  |  | no |  |  | 2018-01-30 |  | 1 | 2018-01-30 | Done
1701 | Celeris New Office | Celeris | 2018-01-25 | Mechanical Pics forwared to Tim |  |  | no | [5 empty] | 2018-01-25 | Done
1692 | Celeris (2018) | Celeris | 2018-01-25 | ATC requires 3 units on each panel |  |  | no |  |  |  |  | 0.5 | 2018-01-25 | Done
1697 | Moss Insurance Office Addition | E180125e | 2018-01-27 | MP Sheets |  |  | no |  |  | 2018-01-28 |  | 1 | 2018-01-28 | Done
1613 | Norman Hotel | E180126a | 2018-01-26 | Additional Scope |  | Talk to Tim | billed | [5 empty] | 2018-04-29 | Done
1583 | 7 City Church | E180125f | 2018-01-28 | Update Revit File |  |  | no |  |  | 2018-01-28 |  | 0.5 | 2018-01-28 | Done
1538 | UNT Coliseum Concourse | E180126b | 2018-01-28 | New Restrooms | Revision 7 |  | no |  |  | 2018-01-29 |  | 1 | 2018-01-29 | Done
1421 | KXAS Remodel |  | 2018-02-28 | CA work |  |  | billed | [5 empty] | 2018-02-28 | Done
OPS | Operations | E180126c | 2018-01-28 | Add Shunt trip to elevator disconnect | From KXAS |  | no |  |  | 2018-01-30 |  | 0.5 | 2018-01-30 | Done
1538 | UNT Coliseum Concourse | E180419a | 2018-04-23 | RFI 96 | Superceded |  | no |  | 2018-04-23 | 2018-04-23 |  |  | 2018-05-19 | Done
1538 | UNT Coliseum Concourse | E180126e | 2018-01-28 | RFI 78 - Grounding cable | 2/8 No news, good news Need Mike's preference |  | no |  |  | 2018-02-07 |  |  | 2018-02-08 | Done
1582 | Northern Hills Elementary Safe Room | E180517d | 2018-05-17 | LTG RFI | 5/18 Sent email to James |  | no |  |  | 2018-05-20 |  | 0.5 | 2018-05-22 | Done
1421 | KXAS Remodel | E180311a | 2018-03-14 | Quad sketch |  |  | billed |  |  | 2018-03-14 |  | 1 | 2018-03-14 | Done
1317 | Joyce Dr PD Station | E180126h | 2018-01-28 | Gear Submittal |  |  | no |  |  | 2018-01-31 |  | 0.5 | 2018-01-30 | Done
1706 | The Joint Windsong Ranch | E180128a | 2018-01-28 | Resend review set |  |  | no |  |  |  |  | 0 | 2018-01-28 | Done
1683 | Weatherford RR Remodel | E180128b | 2018-01-28 | final Comments | Add flush sensors, too. See email |  | billed |  |  | 2018-01-30 |  | 3 | 2018-01-30 | Done
1582 | Northern Hills Elementary Safe Room | E180129a | 2018-01-29 | Meeting Report |  |  | no |  |  | 2018-01-30 |  | 1 | 2018-01-30 | Done
1530 | Brennan Drop-off Changes | E180129b | 2018-01-29 | Forbid MC Cable |  |  | no |  |  | 2018-02-09 |  | 0.5 | 2018-02-09 | Done
1692 | Celeris (2018) | Celeris | 2018-01-29 | Anahuac |  |  | no |  |  | 2018-01-29 |  | 0.5 | 2018-01-29 | Done
1670 | Brookhaven Generator |  | 2018-01-29 | Coordinate initial SV | 1/30 Confirmed: 2/7 at 10 am 1/30 Asked for 2/7 |  | no |  |  | 2018-01-31 |  | 0.5 | 2018-01-30 | Done
1692 | Celeris (2018) | Celeris | 2018-01-29 | Review Garland Project |  |  | no |  |  | 2018-01-30 | 1 | 0.5 | 2018-01-30 | Done
1582 | Northern Hills Elementary Safe Room | E180129c | 2018-01-29 | Review Latest Design Guidelines |  |  | no |  |  | 2018-01-31 |  | 2 | 2018-02-01 | Done
1697 | Moss Insurance Office Addition | E180115d | 2018-01-29 | Clarify FCU closet dimensions |  |  | no |  |  | 2018-01-30 |  | 0.5 | 2018-01-30 | Done
ops | Operations | E180129d | 2018-01-29 | Add Shunt trip to elevator disconnect |  |  | no |  |  | 2018-01-31 |  |  | 2018-01-30 | Done
1706 | The Joint Windsong Ranch | E180129e | 2018-01-29 | Lana's comments |  |  | billed |  |  | 2018-01-29 |  | 1 | 2018-01-29 | Done
1416 | DCCCD Eastfield Generator | E180130b | 2018-01-29 | Punch list Report |  |  | billed |  |  | 2018-01-30 |  | 1 | 2018-01-30 | Done
1683 | Weatherford RR Remodel |  | 2018-01-30 | Verify HP4 can be wall mounted |  |  | no |  |  | 2018-01-30 |  | 0.5 | 2018-01-30 | Done
1708 | Velma Schools |  | 2018-01-30 | Option A |  |  | billed |  |  | 2018-01-30 |  | 0.5 | 2018-01-30 | Done
1708 | Velma Schools |  | 2018-01-30 | Option B |  |  | no |  |  | 2018-01-30 |  | 0.5 | 2018-01-30 | Done
1708 | Velma Schools |  | 2018-01-30 | Option C |  |  | no |  |  | 2018-01-30 |  | 0.5 | 2018-01-30 | Done
1317 | Joyce Dr PD Station | E180130a | 2018-01-30 | RCO 004 |  |  | no |  |  | 2018-01-30 |  | 0.5 | 2018-01-30 | Done
1317 | Joyce Dr PD Station | E180130a | 2018-01-30 | RCO 005 |  |  | no |  |  |  |  | 0.5 | 2018-01-30 | Done
1583 | 7 City Church |  | 2018-01-30 | M Sheets |  |  | no |  |  | 2018-01-31 |  | 1 | 2018-01-31 | Done
1697 | Moss Insurance Office Addition |  | 2018-01-30 | Follow up on signed docs |  |  | no |  |  | 2018-01-31 |  |  | 2018-01-30 | Done
1582 | Northern Hills Elementary Safe Room | E180130c | 2018-01-30 | Review 50% CD notes |  | IFC work | no |  |  | 2018-02-01 |  | 2 | 2018-02-20 | Done
1538 | UNT Coliseum Concourse | E180130d | 2018-01-30 | Site Visit |  |  | billed |  |  | 2018-02-12 |  | 2 | 2018-02-12 | Done
1692 | Celeris (2018) | Celeris | 2018-01-30 | Somerset |  |  | no |  |  |  |  | 0.5 | 2018-01-30 | Done
1697 | Moss Insurance Office Addition | E180115d | 2018-01-30 | Send signed and sealed set |  |  | billed |  |  | 2018-01-31 |  | 0 | 2018-01-30 | Done
1708 | Velma Schools |  | 2018-01-30 | Option D |  |  | no |  |  |  |  | 0.5 | 2018-01-30 | Done
1692 | Celeris (2018) | Celeris | 2018-01-30 | Garland ATC |  |  | no |  |  |  |  | 1 | 2018-01-30 | Done
1692 | Celeris (2018) | Celeris | 2018-01-30 | Grimes Rev 2 |  |  | no |  |  |  |  | 0.5 | 2018-01-30 | Done
1697 | Moss Insurance Office Addition |  | 2018-01-30 | COMCheck |  |  | no |  |  | 2018-01-30 |  | 0.5 | 2018-01-30 | Done
1697 | Moss Insurance Office Addition |  | 2018-01-30 | QC and IFC |  |  | no |  |  | 2018-01-30 |  | 0.5 | 2018-01-30 | Done
1583 | 7 City Church |  | 2018-01-30 | Add LTG room definitions |  |  | no |  |  | 2018-01-31 |  | 1 | 2018-01-31 | Done
1583 | 7 City Church |  | 2018-01-30 | Update LTG fixtures |  |  | no |  |  | 2018-01-31 |  | 1 | 2018-01-31 | Done
1583 | 7 City Church |  | 2018-01-30 | LTG Controls |  |  | no |  |  | 2018-01-31 |  | 1 | 2018-01-31 | Done
1582 | Northern Hills Elementary Safe Room | E180130e | 2018-01-30 | Add dedicated receptacles | Done previously for the 95% | IFC Work | billed |  |  |  |  | 0.5 | 2018-03-05 | Done
1582 | Northern Hills Elementary Safe Room | E180130f | 2018-01-30 | LTG Changes | Done previously for the 95% | IFC Work | billed | [5 empty] | 2018-03-05 | Done
1592 | Deer Park Animal Shelter | E180130g | 2018-01-30 | Fire Alarm question |  |  | no |  |  | 2018-01-30 |  | 0.5 | 2018-01-30 | Done
1317 | Joyce Dr PD Station | E180130h | 2018-01-30 | Flat panel lights |  |  | billed |  |  | 2018-01-30 |  | 1 | 2018-01-30 | Done
1559 | Southlake MOB Shell | E180131a | 2018-01-31 | Panel Resubmittal |  |  | billed |  |  | 2018-02-05 |  | 0.5 | 2018-02-05 | Done
1692 | Celeris (2018) | Celeris | 2018-01-31 | Pleasanton, DXL00982 |  |  | no |  |  |  |  | 0.5 | 2018-01-31 | Done
1692 | Celeris (2018) | Celeris | 2018-01-31 | Fort Worth ATC, Denton ATC |  |  | no |  |  |  |  | 2 | 2018-01-31 | Done
1692 | Celeris (2018) | Celeris | 2018-01-31 | Jefferson Co |  |  | no |  |  |  |  | 0.5 | 2018-01-31 | Done
1631 | Brown Street Church Addition | E180201a | 2018-02-01 | Dimmer in multipurpose room |  |  | no |  |  |  |  | 0.5 | 2018-02-01 | Done
1583 | 7 City Church |  | 2017-12-14 | Switching |  | Design work | no | 100CD |  | 2018-01-19 |  |  | 2018-06-25 | Done
1317 | Joyce Dr PD Station | E180201b | 2018-02-01 | Revision 5. Lighting + fire alarm changes | See also E180205a |  | billed |  | 2018-02-05 | 2018-02-02 |  | 2 | 2018-02-05 | Done
1538 | UNT Coliseum Concourse | E180201c | 2018-02-01 | RFI 80 |  |  | no |  |  |  |  | 0.5 | 2018-02-01 | Done
1691 | Sushi Restaurant Dallas | 180130 | 2018-02-01 | Review kitchen equipment and comment |  |  | no |  |  | 2018-02-02 |  | 2 | 2018-02-04 | Done
1692 | Celeris (2018) |  | 2018-02-01 | Taylor Rev 3 |  |  | no |  |  |  |  | 0.5 | 2018-02-01 | Done
1614 | Euless Library |  | 2018-02-01 | LTG Code and Controls. CKT |  |  | no |  |  |  |  | 5 | 2018-02-01 | Done
1614 | Euless Library |  | 2018-02-01 | LTG 50% CD |  |  | no |  |  | 2018-02-02 |  | 3 | 2018-02-04 | Done
1614 | Euless Library |  | 2018-02-01 | PWR recept and data |  |  | no |  |  | 2018-02-02 |  | 3 | 2018-02-04 | Done
1614 | Euless Library | E180204a | 2018-02-01 | EQP MP Sheets |  |  | no |  |  | 2018-02-02 |  | 2 | 2018-02-04 | Done
1583 | 7 City Church |  | 2017-12-18 | EM lighting |  | Design work | no | 100CD |  | 2018-01-19 |  |  | 2018-06-25 | Done
1583 | 7 City Church | E180110c | 2018-01-10 | Update revit file | Superseded | Design work | no | 100CD |  | 2018-01-19 |  |  | 2018-06-25 | Done
1583 | 7 City Church | T180122 | 2018-01-22 | Update Revit File | Superseded | Design work | no |  |  | 2018-01-23 |  |  | 2018-06-25 | Done
1583 | 7 City Church | E180213d | 2018-02-13 | Review lighting notes from John | Addressed | IFC Work | no | [5 empty] | 2018-06-25 | Done
1583 | 7 City Church | E180223b | 2018-02-27 | MEP Comments | 3/3 There are some comments left. | IFC Work | no |  |  | 2018-03-08 |  |  | 2018-06-26 | Done
1614 | Euless Library | E180202a | 2018-02-02 | Update Revit model |  |  | no |  |  | 2018-02-02 |  | 0.5 | 2018-02-24 | Done
1676 | National Indoor RV Building | E180202b | 2018-02-02 | Review DD Set | Cancelled | IFC Work | billed |  |  | 2018-02-10 |  |  | 2018-03-06 | Done
1676 | National Indoor RV Building | E180202c | 2018-02-02 | Detailed Narrative | Cancelled | IFC work | billed |  |  | 2018-02-13 |  |  | 2018-03-06 | Done
1614 | Euless Library | E180202e | 2018-02-02 | IT Layout meeting | 2/7 Cancelled Postponed. Maybe Thursday 2/8? |  | no |  |  | 2018-02-08 | 2 |  | 2018-02-07 | Done
1697 | Moss Insurance Office Addition | E180202f | 2018-02-02 | Reviewer Comments | Revision 1 |  | no |  |  | 2018-02-02 |  | 1 | 2018-02-02 | Done
1614 | Euless Library |  | 2018-02-04 | IT markup coordination meeting | Cancelled |  | no |  |  | 2018-02-05 | 3 |  | 2018-02-05 | Done
1631 | Brown Street Church Addition | E180201d | 2018-02-05 | Cross out unwanted submittals from log |  |  | no |  |  | 2018-02-05 |  | 0.5 | 2018-02-05 | Done
1692 | Celeris (2018) | Celeris | 2018-02-05 | Clay Rev 2 |  |  | no |  |  |  |  | 0.5 | 2018-02-05 | Done
1631 | Brown Street Church Addition | E180202g | 2018-02-05 | RFI 53 |  |  | no |  |  | 2018-02-05 |  | 0.5 | 2018-02-05 | Done
1676 | National Indoor RV Building | E180203a | 2018-02-05 | Update base files | Superceeded E180208b | IFC Work | no |  |  | 2018-02-07 |  |  | 2018-02-08 | Done
1683 | Weatherford RR Remodel | E180205b | 2018-02-05 | Update IFC to new date |  |  | no |  |  | 2018-02-05 |  | 0.5 | 2018-02-05 | Done
1614 | Euless Library | E180205c | 2018-02-05 | Send list of Qs to Jim Tharp |  |  | no |  |  | 2018-02-07 |  | 0.5 | 2018-02-08 | Done
1317 | Joyce Dr PD Station | E180205d | 2018-02-05 | Review RCOs 6 and 7 |  |  | no |  |  | 2018-02-05 |  | 0.5 | 2018-02-05 | Done
1582 | Northern Hills Elementary Safe Room | E180130f | 2018-02-05 | Review new lighting comments | Done previously for the 95% | IFC work | billed | [5 empty] | 2018-03-05 | Done
1614 | Euless Library |  | 2018-02-05 | Prepare for coordination meeting | 2/8 Meeting cancelled 2/5 IT markups in file |  | no |  |  | 2018-02-07 |  |  | 2018-02-08 | Done
1691 | Sushi Restaurant Dallas |  | 2018-02-05 | Send list of Qs to Tim | Not needed |  | no |  |  | 2018-02-14 |  |  | 2018-02-16 | Done
1613 | Norman Hotel |  | 2018-02-05 | Prepare for SV |  |  | no |  |  | 2018-02-05 |  | 0.5 | 2018-02-05 | Done
1692 | Celeris (2018) | Celeris | 2018-02-06 | Flores Rev 6 |  |  | no |  |  |  |  | 0.5 | 2018-02-06 | Done
1692 | Celeris (2018) | Celeris | 2018-02-06 | DX4754 Rev 1 |  |  | no |  |  |  |  | 0.5 | 2018-02-06 | Done
1692 | Celeris (2018) | Celeris | 2018-02-06 | DX4756 Rev 1 |  |  | no |  |  |  |  | 0.5 | 2018-02-06 | Done
1692 | Celeris (2018) | Celeris | 2018-02-06 | Pleasanton, DXL00982 Rev 2 |  |  | no |  |  |  |  | 0.5 | 2018-02-06 | Done
1692 | Celeris (2018) | Celeris | 2018-02-06 | Webb Co. Center Rev 2 |  |  | no |  |  |  |  | 0.5 | 2018-02-06 | Done
1317 | Joyce Dr PD Station | E180206a | 2018-02-06 | Add fixture to copier |  |  | billed |  |  |  |  | 0.5 | 2018-02-06 | Done
1613 | Norman Hotel |  | 2018-02-06 | SV Report |  |  | no |  |  | 2018-02-07 |  | 0.5 | 2018-02-08 | Done
1708 | Velma Schools | Phone call | 2018-02-06 | Provide new Option C |  |  | no |  |  |  |  | 1 | 2018-02-06 | Done
1708 | Velma Schools |  | 2018-02-07 | Send signed and sealed set |  |  | no |  |  |  |  | 0.5 | 2018-02-07 | Done
1701 | Celeris New Office |  | 2018-02-07 | Send review set |  |  | billed |  |  | 2018-02-07 |  | 4 | 2018-02-07 | Done
1709 | Koinonia Church New Offices | E180208a | 2018-02-08 | Proposal |  |  | no |  |  |  |  | 0.5 | 2018-02-08 | Done
1701 | Celeris New Office | Celeris | 2018-02-08 | Review comments from Mark |  |  | no |  |  | 2018-02-10 |  | 0.5 | 2018-02-13 | Done
ops | Operations |  | 2018-02-08 | Invoicing |  |  | no |  |  |  |  | 3 | 2018-02-08 | Done
ops | Operations |  | 2018-02-08 | Invoicing for February |  |  | billed |  |  | 2018-03-02 |  | 2 | 2018-03-02 | Done
1676 | National Indoor RV Building | E180207a | 2018-02-08 | Pricing set for contrator | 2/8 From Tim, this means detailed narrative | IFC Work | billed |  |  | 2018-02-12 | 2 |  | 2018-03-06 | Done
1676 | National Indoor RV Building | E180207a | 2018-02-08 | Design Narrative |  |  | billed |  | 2018-02-24 | 2018-02-21 |  | 6 | 2018-02-21 | Done
1676 | National Indoor RV Building | E180207a | 2018-02-08 | 50%CD | 3/2 On hold per call from Tim | Mike Ansley's confirmation | billed |  | 2018-03-19 | 2018-03-02 |  |  | 2018-03-06 | Done
1676 | National Indoor RV Building | E180207a | 2018-02-08 | 90% CD | Project cancelled |  | billed |  | 2018-04-06 | 2018-03-25 |  |  | 2018-03-29 | Done
1676 | National Indoor RV Building | E180207a | 2018-02-08 | IFC due to GSBS | Project cancelled |  | billed |  | 2018-04-13 | 2018-04-01 |  |  | 2018-03-29 | Done
1676 | National Indoor RV Building | E180208b | 2018-02-08 | Base files | Cancelled | IFC Work | billed | [5 empty] | 2018-03-06 | Done
1530 | Brennan Drop-off Changes | E180206b | 2018-02-08 | Card reader details | Docs in Brennan |  | no |  |  | 2018-02-09 |  |  | 2018-02-09 | Done
1531 | MLK Drop-off Changes | E180206b | 2018-02-08 | Card reader details | Docs in Brennan |  | no |  |  | 2018-02-09 |  | 0.5 | 2018-02-09 | Done
1532 | Old Hemphill Drop-off Changes | E180206b | 2018-02-08 | Card reader details | Docs in Brennan |  | no |  |  | 2018-02-09 |  |  | 2018-02-09 | Done
1530 | Brennan Drop-off Changes | E180208c | 2018-02-08 | Guard house new card readers |  |  | no |  |  | 2018-02-09 |  | 0.5 | 2018-02-09 | Done
1530 | Brennan Drop-off Changes | E180208d | 2018-02-08 | Spec changes | See email for details |  | no |  |  | 2018-02-09 |  | 0.5 | 2018-02-09 | Done
1530 | Brennan Drop-off Changes | E180208e | 2018-02-08 | Add guardhouse plan to dwgs |  |  | no |  |  | 2018-02-09 |  | 0.5 | 2018-02-09 | Done
1530 | Brennan Drop-off Changes | E180208f | 2018-02-08 | Check civil set | No changes to electrical |  | no |  |  | 2018-02-09 |  |  | 2018-02-09 | Done
1531 | MLK Drop-off Changes | E180208c | 2018-02-08 | Guard house new card readers |  |  | no |  |  | 2018-02-09 |  |  | 2018-02-09 | Done
1531 | MLK Drop-off Changes | E180208d | 2018-02-08 | Spec changes | See email for details |  | no |  |  | 2018-02-09 |  |  | 2018-02-09 | Done
1531 | MLK Drop-off Changes | E180208e | 2018-02-08 | Add guardhouse plan to dwgs |  |  | no |  |  | 2018-02-09 |  |  | 2018-02-09 | Done
1531 | MLK Drop-off Changes | E180208f | 2018-02-08 | Check civil set |  |  | no |  |  | 2018-02-09 |  |  | 2018-02-09 | Done
1532 | Old Hemphill Drop-off Changes | E180208c | 2018-02-08 | Guard house new card readers |  |  | no |  |  | 2018-02-09 |  | 0.5 | 2018-02-09 | Done
1532 | Old Hemphill Drop-off Changes | E180208d | 2018-02-08 | Spec changes | See email for details |  | no |  |  | 2018-02-09 |  |  | 2018-02-09 | Done
1532 | Old Hemphill Drop-off Changes | E180208e | 2018-02-08 | Add guardhouse plan to dwgs |  |  | no |  |  | 2018-02-09 |  |  | 2018-02-09 | Done
1532 | Old Hemphill Drop-off Changes | E180208f | 2018-02-08 | Check civil set |  |  | no |  |  | 2018-02-09 |  |  | 2018-02-09 | Done
1691 | Sushi Restaurant Dallas | E180206c | 2018-02-08 | Add LTG information |  |  | no |  |  | 2018-02-14 |  | 1 | 2018-02-15 | Done
1691 | Sushi Restaurant Dallas | E180206d | 2018-02-08 | Clarifications on kitchen equipment |  |  | no |  |  | 2018-02-14 |  | 1 | 2018-02-15 | Done
1317 | Joyce Dr PD Station | E180207b | 2018-02-08 | RFI 34 | 2/12 Answered, see E180212f 2/8 Sent email to Allison. Fp 2/12 |  | no |  |  | 2018-02-12 |  |  | 2018-02-14 | Done
1710 | Jasco Office Addition | E180208g | 2018-02-08 | Proposal |  |  | no |  |  |  |  | 0.5 | 2018-02-08 | Done
1689 | Jasco Security Gate | E180208h | 2018-02-08 | SV | @1 PM |  | no |  |  | 2018-02-19 | 6 | 7 | 2018-02-20 | Done
1583 | 7 City Church | E180223b | 2018-02-27 | 30% CD Set due |  | IFC Work | no |  | 2018-03-14 | 2018-03-13 |  |  | 2018-06-26 | Done
1692 | Celeris (2018) | Celeris | 2018-02-08 | Calhoun Rev 2 |  |  | billed |  |  |  |  | 0.5 | 2018-02-08 | Done
1530 | Brennan Drop-off Changes | E180209a | 2018-02-09 | Send review set |  |  | no | [5 empty] | 2018-02-09 | Done
1701 | Celeris New Office | E180208j | 2018-02-12 | Update base files |  |  | no |  |  | 2018-02-12 |  | 1 | 2018-02-13 | Done
1701 | Celeris New Office | E180212a | 2018-02-12 | HVAC set | 2/13 Need final set. |  | no |  |  | 2018-02-12 |  | 1 | 2018-02-14 | Done
1711 | Funky Town Donut Shop | E180212b | 2018-02-12 | Proposal |  |  | No |  |  | 2018-02-12 |  | 0.5 | 2018-02-12 | Done
1712 | 6ksf New Restaurant | E180212c | 2018-02-12 | Proposal |  |  | No |  |  | 2018-02-12 |  | 0.5 | 2018-02-12 | Done
1621 | The Creek Church Phase II | E180212d | 2018-02-12 | RFI # 2 | 2/19 Got dimensions E180219d '2/12 Replied. Waiting for information |  | no |  |  | 2018-02-19 |  | 0.5 | 2018-02-19 | Done
1697 | Moss Insurance Office Addition | E180212e | 2018-02-12 | Alternate plan | 2/19 Got authorization. Waiting for DWG file 2/12 Replied to email. Waiting for comments. |  | no |  |  | 2018-02-21 |  |  | 2018-02-28 | Done
1692 | Celeris (2018) | Celeris | 2018-02-13 | Warda Rev 0 |  |  | billed |  |  |  |  | 0.5 | 2018-02-13 | Done
1691 | Sushi Restaurant Dallas | E180213a | 2018-02-13 | Update base files |  | IFC Work | no | [5 empty] | 2018-02-15 | Done
1583 | 7 City Church | E180213b | 2018-02-13 | Send COMCheck report to John |  |  | no |  |  | 2018-02-14 |  | 1 | 2018-02-14 | Done
1613 | Norman Hotel | E180213c | 2018-02-13 | Review clarifications |  | Tim's instructions | billed |  |  | 2018-03-16 |  |  | 2018-04-29 | Done
1583 | 7 City Church | E180301a | 2018-03-01 | Update Revit model | Superseded | IFC Work | no | [5 empty] | 2018-06-26 | Done
1701 | Celeris New Office | E180214a | 2018-02-14 | MP Sheets |  |  | no |  |  | 2018-02-14 |  | 1 | 2018-02-14 | Done
1701 | Celeris New Office |  | 2018-02-14 | QC and IFC |  |  | billed |  |  |  |  | 2 | 2018-02-14 | Done
1582 | Northern Hills Elementary Safe Room | E180209b | 2018-02-14 | 95% CD set due | To Kerr 3 |  | no |  | 2018-02-21 | 2018-02-21 |  | 2 | 2018-02-20 | Done
1582 | Northern Hills Elementary Safe Room | E180209b | 2018-02-14 | 95% CD review mtg | @7AM |  | no |  | 2018-02-23 | 2018-02-23 | 6 | 8 | 2018-02-23 | Done
1582 | Northern Hills Elementary Safe Room | E180209b | 2018-02-14 | IFC for bidding | Moved to 3/7 |  | billed |  | 2018-03-18 | 2018-03-18 |  |  | 2018-03-05 | Done
1582 | Northern Hills Elementary Safe Room | E180210a | 2018-02-14 | RCP updates | Superceded | IFC Work | billed | [5 empty] | 2018-03-05 | Done
1582 | Northern Hills Elementary Safe Room | E180210b | 2018-02-14 | Updated base files | Superceded | IFC Work | billed | [5 empty] | 2018-03-05 | Done
1317 | Joyce Dr PD Station | E180213e | 2018-02-14 | Review RCO 3R | 3x3 to 2x4 ltg replacement |  | no |  |  |  |  | 0.5 | 2018-02-14 | Done
1478 | Handley Meadowbrook Rec Center | E180214b | 2018-02-14 | ONCOR Form |  |  | no |  |  |  |  | 1 | 2018-02-14 | Done
1317 | Joyce Dr PD Station | E180214c | 2018-02-14 | Review RCO 6R |  |  | no |  |  |  |  | 0.5 | 2018-02-14 | Done
1317 | Joyce Dr PD Station | E180214d | 2018-02-14 | Review RCO 11 | 2/14 Allision provided ASI 2/14 asked Allison to provide info on scope |  | no |  |  | 2018-02-15 |  | 0.5 | 2018-02-14 | Done
1621 | The Creek Church Phase II | E180212g | 2018-02-14 | LTG and floor box submittal |  |  | billed |  |  | 2018-02-19 |  | 1 | 2018-02-19 | Done
1583 | 7 City Church | E180305b | 2018-03-05 | Cooledge fixture and renderings | Not used | IFC Work | no |  |  | 2018-03-08 |  |  | 2018-06-26 | Done
1583 | 7 City Church | E180313e | 2018-03-19 | Fixture J cut sheet |  | IFC Work | no | [5 empty] | 2018-06-25 | Done
1538 | UNT Coliseum Concourse | E180214e | 2018-02-14 | SV Report |  |  | no |  |  | 2018-02-14 |  | 2 | 2018-02-14 | Done
1701 | Celeris New Office | Celeris | 2018-02-14 | Update base file |  |  | no |  |  | 2018-02-14 |  | 0.5 | 2018-02-14 | Done
1692 | Celeris (2018) | C180214 | 2018-02-14 | NM requirements |  |  | no |  |  | 2018-02-14 |  | 0.5 | 2018-02-15 | Done
1692 | Celeris (2018) | C180214 | 2018-02-14 | ATC Denton |  |  | no |  |  |  |  | 0.5 | 2018-02-14 | Done
1691 | Sushi Restaurant Dallas |  | 2018-02-15 | Kitchen work |  |  | no |  |  |  |  | 3 | 2018-02-15 | Done
1691 | Sushi Restaurant Dallas |  | 2018-02-15 | PWR |  |  | no |  |  |  |  | 3 | 2018-02-15 | Done
1691 | Sushi Restaurant Dallas |  | 2018-02-15 | LTG |  |  | no |  |  |  |  | 3 | 2018-02-15 | Done
1691 | Sushi Restaurant Dallas | E180216b | 2018-02-16 | M items |  |  | no |  |  | 2018-02-16 |  | 0.5 | 2018-02-16 | Done
1582 | Northern Hills Elementary Safe Room | E180218b | 2018-02-18 | LTG coordination + scope definition |  |  | no |  |  |  |  | 3 | 2018-02-18 | Done
1691 | Sushi Restaurant Dallas | E180218a | 2018-02-18 | Updated base files + markups |  |  | no |  |  | 2018-02-19 |  | 0.5 | 2018-02-19 | Done
1691 | Sushi Restaurant Dallas | E180219a | 2018-02-19 | EM lights in restrooms | 2/19 need direction |  | no |  |  | 2018-02-20 |  | 0.5 | 2018-02-20 | Done
1604 | Botanic Garden Assessment | E180219b | 2018-02-19 | Implement final comments | 2/19 Need to coordinate with Tim |  | no |  | 2018-03-02 | 2018-03-01 |  | 2 | 2018-03-01 | Done
1711 | Funky Town Donut Shop | E180219c | 2018-02-19 | NTP |  |  | no | [5 empty] | 2018-02-19 | Done
1689 | Jasco Security Gate | E180219e | 2018-02-19 | Review slides for narrative | Sent drawings |  | no |  |  | 2018-02-26 |  | 2 | 2018-02-26 | Done
1621 | The Creek Church Phase II | E180215a | 2018-02-19 | Access control revision |  |  | billed |  | 2018-02-20 | 2018-02-20 |  | 0.5 | 2018-02-19 | Done
1613 | Norman Hotel | E180216c | 2018-02-19 | Update base files |  | IFC work | billed | [5 empty] | 2018-04-29 | Done
1614 | Euless Library | E180216d | 2018-02-19 | Updated LTG info from Morrow | 3/1 Need to talk to Morrow |  | no |  |  | 2018-03-07 |  |  | 2018-03-07 | Done
1501 | Kimbell East Parking | E180219g | 2018-02-19 | Network issue |  |  | no |  |  | 2018-02-19 |  | 0.5 | 2018-02-19 | Done
1670 | Brookhaven Generator | E180219f | 2018-02-19 | Arch services request |  |  | no |  |  | 2018-02-20 |  |  | 2018-02-20 | Done
1691 | Sushi Restaurant Dallas | E180218a | 2018-02-19 | Review D-SIZE file |  |  | no |  |  | 2018-02-19 |  | 0.5 | 2018-02-19 | Done
1691 | Sushi Restaurant Dallas | E180218a | 2018-02-19 | MEP Markup |  |  | no |  |  | 2018-02-19 |  | 1 | 2018-02-19 | Done
1691 | Sushi Restaurant Dallas | E180218a | 2018-02-19 | Add Inverter |  |  | no |  |  | 2018-02-19 |  | 1 | 2018-02-20 | Done
1691 | Sushi Restaurant Dallas | E180218a | 2018-02-19 | Check RCP DWG |  |  | no |  |  | 2018-02-19 |  | 0.5 | 2018-02-19 | Done
1691 | Sushi Restaurant Dallas | E180218a | 2018-02-19 | Check Equipment |  |  | no |  |  | 2018-02-19 |  | 1 | 2018-02-19 | Done
1582 | Northern Hills Elementary Safe Room | E182019h | 2018-02-19 | MP Sheets |  |  | no |  |  | 2018-02-20 |  | 0.5 | 2018-02-20 | Done
1582 | Northern Hills Elementary Safe Room | E180220a | 2018-02-20 | Update roof plan |  |  | no |  |  | 2018-02-20 |  | 0.5 | 2018-02-20 | Done
1583 | 7 City Church | E180403e | 2018-04-04 | Evaluate phase 1 |  | Tim's instructions | no |  |  | 2018-04-04 |  |  | 2018-06-25 | Done
1692 | Celeris (2018) | C180220 | 2018-02-20 | Otero Fault Calculations |  |  | no |  |  |  |  | 0.5 | 2018-02-20 | Done
1582 | Northern Hills Elementary Safe Room |  | 2018-02-20 | Need to clarify Fire Alarm reqs. | 3/1 Follow original set | IFC Work | billed | [5 empty] | 2018-03-05 | Done
1582 | Northern Hills Elementary Safe Room |  | 2018-02-20 | Specs |  |  | no |  |  |  |  | 2 | 2018-02-20 | Done
1582 | Northern Hills Elementary Safe Room |  | 2018-02-20 | Basement |  |  | no |  |  |  |  | 1 | 2018-02-20 | Done
1317 | Joyce Dr PD Station | E180220c | 2018-02-20 | RFI 039 |  |  | no |  |  | 2018-02-21 |  | 0.5 | 2018-02-21 | Done
1583 | 7 City Church | E180502d | 2018-05-07 | Phase 1 new strategy. |  | IFC Work | no |  | 2018-05-07 | 2018-05-07 |  |  | 2018-06-25 | Done
1477 | Eugene McCray Recreation Center | E180222b | 2018-02-22 | ASA proposal |  |  | no |  | 2018-02-23 | 2018-02-23 |  | 0.5 | 2018-02-26 | Done
1629 | Heritage Glenn MOB Shell | E180222c | 2018-02-22 | Set up project | Superceded E180227f |  | billed |  |  | 2018-03-05 |  |  | 2018-03-01 | Done
1478 | Handley Meadowbrook Rec Center | E180222b | 2018-02-22 | ASA proposal |  |  | no |  | 2018-02-23 | 2018-02-23 |  | 0.5 | 2018-02-26 | Done
1317 | Joyce Dr PD Station | E180222d | 2018-02-22 | Gear Submittal |  |  | billed |  | 2018-02-26 | 2018-02-23 |  | 0.5 | 2018-02-26 | Done
1714 | Dickies Retail Renovation | E180221a | 2018-02-22 | Proposal |  |  | no |  | 2018-02-23 | 2018-02-23 |  | 0.5 | 2018-02-26 | Done
1621 | The Creek Church Phase II | E180221b | 2018-02-22 | Elevator Shop Drawings |  |  | billed |  | 2018-02-26 | 2018-02-23 |  | 1 | 2018-02-27 | Done
1583 | 7 City Church | E180508c | 2018-05-08 | Review complete model | Superseded | IFC Work | no |  |  | 2018-05-10 |  |  | 2018-06-25 | Done
1697 | Moss Insurance Office Addition | E180220e | 2018-02-22 | New Plan | See E180226a |  | no |  |  | 2018-02-23 |  |  | 2018-02-28 | Done
1689 | Jasco Security Gate | E180226b | 2018-02-26 | Preliminary sets |  |  | billed |  |  |  |  | 3 | 2018-02-26 | Done
1689 | Jasco Security Gate | E180223a | 2018-02-27 | 50% CD Set due | Follow up with Tim4/23 Superceded | JAMES'S INSTRUCTION | no |  | 2018-03-28 | 2018-03-30 |  |  | 2018-04-23 | Done
1689 | Jasco Security Gate | E180223a | 2018-02-27 | 95% CD set due | 4/23 Superceded | Tim's instructions | no |  | 2018-04-11 | 2018-04-11 |  |  | 2018-04-23 | Done
1689 | Jasco Security Gate | E180223a | 2018-02-27 | Issue for Bid | 4/23 Superceded |  | no |  | 2018-04-19 | 2018-04-23 |  |  | 2018-04-23 | Done
1614 | Euless Library |  | 2017-06-08 | Need under carpet specs from Jim |  | CD work | no | PWR |  |  |  |  | 2018-09-12 | Done
1614 | Euless Library | E180112e | 2018-01-14 | Add exterior wall-mtd fixture to schedule | 2/8 Got spec from Morrow 2/2 Need to add fixture definition to LFS 1/15 Jim will get into it after 7CC. Fp->1/26 1/14 Sent email to Jim Morrow requesting substitute for the triangular fixture | IFC Work | no |  |  | 2018-01-31 |  |  | 2018-09-04 | Done
1582 | Northern Hills Elementary Safe Room | E180223c | 2018-02-27 | 95% CD meeting notes |  |  | billed |  | 2018-03-08 | 2018-03-02 |  | 2 | 2018-03-05 | Done
1582 | Northern Hills Elementary Safe Room |  | 2018-02-27 | 100% CD due |  |  | billed |  | 2018-03-07 | 2018-03-06 |  | 3 | 2018-03-06 | Done
1676 | National Indoor RV Building | E180223d | 2018-02-27 | Review Morrow's calculations | Cancelled |  | billed |  |  | 2018-03-02 |  |  | 2018-03-06 | Done
1715 | Modern Acupuncture - Kingwood | E180226c | 2018-02-27 | IFR |  |  | billed |  |  | 2018-03-03 |  | 4 | 2018-03-04 | Done
1613 | Norman Hotel | E180226d | 2018-02-27 | Updated Revit model |  | Tim's instructions | billed |  |  | 2018-03-16 |  |  | 2018-04-29 | Done
1614 | Euless Library | E180226e | 2018-02-27 | Review LTG with Morrow |  |  | no |  |  | 2018-03-07 |  | 2 | 2018-03-06 | Done
1697 | Moss Insurance Office Addition | E180227a | 2018-02-27 | LTG to Tim |  |  | no |  |  |  |  | 0.5 | 2018-02-27 | Done
1530 | Brennan Drop-off Changes | E180227b | 2018-02-27 | IFC due | Superceded |  | billed |  | 2018-03-26 | 2018-03-25 |  |  | 2018-03-28 | Done
1531 | MLK Drop-off Changes | E180227b | 2018-02-27 | IFC due |  |  | billed |  | 2018-03-30 | 2018-03-29 |  |  | 2018-03-29 | Done
1532 | Old Hemphill Drop-off Changes | E180227b | 2018-02-27 | IFC due |  |  | billed |  | 2018-03-30 | 2018-03-29 |  |  | 2018-03-29 | Done
1676 | National Indoor RV Building | E180227c | 2018-02-27 | 50% CD due | Cancelled |  | billed |  | 2018-03-19 | 2018-03-16 |  |  | 2018-03-06 | Done
1676 | National Indoor RV Building | E180227c | 2018-02-27 | 90% CD due | Project cancelled |  | billed |  | 2018-04-06 | 2018-04-03 |  |  | 2018-03-29 | Done
1676 | National Indoor RV Building | E180227c | 2018-02-27 | IFC due | Project cancelled |  | billed |  | 2018-04-13 | 2018-04-10 |  |  | 2018-03-29 | Done
1670 | Brookhaven Generator | E180227d | 2018-02-27 | Review proposals |  |  | billed |  |  | 2018-02-28 |  | 2 | 2018-03-01 | Done
1707 | Ryan Schools | E180227e | 2018-02-27 | Set up project |  |  | billed | s |  | 2018-03-29 |  | 2 | 2018-04-03 | Done
1629 | Heritage Glenn MOB Shell | E180227f | 2018-02-27 | Set up project |  |  | billed |  |  | 2018-03-14 |  | 1 | 2018-03-15 | Done
1582 | Northern Hills Elementary Safe Room | E180227g | 2018-02-27 | Additional charging station |  | IFC work | billed |  |  |  |  | 0.5 | 2018-03-05 | Done
1692 | Celeris (2018) | C180227 | 2018-02-27 | Bosque Rev 3 |  |  | no |  |  |  |  | 0.5 | 2018-02-27 | Done
1629 | Heritage Glenn MOB Shell | E180227f | 2018-02-27 | Site has gas | No, it is all electric. P11-90 | IFC work | billed | [5 empty] | 2018-03-29 | Done
1676 | National Indoor RV Building | E180228a | 2018-02-28 | Running List | 2/28 Need clarification on items | Response | billed | [5 empty] | 2018-03-06 | Done
1697 | Moss Insurance Office Addition | E180220e | 2018-02-28 | Revision 2 |  |  | billed |  |  | 2018-02-28 |  | 2 | 2018-02-28 | Done
1614 | Euless Library | E180126f | 2018-01-28 | IT Layouts | Need to clarify with Jim | IFC Work | no | PWR |  | 2018-01-31 |  | 0.5 | 2018-09-12 | Done
1670 | Brookhaven Generator |  | 2018-03-01 | Review Set |  |  | billed |  |  |  |  | 8 | 2018-03-01 | Done
1692 | Celeris (2018) | C180301 | 2018-03-01 | Dallas CC Fault Current Calcs |  |  | billed |  |  | 2018-03-01 |  | 1 | 2018-03-01 | Done
1692 | Celeris (2018) | C180301 | 2018-03-01 | AA @ DFW Hangar # 5 DAS | Proposal |  | billed |  |  | 2018-03-01 |  | 0.5 | 2018-03-01 | Done
ops | Operations |  | 2018-03-01 | Clean up desk |  |  | billed |  |  | 2018-03-16 |  | 2 | 2018-03-17 | Done
ops | Operations |  | 2018-03-01 | 1120S |  |  | billed |  |  | 2018-03-14 |  | 3 | 2018-03-15 | Done
1582 | Northern Hills Elementary Safe Room | E180228c | 2018-03-01 | Two more changes |  | IFC work | billed |  |  |  |  | 0 | 2018-03-05 | Done
1317 | Joyce Dr PD Station | E180301b | 2018-03-01 | Service feeder informatiion for Rev 6 |  |  | no |  |  | 2018-03-02 |  | 0 | 2018-03-02 | Done
1416 | DCCCD Eastfield Generator | E180301c | 2018-03-01 | Review Final GFI test report |  |  | no |  |  | 2018-03-01 |  | 0.5 | 2018-03-01 | Done
1672 | FBC Watauga - Phase 1 | E180301d | 2018-03-01 | Set up project | Superceded |  | no |  |  | 2018-03-16 |  |  | 2018-03-14 | Done
1614 | Euless Library |  | 2018-03-01 | Print set for markup and AIs |  |  | no |  |  | 2018-03-02 |  |  | 2018-03-06 | Done
1692 | Celeris (2018) | C180301 | 2018-03-01 | ATC Fort Worth Comments |  |  | no |  |  | 2018-03-01 |  | 0.5 | 2018-03-01 | Done
1692 | Celeris (2018) | C180301 | 2018-03-01 | Seguin Rev 2 |  |  | no |  |  |  |  | 0.5 | 2018-03-01 | Done
1692 | Celeris (2018) | C180302 | 2018-03-02 | Dallas CC Rev 1 |  |  | billed |  |  |  |  | 0.5 | 2018-03-02 | Done
1631 | Brown Street Church Addition | E180302a | 2018-03-02 | LTG controls email review |  |  | billed |  |  |  |  | 0.5 | 2018-03-02 | Done
1670 | Brookhaven Generator | E180302b | 2018-03-02 | Prepare ASA01 proposal |  |  | no |  |  |  |  | 0.5 | 2018-03-02 | Done
1317 | Joyce Dr PD Station | E180301b | 2018-03-01 | Revision 6 |  |  | billed |  |  | 2018-03-02 |  | 1 | 2018-03-02 | Done
1583 | 7 City Church | E180223b | 2018-03-03 | Completed 80% MEP comments |  |  | billed |  |  |  |  | 4 | 2018-03-03 | Done
1421 | KXAS Remodel | E180311a | 2018-03-15 | Revision 6 | Confirmed |  | no | A | 2018-03-19 | 2018-03-16 |  | 0.5 | 2018-03-19 | Done
1614 | Euless Library |  | 2018-02-28 | Feb IFC work |  |  | billed | [5 empty] | 2018-02-28 | Done
1715 | Modern Acupuncture - Kingwood |  | 2018-03-04 | Need to clarify reqs |  |  | billed |  |  | 2018-03-04 |  |  | 2018-03-06 | Done
1614 | Euless Library | E180305a | 2018-03-05 | Morrow's materials |  |  | no |  |  | 2018-03-07 |  |  | 2018-03-07 | Done
1614 | Euless Library |  | 2018-02-01 | Verify that all LTG is replaced |  | Coord Meeting | no | [5 empty] | 2018-09-04 | Done
1614 | Euless Library |  | 2018-03-07 | LFS | Same as E180216d |  | no |  |  | 2018-03-07 | 1.5 | 1.5 | 2018-03-07 | Done
1614 | Euless Library |  | 2018-03-07 | Floor Plans |  |  | no |  |  | 2018-03-07 | 1.5 | 2 | 2018-03-07 | Done
1614 | Euless Library |  | 2018-02-01 | check what parking lot LTG to add |  | Coord Meeting | no | [5 empty] | 2018-09-04 | Done
1614 | Euless Library |  | 2018-03-07 | COMCheck |  |  | no |  |  | 2018-03-07 | 2 | 2 | 2018-03-07 | Done
1614 | Euless Library |  | 2018-03-07 | Egress / Emergency LTG |  |  | no |  |  | 2018-03-07 | 2 | 1 | 2018-03-09 | Done
1696 | EPIROC Headquarters | E180307a | 2018-03-07 | Site Visit | @10 AM |  | billed |  | 2018-03-14 | 2018-03-14 | 3 | 3 | 2018-03-14 | Done
1629 | Heritage Glenn MOB Shell | E180227f | 2018-03-07 | Progress Set Due |  |  | billed |  | 2018-03-16 | 2018-03-15 |  | 2 | 2018-03-15 | Done
1629 | Heritage Glenn MOB Shell | E180227f | 2018-03-07 | 95% CD |  |  | billed |  | 2018-03-23 | 2018-03-22 |  |  | 2018-03-22 | Done
1629 | Heritage Glenn MOB Shell | E180227f | 2018-03-07 | 100% CD IFR | Changed into IFR |  | billed |  | 2018-03-30 | 2018-03-29 |  |  | 2018-03-30 | Done
1614 | Euless Library |  | 2018-02-01 | Add spots for glass statue |  | Coord Meeting | no | [5 empty] | 2018-09-04 | Done
1614 | Euless Library |  |  | ckt Power |  |  | no |  |  | 2018-03-08 |  | 3 | 2018-03-09 | Done
1614 | Euless Library |  |  | Equipment |  |  | no |  |  | 2018-03-08 |  | 3 | 2018-03-09 | Done
1614 | Euless Library |  |  | One line |  |  | no |  |  | 2018-03-08 |  | 3 | 2018-03-09 | Done
1614 | Euless Library | E180308a | 2018-03-08 | Access Cards |  |  | no |  |  | 2018-03-08 |  | 0.5 | 2018-03-08 | Done
1672 | FBC Watauga - Phase 1 | E180301d | 2018-03-01 | 100% CD review set | Need new date |  | no |  | 2018-03-30 | 2018-03-30 |  | 6 | 2018-03-30 | Done
1672 | FBC Watauga - Phase 1 | E180301d | 2018-03-01 | IFC |  |  | billed | 4 | 2018-04-05 | 2018-04-05 |  | 2 | 2018-04-05 | Done
1692 | Celeris (2018) | c180314 | 2018-03-14 | Dallas CC Rev 1 |  |  | no |  |  | 2018-03-14 |  | 0.5 | 2018-03-14 | Done
1421 | KXAS Remodel | E180327b | 2018-03-27 | Punch List visit | Monday time. Not needed |  | no | [5 empty] | 2018-04-02 | Done
1317 | Joyce Dr PD Station | E180312a | 2018-03-14 | Device markups. | This is Rfi 046 |  | no |  |  | 2018-03-14 |  |  | 2018-03-14 | Done
1416 | DCCCD Eastfield Generator | E180312b | 2018-03-14 | Check change order | Need to download materials. |  | no |  |  | 2018-03-15 |  | 0.5 | 2018-03-16 | Done
1317 | Joyce Dr PD Station | E180312c | 2018-03-14 | RFI 06 |  |  | billed |  |  | 2018-03-14 |  | 1 | 2018-03-14 | Done
1317 | Joyce Dr PD Station | E180312d | 2018-03-14 | Justify resubmittal of gear for add. Services |  |  | no |  |  | 2018-03-15 |  | 0.5 | 2018-03-16 | Done
1582 | Northern Hills Elementary Safe Room | E180314a | 2018-03-14 | Substitution Request |  |  | billed |  |  | 2018-03-14 |  | 0.5 | 2018-03-14 | Done
1621 | The Creek Church Phase II | E180314b | 2018-03-14 | Rfi 05 |  |  | billed |  |  | 2018-03-14 |  | 0.5 | 2018-03-14 | Done
1672 | FBC Watauga - Phase 1 | E180313a | 2018-03-14 | Updated Revit model |  |  | billed |  |  | 2018-03-16 |  | 2 | 2018-03-20 | Done
1632 | Upper Trinity Conservation | E180313b | 2018-03-14 | Punch List sv | @10 AM |  | billed |  | 2018-03-15 | 2018-03-15 | 3 | 3 | 2018-03-15 | Done
1629 | Heritage Glenn MOB Shell | E180313c | 2018-03-14 | Updated Revit model |  |  | billed |  |  | 2018-03-14 |  | 0.5 | 2018-03-15 | Done
1717 | Greenbriar CC Reception Desk | E180313d | 2018-03-14 | Proposal |  |  | no |  |  | 2018-03-15 |  | 0.5 | 2018-03-15 | Done
1317 | Joyce Dr PD Station | E180306b | 2018-03-14 | Floor box submittal |  |  | billed |  |  | 2018-03-14 |  | 0.5 | 2018-03-14 | Done
1632 | Upper Trinity Conservation |  | 2018-03-15 | Punch list Report |  |  | no |  |  | 2018-03-15 |  | 1 | 2018-03-16 | Done
1538 | UNT Coliseum Concourse | E180312e | 2018-03-15 | SV Report |  |  | billed |  |  | 2018-03-15 |  | 2 | 2018-03-16 | Done
1421 | KXAS Remodel | E180328c | 2018-03-28 | Punch List Site Visit for Phase 1 | Not needed |  | no |  |  | 2018-04-02 |  |  | 2018-04-02 | Done
1614 | Euless Library |  | 2018-02-01 | Add E/M generator connection |  | IFC Work | no | PWR |  |  |  |  | 2018-09-10 | Done
1629 | Heritage Glenn MOB Shell | E180315b | 2018-03-15 | Coordinate transformer location |  |  | billed |  |  | 2018-03-29 |  | 2 | 2018-03-29 | Done
1621 | The Creek Church Phase II | E180309a | 2018-03-15 | LTG fixture substitutions |  |  | billed |  |  |  |  | 1 | 2018-03-15 | Done
1538 | UNT Coliseum Concourse |  | 2018-03-16 | Modify SV report. Eliminate lightning design |  |  | billed | A | 2018-03-19 | 2018-03-19 |  | 0.5 | 2018-03-19 | Done
1620 | City of Weatherford Service Center | E180319a | 2018-03-19 | Reduced scope | 3/19 Addendum A dated 3/21/18 3/19 Need to talk to Tim |  | no |  | 2018-03-20 | 2018-03-19 |  | 1 | 2018-03-20 | Done
1614 | Euless Library |  | 2018-02-01 | Fire Alarm (not proprietary) with audible voice system. |  | Coord Meeting | no | PWR |  |  |  |  | 2018-09-11 | Done
1711 | Funky Town Donut Shop | E180315c | 2018-03-19 | Set up project |  |  | No |  |  | 2018-03-29 |  | 4 | 2018-04-03 | Done
1614 | Euless Library | E180208j | 2018-02-08 | Glass sculpture lighting | 2/8 Morrow sent email | IFC work | no |  |  | 2018-02-16 |  |  | 2018-09-04 | Done
1614 | Euless Library | E180213f | 2018-02-14 | LTG Markups |  | IFC Work | no | [5 empty] | 2018-09-04 | Done
1614 | Euless Library | E180213f | 2018-02-14 | IT PWR Markups |  |  | no | Add 02 |  |  |  |  | 2018-10-04 | Done
1629 | Heritage Glenn MOB Shell | E180315b | 2018-03-19 | Locate pad mounted transformer |  | IFC Work | billed |  |  |  |  | 1 | 2018-03-29 | Done
1538 | UNT Coliseum Concourse | E180316a | 2018-03-19 | Addition Punch List SV | Visit and Report |  | billed |  | 2018-03-20 | 2018-03-20 |  | 5 | 2018-03-20 | Done
1631 | Brown Street Church Addition | E180319a | 2018-03-19 | LTG Controls Submittal |  |  | billed |  |  |  |  | 1 | 2018-03-19 | Done
1538 | UNT Coliseum Concourse | E180320e | 2018-03-20 | Lightning Report |  |  | billed |  |  | 2018-03-20 |  | 2 | 2018-03-20 | Done
1704 | Knights Inn Willow Park | E180320a | 2018-03-20 | Set up project |  | IFC Work | no |  |  | 2018-03-29 |  | 2 | 2018-04-29 | Done
1613 | Norman Hotel | E180320b | 2018-03-20 | Include bar information |  | IFC Work | billed | [5 empty] | 2018-04-29 | Done
1530 | Brennan Drop-off Changes | E180315d | 2018-03-20 | Incorporate easement comments | Nothing to add |  | no |  |  | 2018-03-23 |  | 0.5 | 2018-03-28 | Done
1531 | MLK Drop-off Changes | E180315d | 2018-03-20 | Incorporate easement comments |  |  | no |  |  | 2018-03-23 |  |  | 2018-03-28 | Done
1532 | Old Hemphill Drop-off Changes | E180315d | 2018-03-20 | Incorporate easement comments |  |  | no |  |  | 2018-03-23 |  |  | 2018-03-28 | Done
1530 | Brennan Drop-off Changes | E180319b | 2018-03-20 | Incorporate Debbie's comments |  |  | no |  |  | 2018-03-23 |  | 1 | 2018-03-28 | Done
1416 | DCCCD Eastfield Generator | E180320c | 2018-03-20 | Review As-builts and generate record set |  |  | billed | 6 |  | 2018-04-17 |  | 2 | 2018-04-18 | Done
1416 | DCCCD Eastfield Generator | E180320c | 2018-03-20 | Review photos for final acceptance |  |  | no |  |  | 2018-03-21 |  | 1 | 2018-03-22 | Done
1317 | Joyce Dr PD Station | E180320d | 2018-03-20 | CR floor receptacle submittal |  |  | no |  |  | 2018-03-20 |  | 0.5 | 2018-03-22 | Done
1692 | Celeris (2018) | C180320 | 2018-03-20 | Texas Tech Analysis | p11-86 |  | billed |  |  | 2018-03-20 |  | 1 | 2018-03-21 | Done
1711 | Funky Town Donut Shop |  | 2018-03-21 | Site Visit |  |  | No |  |  | 2018-03-21 | 3 | 3 | 2018-03-21 | Done
1711 | Funky Town Donut Shop |  | 2018-03-21 | Load Analysis |  |  | No |  |  | 2018-03-29 |  | 3 | 2018-04-03 | Done
1672 | FBC Watauga - Phase 1 |  | 2018-03-21 | Review set |  |  | No |  |  | 2018-03-30 |  | 6 | 2018-03-30 | Done
1718 | Cantilivered Restaurant | E180321a | 2018-03-22 | Proposal |  |  | billed |  |  |  |  | 0.5 | 2018-03-22 | Done
1719 | Grand Prairie Warehouse Additions | E180321b | 2018-03-22 | Proposal |  |  | billed |  |  |  |  | 0.5 | 2018-03-22 | Done
1696 | EPIROC Headquarters | E180321c | 2018-03-22 | Update revit file | Superceeded |  | no |  |  | 2018-04-05 |  |  | 2018-03-28 | Done
1692 | Celeris (2018) | C180320 | 2018-03-22 | Texas Tech Analysis | p11-88 |  | billed |  |  | 2018-03-21 |  |  | 2018-03-21 | Done
1621 | The Creek Church Phase II | E180322a | 2018-03-23 | LTG Controls Submittal |  |  | billed |  |  | 2018-03-23 |  | 0.5 | 2018-03-29 | Done
1704 | Knights Inn Willow Park | E180322a | 2018-03-23 | Appliance information |  | IFC Work | no |  |  |  |  | 1 | 2018-04-29 | Done
1711 | Funky Town Donut Shop | E180315c | 2018-03-23 | Review answers to questions |  |  | No |  |  | 2018-03-29 |  | 3 | 2018-04-03 | Done
1629 | Heritage Glenn MOB Shell | E180322b | 2018-03-23 | Review comments |  |  | billed |  |  | 2018-03-29 |  | 1 | 2018-03-29 | Done
1535 | Cornerstone Baptist Church | E180323a | 2018-03-23 | Lumens per watt??? | 3/23 Eric called Kids area is fixed. Still arguing about the café. 3/23 Left message to Eric |  | billed |  |  |  |  | 0.5 | 2018-03-23 | Done
1672 | FBC Watauga - Phase 1 | E180323b | 2018-03-27 | Demolition notes |  | IFC Work | billed | [5 empty] | 2018-03-30 | Done
1614 | Euless Library | E180222a | 2018-02-22 | Answers to questions |  | IFC Work | no | PWR |  |  |  |  | 2018-09-12 | Done
1530 | Brennan Drop-off Changes | E180319b | 2018-03-27 | IFC deadline | Dated 3/30 |  | no |  | 2018-03-29 | 2018-03-27 |  |  | 2018-03-29 | Done
1582 | Northern Hills Elementary Safe Room | E180326a | 2018-03-27 | Substitution Request |  |  | billed |  |  | 2018-03-27 |  | 0.5 | 2018-03-27 | Done
1629 | Heritage Glenn MOB Shell | E180326b | 2018-03-27 | Verify Type SA fixture |  | IFC Work | billed | [5 empty] | 2018-03-29 | Done
1672 | FBC Watauga - Phase 1 | E180326c | 2018-03-27 | Remove sign |  |  | billed |  |  |  |  | 0.5 | 2018-03-27 | Done
1530 | Brennan Drop-off Changes | E180326e | 2018-03-27 | Naming Corrections |  |  | no |  |  | 2018-03-27 |  | 1 | 2018-03-28 | Done
1531 | MLK Drop-off Changes | E180326e | 2018-03-27 | Naming Corrections |  |  | no |  |  | 2018-03-27 |  | 0.5 | 2018-03-28 | Done
1532 | Old Hemphill Drop-off Changes | E180326e | 2018-03-27 | Naming Corrections |  |  | no |  |  | 2018-03-27 |  | 0.5 | 2018-03-28 | Done
1530 | Brennan Drop-off Changes | E180326e | 2018-03-27 | Update border |  |  | no |  |  | 2018-03-27 |  |  | 2018-03-28 | Done
1531 | MLK Drop-off Changes | E180326e | 2018-03-27 | Update border |  |  | no |  |  | 2018-03-27 |  | 0.5 | 2018-03-28 | Done
1532 | Old Hemphill Drop-off Changes | E180326e | 2018-03-27 | Update border |  |  | no |  |  | 2018-03-27 |  | 0.5 | 2018-03-28 | Done
1530 | Brennan Drop-off Changes | E180326e | 2018-03-27 | Update specs |  |  | no |  |  | 2018-03-27 |  |  | 2018-03-28 | Done
1629 | Heritage Glenn MOB Shell | E180326f | 2018-03-27 | Revit update |  | IFC Work | billed |  |  |  |  | 0.5 | 2018-03-29 | Done
1720 | GAF Renovations | E180326g | 2018-03-27 | Proposal |  |  | billed |  |  | 2018-03-27 |  | 0.5 | 2018-03-27 | Done
1538 | UNT Coliseum Concourse | E180327a | 2018-03-27 | Lightning Protection Meeting |  |  | no |  | 2018-04-03 | 2018-04-03 | 3 | 2 | 2018-04-03 | Done
1421 | KXAS Remodel | E180402d | 2018-04-04 | Rev 7 Proposal |  |  | no | 3 |  | 2018-04-04 |  | 0.5 | 2018-04-04 | Done
1704 | Knights Inn Willow Park | E180327c | 2018-03-27 | Site Visit |  |  | billed |  | 2018-03-27 | 2018-03-27 | 2 | 3 | 2018-03-27 | Done
1613 | Norman Hotel |  | 2018-03-27 | Issue for Review |  |  | billed |  | 2018-04-10 | 2018-04-05 |  | 20 | 2018-04-09 | Done
1416 | DCCCD Eastfield Generator | E180327d | 2018-03-27 | Sign Change Order 2 |  |  | no |  |  | 2018-03-27 |  | 0.5 | 2018-03-27 | Done
1416 | DCCCD Eastfield Generator | E180327e | 2018-03-27 | Payment Request |  |  | no |  |  | 2018-03-27 |  |  | 2018-03-27 | Done
1707 | Ryan Schools | E180327f | 2018-03-27 | Update base files |  |  | billed |  |  | 2018-03-29 |  |  | 2018-04-03 | Done
1531 | MLK Drop-off Changes | E180328a | 2018-03-28 | Update cost estimate | Not needed |  | no |  |  | 2018-03-29 |  |  | 2018-04-02 | Done
1532 | Old Hemphill Drop-off Changes | E180328a | 2018-03-28 | Update cost estimate | Not needed |  | no |  |  | 2018-03-29 |  |  | 2018-04-02 | Done
1530 | Brennan Drop-off Changes | E180328a | 2018-03-28 | Update cost estimate | Not needed |  | no |  |  | 2018-03-29 |  |  | 2018-04-02 | Done
1721 | Granite Schools | E180328b | 2018-03-28 | Granite Meeting |  |  | no | 5 | 2018-04-11 | 2018-04-10 |  | 6 | 2018-04-11 | Done
1421 | KXAS Remodel | E180409b | 2018-04-14 | Effort to complete |  |  | no |  |  | 2018-04-14 |  | 1 | 2018-04-16 | Done
1711 | Funky Town Donut Shop | E180328d | 2018-03-28 | Ventless Dishwasher | Seems to be a sample not actual equipment | IFC Work | billed | [5 empty] | 2018-03-29 | Done
1631 | Brown Street Church Addition | E180328e | 2018-03-28 | EM lights in classrooms |  |  | billed |  |  |  |  | 0.5 | 2018-03-28 | Done
1629 | Heritage Glenn MOB Shell | E180328f | 2018-03-28 | Review Comments |  | IFC work | billed | [5 empty] | 2018-03-29 | Done
1530 | Brennan Drop-off Changes | E180328a | 2018-03-28 | New Border |  |  | no |  |  | 2018-03-28 |  |  | 2018-03-28 | Done
1531 | MLK Drop-off Changes | E180328a | 2018-03-28 | New Border |  |  | no |  |  | 2018-03-28 |  |  | 2018-03-28 | Done
1532 | Old Hemphill Drop-off Changes | E180328a | 2018-03-28 | New Border |  |  | no |  |  | 2018-03-28 |  |  | 2018-03-28 | Done
1711 | Funky Town Donut Shop | E180328g | 2018-03-28 | Latest Equipment information plus base file |  |  | No |  |  | 2018-03-29 |  | 2 | 2018-04-03 | Done
1696 | EPIROC Headquarters | E180328h | 2018-03-28 | Updated Revit model | Superceded by E180330a |  | billed |  |  | 2018-04-05 |  |  | 2018-04-10 | Done
1530 | Brennan Drop-off Changes | E180328j | 2018-03-28 | Update HVAC equip parameters |  |  | no |  |  | 2018-03-28 |  | 1 | 2018-03-29 | Done
1531 | MLK Drop-off Changes | E180328j | 2018-03-28 | Update HVAC equip parameters |  |  | no |  |  | 2018-03-28 |  | 1 | 2018-03-29 | Done
1532 | Old Hemphill Drop-off Changes | E180328j | 2018-03-28 | Update HVAC equip parameters |  |  | no |  |  | 2018-03-28 |  | 1 | 2018-03-29 | Done
1613 | Norman Hotel |  | 2018-03-29 | Set up project |  |  | billed |  |  | 2018-04-05 |  | 4 | 2018-04-06 | Done
1614 | Euless Library |  | 2018-03-07 | Schematics |  | FINAL IFC | no | LTG |  | 2018-03-07 | 2 |  | 2018-09-12 | Done
1614 | Euless Library | E180315a | 2018-03-15 | Review photometrics and verify Type BB and CC are independently dimmed |  | IFC Work | no | [5 empty] | 2018-09-04 | Done
1614 | Euless Library |  | 2018-03-31 | Coordinate exact location of W and D |  | IFC Work | no | PWR |  |  |  |  | 2018-09-10 | Done
1614 | Euless Library |  | 2018-03-31 | Verify space for MTS-1 |  | IFC Work | no | PWR |  |  |  |  | 2018-09-10 | Done
1614 | Euless Library |  | 2018-03-31 | Coordinate main stack LTG conrols |  | IFC Work | no | [5 empty] | 2018-09-04 | Done
1614 | Euless Library |  | 2018-03-31 | LTG Controls |  | IFC Work | no | LTG |  |  |  |  | 2018-09-12 | Done
1704 | Knights Inn Willow Park | E180402a | 2018-04-02 | Update Revit File |  | IFC Work | no |  |  | 2018-04-03 |  | 0 | 2018-04-30 | Done
1704 | Knights Inn Willow Park | E180402b | 2018-04-02 | Review As-builts |  | IFC Work | no |  |  | 2018-04-03 |  | 0 | 2018-04-30 | Done
1696 | EPIROC Headquarters | E180330a | 2018-04-02 | Update Revit File |  |  | billed | 4 |  | 2018-04-10 |  | 2 | 2018-04-12 | Done
1614 | Euless Library |  | 2018-03-31 | Schematics |  | IFC Work | no | LTG |  |  |  |  | 2018-09-12 | Done
1621 | The Creek Church Phase II | p11-95 | 2018-04-23 | Rev 6: Change RTU-1 to MCA 57 and MOCP 70 |  | Next Revision | no | [5 empty] | 2018-05-11 | Done
1711 | Funky Town Donut Shop | E180403a | 2018-04-03 | Walk in spec |  |  | No |  |  | 2018-04-03 |  | 0.5 | 2018-04-03 | Done
1692 | Celeris (2018) | C180403 | 2018-04-03 | Spring Valley/Marsh (temp relo) |  |  | no |  |  |  |  | 0.5 | 2018-04-03 | Done
1477 | Eugene McCray Recreation Center | E180402c | 2018-04-02 | Mod 03 Parking lot changes |  |  | billed | 1 | 2018-04-11 | 2018-04-10 |  | 1.5 | 2018-04-10 | Done
1478 | Handley Meadowbrook Rec Center | E180402c | 2018-04-02 | Mod 03 Parking lot changes |  |  | billed | 2 | 2018-04-11 | 2018-04-10 |  | 1.5 | 2018-04-10 | Done
1629 | Heritage Glenn MOB Shell |  | 2018-03-29 | IFC | Superceded | Final date | no | [5 empty] | 2018-05-23 | Done
1421 | KXAS Remodel | E180430b | 2018-04-30 | Phase 2, 3 abatement meeting |  |  | no |  | 2018-05-02 | 2018-05-02 | 3 | 4 | 2018-05-02 | Done
1707 | Ryan Schools | E180402d | 2018-04-04 | Site Plan | No scope here |  | billed |  |  | 2018-04-04 |  |  | 2018-04-04 | Done
1717 | Greenbriar CC Reception Desk | E180403b | 2018-04-04 | Site Visit | @1:30 PM |  | no |  |  | 2018-04-09 |  | 2 | 2018-04-09 | Done
1317 | Joyce Dr PD Station | E180403c | 2018-04-04 | RCO 018 |  |  | no |  |  | 2018-04-04 |  | 0.5 | 2018-04-04 | Done
1621 | The Creek Church Phase II | E180403d | 2018-04-04 | LTG and PWR submittals |  |  | no | 7 |  | 2018-04-04 |  | 1.5 | 2018-04-05 | Done
1724 | TDC Parking Phase 1 | E180403e | 2018-04-04 | Proposal |  |  | no | 2 |  | 2018-04-04 |  | 0.5 | 2018-04-04 | Done
1538 | UNT Coliseum Concourse | E180403f | 2018-04-04 | Received punch list report. | Filed under 180320 SV |  | no | [5 empty] | 2018-04-04 | Done
1629 | Heritage Glenn MOB Shell | E180328f | 2018-04-02 | IFC Due | Superceded | Tim's instructions | no |  | 2018-04-13 | 2018-04-12 |  |  | 2018-05-23 | Done
1672 | FBC Watauga - Phase 1 | E180326d | 2018-04-04 | Specs |  |  | no | 4 |  | 2018-04-04 |  | 2 | 2018-04-05 | Done
1704 | Knights Inn Willow Park |  | 2018-04-04 | Need deadline |  |  | no |  | 2018-04-30 | 2018-04-06 |  |  | 2018-04-30 | Done
1672 | FBC Watauga - Phase 1 | E180326d | 2018-04-04 | Comments |  |  | no | 4 |  | 2018-04-04 |  | 3 | 2018-04-05 | Done
1711 | Funky Town Donut Shop |  | 2018-04-04 | Send track head sample |  |  | No | 1 |  | 2018-04-04 |  | 0.5 | 2018-04-04 | Done
1707 | Ryan Schools |  | 2018-04-04 | DD set |  |  | billed | 5 | 2018-04-04 | 2018-04-04 |  | 3 | 2018-04-04 | Done
1629 | Heritage Glenn MOB Shell |  | 2018-04-02 | Spec book | Superceded | IFC Work | no | [5 empty] | 2018-05-23 | Done
1711 | Funky Town Donut Shop |  | 2018-04-05 | IFC |  |  | billed |  | 2018-04-06 | 2018-04-05 |  | 2 | 2018-04-05 | Done
1317 | Joyce Dr PD Station | E180405a | 2018-04-05 | LCP Submittal |  |  | billed |  |  | 2018-04-05 |  | 0.5 | 2018-04-05 | Done
1538 | UNT Coliseum Concourse | E180406a | 2018-04-06 | RFI 93 |  |  | no |  |  | 2018-04-06 |  | 0.5 | 2018-04-06 | Done
1613 | Norman Hotel | E180406b | 2018-04-07 | Fire Place |  |  | no |  |  | 2018-04-07 |  | 1 | 2018-04-09 | Done
1725 | Camacho UPV Office | E180409a | 2018-04-09 | Proposal |  |  | no |  |  |  |  | 0.5 | 2018-04-09 | Done
1621 | The Creek Church Phase II | E180410a | 2018-04-10 | M fixture mounting height |  |  | no |  |  |  |  | 0.5 | 2018-04-10 | Done
1538 | UNT Coliseum Concourse | E180406a | 2018-04-06 | OS Clarification |  |  | no |  |  | 2018-04-06 |  | 0.5 | 2018-04-10 | Done
1583 | 7 City Church |  | 2018-04-10 | Narrative for Phase 1 |  |  | no | 3 |  | 2018-04-10 |  | 2 | 2018-04-12 | Done
1692 | Celeris (2018) |  | 2018-04-11 | DX4753 rev 1 |  |  | no |  |  |  |  | 0.5 | 2018-04-11 | Done
1692 | Celeris (2018) |  | 2018-04-11 | Pleasanton |  |  | no |  |  |  |  | 0.5 | 2018-04-11 | Done
1692 | Celeris (2018) |  | 2018-04-11 | Anahuac |  |  | no |  |  |  |  | 0.5 | 2018-04-11 | Done
1613 | Norman Hotel | E180412a | 2018-04-12 | Go to Meeting |  |  | no |  |  | 2018-04-12 |  | 1 | 2018-04-12 | Done
1692 | Celeris (2018) | C180412 | 2018-04-12 | Light Farms WT |  |  | no |  |  |  |  | 0.5 | 2018-04-12 | Done
ops | Operations |  | 2018-04-13 | Prepare Record book # 12 |  |  | no |  |  | 2018-04-30 |  |  | 2018-05-11 | Done
1613 | Norman Hotel | E180406b | 2018-04-14 | Delta Design Guidelines |  |  | no | [5 empty] | 2018-04-10 | Done
1421 | KXAS Remodel | E180507e | 2018-05-08 | Review Lab scope of work | Superceded. Waiting for Scott on receptacles | Receptacle layouts | no | [5 empty] | 2018-10-29 | Done
1721 | Granite Schools | E180410b | 2018-04-14 | Project files |  |  | no |  |  | 2018-04-23 |  |  | 2018-04-23 | Done
1716 | Humane Society Animal Shelter | E180416c | 2018-04-14 | Civil Progress Set | See email for additional info |  | no |  |  | 2018-04-24 |  |  | 2018-04-30 | Done
1689 | Jasco Security Gate | E180410d | 2018-04-14 | 95% CD Review Set due | 4/23 Superceded |  | no |  | 2018-04-27 | 2018-04-23 |  |  | 2018-04-23 | Done
1689 | Jasco Security Gate | E180410d | 2018-04-14 | IFC due | Superceded |  | no |  | 2018-05-03 | 2018-04-23 |  |  | 2018-04-23 | Done
1629 | Heritage Glenn MOB Shell | E180328f | 2018-04-04 | Specs | Superceded | Tim's instructions | no |  |  | 2018-04-12 |  |  | 2018-05-23 | Done
1629 | Heritage Glenn MOB Shell | E180514c | 2018-05-17 | Updated site plan | Waiting for comments |  | no |  |  | 2018-05-23 |  | 1 | 2018-05-23 | Done
1538 | UNT Coliseum Concourse | E180410g | 2018-04-14 | South RR punch list |  |  | no |  |  | 2018-04-13 |  | 3 | 2018-04-13 | Done
1538 | UNT Coliseum Concourse | E180410g | 2018-04-14 | South RR punch list report | No punch list, yet |  | no |  |  | 2018-04-16 |  | 2 | 2018-04-16 | Done
1696 | EPIROC Headquarters | E180411a | 2018-04-14 | Review new DWG files |  |  | billed |  |  |  |  | 2 | 2018-04-12 | Done
1696 | EPIROC Headquarters | E180411a | 2018-04-14 | Specifications | In drawings |  | billed |  |  |  |  | 2 | 2018-04-12 | Done
1725 | Camacho UPV Office | E180412b | 2018-04-14 | Review photos |  |  | billed |  |  | 2018-04-23 |  | 0.5 | 2018-04-22 | Done
1696 | EPIROC Headquarters | E180412c | 2018-04-14 | Fixture selection email |  |  | billed |  |  |  |  | 1 | 2018-04-12 | Done
1613 | Norman Hotel | E180412d | 2018-04-14 | Architect's markups |  |  | no |  |  |  |  | 2 | 2018-04-17 | Done
1613 | Norman Hotel | E180412e | 2018-04-14 | Interior Designer Progress Set |  |  | no |  |  |  |  | 3 | 2018-04-17 | Done
1721 | Granite Schools | E180412f | 2018-04-14 | Owner requirements |  |  | no |  |  | 2018-04-23 |  | 1 | 2018-05-09 | Done
1696 | EPIROC Headquarters | E180412g | 2018-04-14 | M Sheets |  |  | billed |  |  |  |  | 1 | 2018-04-12 | Done
1613 | Norman Hotel | E180412h | 2018-04-14 | Update Revit model |  |  | no |  |  |  |  | 1 | 2018-04-17 | Done
1613 | Norman Hotel | E180413a | 2018-04-14 | EF in restroom stays as is. |  |  | no |  |  |  |  | 0.5 | 2018-04-17 | Done
1613 | Norman Hotel | E180413b | 2018-04-14 | Pantry DWG file |  |  | no |  |  |  |  | 1 | 2018-04-17 | Done
1721 | Granite Schools |  | 2018-04-16 | Review Set |  |  | no |  | 2018-04-24 | 2018-04-23 |  | 10 | 2018-04-26 | Done
1725 | Camacho UPV Office |  | 2018-04-16 | Site Visit |  |  | billed |  |  | 2018-04-18 |  | 1.5 | 2018-04-18 | Done
1696 | EPIROC Headquarters | E180411a | 2018-04-16 | COMCheck | In drawings |  | billed |  | 2018-04-25 | 2018-04-23 |  | 1 | 2018-04-25 | Done
1613 | Norman Hotel | E180417a | 2018-04-17 | M Sheets |  |  | no |  |  |  |  | 1 | 2018-04-17 | Done
1416 | DCCCD Eastfield Generator | E180417b | 2018-04-17 | Completion Letter |  |  | billed | [5 empty] | 2018-04-17 | Done
1613 | Norman Hotel | E180417c | 2018-04-17 | Specifications |  |  | no |  |  |  |  | 2 | 2018-04-18 | Done
1613 | Norman Hotel |  | 2018-04-17 | IFC |  |  | billed |  |  |  |  | 2 | 2018-04-18 | Done
1708 | Velma Schools | E180416c | 2018-04-18 | LTG Submittal | 4/26 Reviewed second submittal. 4/18 Sent email to Tom |  | no |  | 2018-04-23 | 2018-04-23 |  | 0.5 | 2018-04-26 | Done
1317 | Joyce Dr PD Station | E180418a | 2018-04-18 | Revise COMCheck |  |  | no |  |  |  |  | 0.5 | 2018-04-18 | Done
1727 | Moss Public Schools | E180418b | 2018-04-18 | Proposal |  |  | no |  |  |  |  | 0.5 | 2018-04-18 | Done
1317 | Joyce Dr PD Station | E180418d | 2018-04-18 | RFI 50 |  |  | no |  |  |  |  | 0.5 | 2018-04-18 | Done
1725 | Camacho UPV Office |  | 2018-04-21 | Set up project |  |  | billed |  |  |  |  | 3 | 2018-04-21 | Done
1725 | Camacho UPV Office |  | 2018-04-21 | LTG |  |  | billed |  |  |  |  | 1 | 2018-04-22 | Done
1725 | Camacho UPV Office |  | 2018-04-21 | PWR |  |  | billed |  |  |  |  | 1 | 2018-04-22 | Done
1725 | Camacho UPV Office |  | 2018-04-21 | Review Set |  |  | billed |  | 2018-04-23 | 2018-04-23 |  | 2 | 2018-04-23 | Done
1721 | Granite Schools | E180418e | 2018-04-23 | Talk to Lev about Auditorium lights |  |  | no |  | 2018-04-23 | 2018-04-23 |  |  | 2018-04-24 | Done
1631 | Brown Street Church Addition | E180124a | 2018-01-24 | AV Change impact | 1/24 Called Eric. | Eric's call | no | [5 empty] | 2018-07-22 | Done
1631 | Brown Street Church Addition | E180125a | 2018-01-25 | More AV changes. | 1/25 Sent proposal to Eric | Eric's approval | no | [5 empty] | 2018-07-22 | Done
1704 | Knights Inn Willow Park | E180419b | 2018-04-23 | Update Revit file |  |  | no |  |  | 2018-04-25 |  | 0 | 2018-04-29 | Done
1717 | Greenbriar CC Reception Desk | E180424a | 2018-04-23 | IFR due |  |  | no |  | 2018-04-24 | 2018-04-23 |  | 3 | 2018-04-24 | Done
1317 | Joyce Dr PD Station | E180419c | 2018-04-23 | RCO 023 024 |  |  | no |  | 2018-04-23 | 2018-04-23 |  | 0.5 | 2018-04-23 | Done
1689 | Jasco Security Gate | E180420a | 2018-04-23 | 25% CD due |  |  | no |  | 2018-05-01 | 2018-04-25 |  | 3 | 2018-05-14 | Done
1631 | Brown Street Church Addition | E180504b | 2018-05-07 | Punch List Walk Through |  |  | no |  | 2018-05-24 | 2018-05-24 |  | 3 | 2018-05-24 | Done
1670 | Brookhaven Generator | E180220d | 2018-02-22 | Wall information and DWG files | Compile wall information | Approval and comments | no |  |  | 2018-03-02 |  |  | 2018-07-22 | Done
1689 | Jasco Security Gate | E180306a | 2018-03-08 | Contact Utility Co. | 3/14 Follow up on 3/15 Eddie Klepacki (405) 553-5406. Need to coordinate moving the poles | Tim's instructions | no |  |  | 2018-04-12 |  |  | 2018-05-27 | Done
1689 | Jasco Security Gate | E180420a | 2018-04-23 | 75% CD due | Superceded | 25% CD issue | no |  | 2018-05-14 | 2018-05-05 |  |  | 2018-05-26 | Done
1717 | Greenbriar CC Reception Desk | E180423a | 2018-04-23 | Base files |  |  | no |  | 2018-04-24 | 2018-04-23 |  |  | 2018-04-24 | Done
1696 | EPIROC Headquarters | p11-95 | 2018-04-23 | IFC |  |  | billed |  | 2018-04-25 | 2018-04-24 |  | 3 | 2018-04-25 | Done
1715 | Modern Acupuncture - Kingwood | E180418f | 2018-04-23 | Send Letter to Lana regarding city comments |  |  | no |  | 2018-04-23 | 2018-04-23 |  |  | 2018-05-08 | Done
1716 | Humane Society Animal Shelter |  | 2018-04-23 | Base files |  |  | no |  |  | 2018-04-24 |  | 1 | 2018-04-30 | Done
1689 | Jasco Security Gate | E180420a | 2018-04-23 | IFC | Superceded |  | no |  | 2018-06-06 | 2018-06-05 |  |  | 2018-06-11 | Done
1317 | Joyce Dr PD Station | p11-95 | 2018-04-23 | Call inspector to determine changes to be made. | 4/23 Called @4:40PM left message |  | no |  |  | 2018-04-24 |  | 1 | 2018-04-24 | Done
1692 | Celeris (2018) | c180424 | 2018-04-24 | Candidate A Forney |  |  | no |  |  |  |  | 0.5 | 2018-04-24 | Done
1721 | Granite Schools |  | 2018-04-25 | LTG work |  |  | no |  |  |  |  | 4 | 2018-04-25 | Done
1725 | Camacho UPV Office |  | 2018-04-25 | IFC |  |  | billed |  | 2018-04-26 |  |  | 0.5 | 2018-04-25 | Done
1724 | TDC Parking Phase 1 | E180426a | 2018-04-26 | Set up files and schedule |  |  | no |  |  | 2018-04-30 |  | 2 | 2018-05-01 | Done
1724 | TDC Parking Phase 1 | E180426a | 2018-04-26 | Review set to OWT | Internal review |  | no |  | 2018-05-07 | 2018-05-07 |  | 4 | 2018-05-01 | Done
1689 | Jasco Security Gate | E180515b | 2018-05-17 | 95% drawings and specs due | Schedule in email |  | no |  | 2018-05-28 | 2018-05-26 |  | 1 | 2018-05-27 | Done
1716 | Humane Society Animal Shelter | E180423b | 2018-04-26 | Set up project | See email for requirements |  | no |  |  | 2018-04-27 |  | 1 | 2018-04-30 | Done
1716 | Humane Society Animal Shelter |  | 2018-04-26 | Preliminary set |  |  | no |  | 2018-05-01 | 2018-04-30 |  | 6 | 2018-04-30 | Done
1535 | Cornerstone Baptist Church | E180426c | 2018-04-26 | Fixture K photometrics |  |  | no | [5 empty] | 2018-04-26 | Done
1704 | Knights Inn Willow Park | E180427b | 2018-04-27 | Update revit model |  |  | no |  |  | 2018-04-27 |  | 1 | 2018-04-29 | Done
1704 | Knights Inn Willow Park | E180427c | 2018-04-27 | MP Sheets |  |  | no |  |  | 2018-04-27 |  | 2 | 2018-04-29 | Done
1707 | Ryan Schools |  | 2018-04-27 | Design Site Visit |  |  | billed |  |  | 2018-04-20 |  | 6 | 2018-04-20 | Done
1392 | UNT Clark Bakery | E180430a | 2018-05-01 | Record drawings |  |  | billed |  |  | 2018-05-02 |  | 1 | 2018-05-14 | Done
1689 | Jasco Security Gate | E180515b | 2018-05-17 | 100% CD set |  |  | no |  | 2018-06-01 | 2018-05-31 |  | 0.5 | 2018-06-04 | Done
1721 | Granite Schools | E180427d | 2018-04-27 | Comments from Powers | See email for comments |  | no |  |  | 2018-05-02 |  | 2 | 2018-05-09 | Done
1421 | KXAS Remodel | E180515c | 2018-05-17 | Lab revision data | Superceded. Scott to provide outlet layouts | Scott's information | no | [5 empty] | 2018-10-29 | Done
1538 | UNT Coliseum Concourse | E180430c | 2018-05-01 | RFI 94 | Mike took care of it. |  | no |  |  | 2018-05-02 |  |  | 2018-05-14 | Done
1715 | Modern Acupuncture - Kingwood | E180501a | 2018-05-01 | Lana's comments | 5/8 Resolved. Call Lana 5/2 afternoon See email for comments |  | no |  |  | 2018-05-02 |  | 1 | 2018-05-08 | Done
1535 | Cornerstone Baptist Church | E180501b | 2018-05-01 | Fixture K submittal |  |  | no |  | 2018-05-02 | 2018-05-02 |  | 1 | 2018-05-02 | Done
1670 | Brookhaven Generator | E180502a | 2018-05-02 | Change order | Done |  | no |  |  | 2018-05-02 |  |  | 2018-05-02 | Done
1317 | Joyce Dr PD Station | E180503a | 2018-05-03 | Daylight switching and other qs |  |  | no |  |  |  |  | 1 | 2018-05-03 | Done
1689 | Jasco Security Gate | E180517c | 2018-05-17 | Provide photometrics |  |  | no |  |  | 2018-05-20 |  | 3 | 2018-05-21 | Done
1721 | Granite Schools | E180502c | 2018-05-07 | Tom's Comments | See email for instructions |  | no |  |  | 2018-05-07 |  | 2 | 2018-05-09 | Done
1689 | Jasco Security Gate | E180517c | 2018-05-17 | Review action items |  | IFC Work | no | [5 empty] | 2018-06-01 | Done
1696 | EPIROC Headquarters | E180323c | 2018-03-27 | Revit update |  | IFC Work | no | [5 empty] | 2018-04-25 | Done
1729 | Angel Montisory | E180507a | 2018-05-07 | Prepare proposal |  |  | no |  |  | 2018-05-08 |  | 1 | 2018-05-09 | Done
1692 | Celeris (2018) | C180507 | 2018-05-07 | Nash |  |  | billed |  |  |  |  | 0.5 | 2018-05-07 | Done
1696 | EPIROC Headquarters | E180420b | 2018-04-23 | Update Revit file |  | Schedule | no | [5 empty] | 2018-04-25 | Done
1594 | Pflugerville AS |  | 2018-05-08 | Submittal billing |  |  | billed | [5 empty] | 2018-05-08 | Done
1689 | Jasco Security Gate | E180506a | 2018-05-08 | Update base files |  |  | no |  |  | 2018-05-09 |  | 1 | 2018-05-14 | Done
1727 | Moss Public Schools | E180507b | 2018-05-08 | Set up project / review set |  |  | no | HIGH | 2018-05-09 | 2018-05-09 |  | 6 | 2018-05-13 | Done
1696 | EPIROC Headquarters | E180420b | 2018-04-23 | Specs go by |  | Schedule | no | [5 empty] | 2018-04-25 | Done
1317 | Joyce Dr PD Station | E180508a | 2018-05-08 | RCO 031 |  |  | no |  |  | 2018-05-08 |  | 0.5 | 2018-05-08 | Done
1704 | Knights Inn Willow Park | E180507c | 2018-05-08 | Comments |  |  | no |  |  | 2018-05-23 |  | 1 | 2018-05-23 | Done
1670 | Brookhaven Generator | E180507f | 2018-05-08 | Coordinate architect's site visit | Done on 5/11 |  | no |  | 2018-05-11 | 2018-05-09 |  | 3 | 2018-05-11 | Done
1728 | The Joint - Park Forest | E180508b | 2018-05-08 | Review existing information |  |  | no |  |  | 2018-05-09 |  |  | 2018-05-10 | Done
1704 | Knights Inn Willow Park |  | 2018-05-14 | reverse washer and dryer |  | IFC | no | [5 empty] | 2018-05-23 | Done
1729 | Angel Montisory | E180508d | 2018-05-08 | MP Data for proposal | Information in email |  | no |  |  | 2018-05-09 |  | 0 | 2018-05-09 | Done
1708 | Velma Schools | E180508e | 2018-05-08 | Review ltg fixture submittal |  |  | no |  |  | 2018-05-09 |  | 0.5 | 2018-05-11 | Done
1704 | Knights Inn Willow Park |  | 2018-05-14 | relocate condenser |  | IFC | no | [5 empty] | 2018-05-23 | Done
1704 | Knights Inn Willow Park | E180514a | 2018-05-17 | Ice Maker nameplate information |  | IFC work | no | [5 empty] | 2018-05-23 | Done
1317 | Joyce Dr PD Station | E180509c | 2018-05-09 | Punch List SV | @10 AM |  | no |  | 2018-05-15 | 2018-05-15 | 3 | 3 | 2018-05-15 | Done
1721 | Granite Schools |  | 2018-05-09 | IFC |  |  | billed |  |  |  |  | 2 | 2018-05-10 | Done
1728 | The Joint - Park Forest | E180510b | 2018-05-10 | Base files |  |  | billed |  |  | 2018-05-10 |  | 2 | 2018-05-10 | Done
1730 | The Joint - Edmond OK | E180510a | 2018-05-10 | Base files |  |  | no |  |  |  |  | 3 | 2018-05-10 | Done
1707 | Ryan Schools | E180410f | 2018-04-14 | Update base file | 5/17 superceded See email for additional info |  | no |  |  | 2018-04-24 |  |  | 2018-05-17 | Done
1707 | Ryan Schools | E180502b | 2018-05-03 | Update base file | 5/17 Superceded |  | no |  |  | 2018-05-03 |  |  | 2018-05-17 | Done
1707 | Ryan Schools | E180509d | 2018-05-17 | IFC |  |  | billed |  | 2018-05-21 | 2018-05-20 |  | 4 | 2018-05-19 | Done
1707 | Ryan Schools | E180517a | 2018-05-17 | Book specs |  |  | no |  |  | 2018-05-18 |  | 1 | 2018-05-20 | Done
1707 | Ryan Schools | E180517a | 2018-05-17 | Update base files |  |  | no |  |  | 2018-05-17 |  | 1 | 2018-05-19 | Done
1544 | The Community At Lake Ridge | E180510c | 2018-05-10 | RFI 11 |  |  | no |  |  | 2018-05-11 |  | 0.5 | 2018-05-11 | Done
1582 | Northern Hills Elementary Safe Room | E180510d | 2018-05-10 | Electrical Submittal |  |  | billed |  | 2018-05-15 | 2018-05-11 |  | 2 | 2018-05-14 | Done
1728 | The Joint - Park Forest | E180510d | 2018-05-10 | Additional photos |  |  | no |  |  | 2018-05-10 |  | 0.5 | 2018-05-10 | Done
1582 | Northern Hills Elementary Safe Room | E180511a | 2018-05-11 | CAD file to contractor |  |  | billed |  |  | 2018-05-15 | 1 | 0.5 | 2018-05-15 | Done
1711 | Funky Town Donut Shop | p11-90 | 2018-04-04 | LFS Note regarding submittals to architect |  | IFC Work | no | [5 empty] | 2018-07-22 | Done
1715 | Modern Acupuncture - Kingwood | E180418f | 2018-04-23 | City Comments | Done | Lana's response | no |  |  | 2018-04-23 |  |  | 2018-07-22 | Done
1716 | Humane Society Animal Shelter | E180504a | 2018-05-07 | Architect's markups |  |  | no |  | 2018-05-07 | 2018-05-21 |  | 1 | 2018-05-23 | Done
1727 | Moss Public Schools | E180507b | 2018-05-15 | IFC |  |  | billed |  |  | 2018-05-15 |  | 0.5 | 2018-05-15 | Done
1715 | Modern Acupuncture - Kingwood | E180501a | 2018-05-15 | Corporate Comments | See email for comments |  | billed |  |  | 2018-05-15 | 1 | 1 | 2018-05-15 | Done
1317 | Joyce Dr PD Station |  | 2018-05-15 | Punch list Report |  |  | billed |  |  | 2018-05-15 | 2 | 3 | 2018-05-16 | Done
1544 | The Community At Lake Ridge | E180515a | 2018-05-15 | RFI 013 |  |  | no |  |  | 2018-05-15 | 1 | 1 | 2018-05-15 | Done
1716 | Humane Society Animal Shelter | E180509a | 2018-05-09 | Solar light for monument sign | Went traditional |  | no |  |  | 2018-05-21 |  |  | 2018-05-22 | Done
1692 | Celeris (2018) |  | 2018-05-15 | DXL06051 |  |  | no |  |  |  |  | 0.5 | 2018-05-15 | Done
1716 | Humane Society Animal Shelter | E180509b | 2018-05-09 | Update border | Superceded |  | no |  |  | 2018-05-21 |  | 0 | 2018-05-22 | Done
1724 | TDC Parking Phase 1 | E180514b | 2018-05-17 | Update site plan | Superceded | IFC work | no | [5 empty] | 2018-05-25 | Done
1724 | TDC Parking Phase 1 | E180426a | 2018-04-26 | Issue for Construction |  |  | billed |  | 2018-05-31 | 2018-05-30 |  | 3 | 2018-05-30 | Done
1724 | TDC Parking Phase 1 | E180426a | 2018-04-26 | Review set to OWT |  |  | no |  | 2018-05-25 | 2018-05-26 |  |  | 2018-05-26 | Done
1726 | Lana's New Project | E180410e | 2018-04-14 | Prepare proposal |  | Tim's instructions | no |  |  | 2018-04-16 |  |  | 2018-04-16 | Done
1728 | The Joint - Park Forest |  | 2018-05-11 | Check COMCheck SF |  | IFC | no | [5 empty] | 2018-06-26 | Done
1728 | The Joint - Park Forest |  | 2018-05-10 | Coordinate MP sheets | Waiting for Tim | IFC Work | no |  |  | 2018-05-11 |  |  | 2018-06-26 | Done
1728 | The Joint - Park Forest |  | 2018-05-10 | IFR due | Waiting for Tim | Tim's instructions | no |  | 2018-05-11 | 2018-05-11 |  |  | 2018-06-26 | Done
1730 | The Joint - Edmond OK |  | 2018-05-10 | Change seal to OK seal |  | IFC Work | no |  |  | 2018-05-14 |  |  | 2018-06-26 | Done
1317 | Joyce Dr PD Station | E180517b | 2018-05-17 | Revision 10 |  |  | no |  |  | 2018-05-17 |  | 1 | 2018-05-17 | Done
1730 | The Joint - Edmond OK |  | 2018-05-10 | Coordinate M equipment |  | IFC Work | no | [5 empty] | 2018-06-26 | Done
1730 | The Joint - Edmond OK |  | 2018-05-10 | Coordiante (e) panel |  | IFC Work | no | [5 empty] | 2018-06-26 | Done
1732 | City of Lake Worth Projects | E180516c | 2018-05-17 | Proposal |  |  | no |  | 2018-05-17 | 2018-05-17 |  | 1 | 2018-05-17 | Done
1730 | The Joint - Edmond OK | E180510a | 2018-05-17 | Site Pictures: (208V/3ph) | Photos are also in the email. | IFC Work | no | [5 empty] | 2018-06-26 | Done
1731 | Church at the Crossings | E180516b | 2018-05-17 | Proposal |  |  | no |  |  | 2018-05-18 |  | 0.5 | 2018-05-18 | Done
mkt | Marketing | E180517e | 2018-05-17 | Marketing Meeting | 5/21 @ 1:30 PM |  | no |  |  | 2018-05-21 | 2 | 2 | 2018-05-22 | Done
OPS | Operations |  | 2018-02-01 | LTG controls to include dimmer controls | Plan for V02 | Specs V02 | no | V02 |  |  | 2 |  |  | Waiting
OPS | Operations |  | 2018-05-15 | Update palette in template | Lighting fixtures, scales etc. | Next Update | no | V02 |  |  | 2 |  |  | Waiting
1689 | Jasco Security Gate | E180518a | 2018-05-18 | Updated base file |  | IFC Work | no | [5 empty] | 2018-06-01 | Done
1730 | The Joint - Edmond OK |  | 2018-05-18 | IFC due | Confirm date | Tim's instructions | no |  |  | 2018-05-18 |  |  | 2018-06-04 | Done
1707 | Ryan Schools |  | 2018-05-18 | Add gas controller |  |  | no |  |  |  |  | 1 | 2018-05-19 | Done
1317 | Joyce Dr PD Station | E180518b | 2018-05-18 | RFI053 |  |  | no |  |  |  |  | 0.5 | 2018-05-18 | Done
1716 | Humane Society Animal Shelter | E180518c | 2018-05-18 | IFC due |  |  | billed |  | 2018-05-25 | 2018-05-22 |  |  | 2018-05-25 | Done
1716 | Humane Society Animal Shelter | E180518c | 2018-05-18 | Comments |  |  | no |  |  | 2018-05-21 |  | 1 | 2018-05-23 | Done
1716 | Humane Society Animal Shelter | E180518c | 2018-05-18 | Update base files |  |  | no |  |  | 2018-05-21 |  |  | 2018-05-22 | Done
1707 | Ryan Schools | E180519a | 2018-05-19 | MP Sheets |  |  | no |  |  | 2018-05-19 |  | 3 | 2018-05-19 | Done
1707 | Ryan Schools |  | 2018-05-20 | Final IFC QC |  |  | no |  |  | 2018-05-21 |  | 2 | 2018-05-20 | Done
1707 | Ryan Schools |  | 2018-05-20 | Verify Fire alarm reqs |  |  | no |  |  | 2018-05-21 |  | 1 | 2018-05-20 | Done
1583 | 7 City Church |  | 2018-05-20 | Plan SV | Set for 6/11 @ 10 AM |  | billed |  |  | 2018-05-29 |  |  | 2018-06-06 | Done
1707 | Ryan Schools | E180520a | 2018-05-20 | Last touches |  |  | no |  |  | 2018-05-21 |  | 1 | 2018-05-21 | Done
1716 | Humane Society Animal Shelter |  | 2018-05-20 | Site Plan |  |  | no |  |  |  |  | 3 | 2018-05-20 | Done
1451 | The Door Church | E180518d | 2018-05-22 | Hardware Submittal |  |  | no |  |  | 2018-05-22 |  | 0.5 | 2018-05-22 | Done
1716 | Humane Society Animal Shelter | E180521a | 2018-05-21 | Update files. | See email |  | no |  |  |  |  | 1 | 2018-05-22 | Done
1691 | Sushi Restaurant Dallas | E180521b | 2018-05-21 | Dimmer submittal |  |  | no |  |  | 2018-05-22 |  | 0.5 | 2018-05-22 | Done
1716 | Humane Society Animal Shelter | E180518c | 2018-05-21 | Spec go by |  |  | no |  |  | 2018-05-23 |  | 1 | 2018-05-24 | Done
1716 | Humane Society Animal Shelter | E180518c | 2018-05-21 | Monument sign and outlet locations |  |  | no |  |  | 2018-05-22 |  | 1 | 2018-05-23 | Done
1689 | Jasco Security Gate | E180522a | 2018-05-22 | Change fixture to XARL | Waiting for James' confirmation |  | no |  |  | 2018-05-26 |  | 1 | 2018-05-27 | Done
1629 | Heritage Glenn MOB Shell | E180522b | 2018-05-22 | IFC Due |  | Final Date | no |  | 2018-06-01 | 2018-05-31 |  |  | 2018-07-22 | Done
1583 | 7 City Church | E180522c | 2018-05-22 | Update model | Superceded |  | no |  |  | 2018-06-06 |  |  | 2018-06-25 | Done
1716 | Humane Society Animal Shelter | E180522d | 2018-05-22 | Latest files and site plan comments |  |  | no |  |  | 2018-05-22 |  | 1 | 2018-05-23 | Done
1716 | Humane Society Animal Shelter | E180522d | 2018-05-22 | Send CAD site plan to William |  |  | no |  |  | 2018-05-22 |  | 1 | 2018-05-23 | Done
1670 | Brookhaven Generator | E180522e | 2018-05-22 | Gravel vs pad | 5/23 Pad ok 5/22 Sent email to Bobby |  | no |  |  | 2018-05-23 |  |  | 2018-05-24 | Done
1704 | Knights Inn Willow Park | 180521 | 2018-05-22 | Update Revit file |  |  | no |  |  | 2018-05-23 |  | 1 | 2018-05-23 | Done
1716 | Humane Society Animal Shelter |  | 2018-05-22 | Final IFC QC |  |  | no |  |  | 2018-05-23 |  | 3 | 2018-05-25 | Done
1689 | Jasco Security Gate | E180522g | 2018-05-22 | Meeting notes |  |  | no |  |  | 2018-05-26 |  | 1 | 2018-05-27 | Done
1689 | Jasco Security Gate | E180522h | 2018-05-22 | Update base file | Superceded |  | no |  |  | 2018-05-26 |  | 1 | 2018-05-26 | Done
1716 | Humane Society Animal Shelter | E180522i | 2018-05-22 | Match future floor plan |  |  | no |  |  | 2018-05-23 |  | 0.5 | 2018-05-24 | Done
1421 | KXAS Remodel | E180523a | 2018-05-23 | Revision 7 |  |  | billed |  | 2018-05-28 | 2018-05-26 |  |  | 2018-05-29 | Done
1629 | Heritage Glenn MOB Shell | E180523b | 2018-05-23 | Review set only |  |  | no |  | 2018-05-24 | 2018-05-23 |  |  | 2018-05-23 | Done
1704 | Knights Inn Willow Park | p12-8 | 2018-05-23 | Tim's additions |  |  | billed |  |  | 2018-05-23 |  | 1 | 2018-05-23 | Done
1716 | Humane Society Animal Shelter |  | 2018-05-23 | Check future loads |  |  | no |  |  |  |  | 0.5 | 2018-05-25 | Done
1629 | Heritage Glenn MOB Shell | E180522b | 2018-05-23 | Comments and such |  |  | no |  |  | 2018-05-23 |  | 2 | 2018-05-23 | Done
1716 | Humane Society Animal Shelter | P12-8 | 2018-05-23 | Resize main service for expansion |  |  | no |  |  | 2018-05-23 |  | 0.5 | 2018-05-25 | Done
1629 | Heritage Glenn MOB Shell | E180522bc | 2018-05-23 | Specs go by |  | IFC Work | no |  |  | 2018-05-23 |  | 1 | 2018-05-31 | Done
1689 | Jasco Security Gate | E180522g | 2018-05-23 | Meeting notes. | See email for clarifications | IFC Work | no | [5 empty] | 2018-06-01 | Done
1477 | Eugene McCray Recreation Center | E180523c | 2018-05-23 | CAD files to GSBS |  |  | no |  |  |  |  | 0.5 | 2018-05-23 | Done
1478 | Handley Meadowbrook Rec Center | E180523c | 2018-05-23 | CAD files to GSBS |  |  | no |  |  |  |  | 0.5 | 2018-05-23 | Done
1629 | Heritage Glenn MOB Shell | E180524a | 2018-05-24 | Site lighting changes |  |  | no |  |  | 2018-05-24 |  | 1 | 2018-05-24 | Done
1631 | Brown Street Church Addition | E180504b | 2018-05-24 | Punch List Report |  |  | billed |  |  | 2018-05-25 |  | 3 | 2018-05-25 | Done
1706 | The Joint Windsong Ranch | E180524b | 2018-05-24 | P sheets and fire alarm |  |  | no |  |  | 2018-05-24 |  |  | 2018-05-25 | Done
1689 | Jasco Security Gate | P12-9 | 2018-05-25 | Add Sensors |  |  | no |  |  | 2018-05-26 |  | 1 | 2018-05-27 | Done
1730 | The Joint - Edmond OK |  | 2018-05-25 | IFR |  |  | no |  |  |  |  | 4 | 2018-05-25 | Done
1733 | Nekter | E180525a | 2018-05-25 | Proposal | 5/26 Sent email to Tim |  | no |  |  | 2018-05-29 |  | 0.5 | 2018-05-30 | Done
1421 | KXAS Remodel | E180524c | 2018-05-26 | Add data to rev 7 | Se email |  | no |  |  | 2018-05-26 |  |  | 2018-05-29 | Done
1421 | KXAS Remodel | E180524d | 2018-05-26 | Update base file | See email |  | no |  |  | 2018-05-26 |  |  | 2018-05-29 | Done
1689 | Jasco Security Gate | E180525b | 2018-05-26 | Update base file |  |  | no |  |  | 2018-05-26 |  | 0.5 | 2018-05-26 | Done
1724 | TDC Parking Phase 1 | E180525c | 2018-05-26 | Update base file |  |  | no |  |  | 2018-05-26 |  | 0.5 | 2018-05-26 | Done
1689 | Jasco Security Gate | E180517c | 2018-05-26 | Meeting notes | Add bollard lights |  | no |  |  | 2018-05-26 |  | 1 | 2018-05-27 | Done
1421 | KXAS Remodel | E180529a | 2018-05-26 | Replace homeruns? | 5/29 Yes Need Scott's confirmation |  | no |  |  | 2018-05-29 |  | 0.5 | 2018-05-29 | Done
1670 | Brookhaven Generator | E180529b | 2018-05-26 | Issue for Review |  |  | billed |  |  | 2018-05-29 |  | 0.5 | 2018-05-29 | Done
1689 | Jasco Security Gate | E180529c | 2018-05-29 | Specs |  |  | no |  |  |  |  | 1 | 2018-05-29 | Done
1583 | 7 City Church | E180529d | 2018-05-29 | AVL Consultant Information |  |  | no |  |  |  |  | 0.5 | 2018-05-29 | Done
1421 | KXAS Remodel | E180529e | 2018-05-29 | Revision 7 | Waiting for Scott's instructions |  | no | Rev 7 |  |  |  |  | 2018-07-05 | Done
1544 | The Community At Lake Ridge | E180529f | 2018-05-29 | AVL changes | Waiting for power equip consumption | John's info | no | Rev 6 |  |  |  | 1 | 2018-06-14 | Done
1734 | The Joint - Quail Springs | E180530a | 2018-05-30 | Review Set |  |  | no |  |  | 2018-05-31 |  | 1 | 2018-06-05 | Done
1724 | TDC Parking Phase 1 | E180530b | 2018-05-30 | Camera Locations |  |  | no |  |  | 2018-05-30 |  | 1 | 2018-05-30 | Done
1544 | The Community At Lake Ridge | E180530c | 2018-05-30 | Meter location RFI. | Answered email |  | no |  |  |  |  | 0.5 | 2018-05-30 | Done
1583 | 7 City Church | E180530d | 2018-05-30 | AVL Contact Information |  |  | no | [5 empty] | 2018-05-30 | Done
1689 | Jasco Security Gate | E180531a | 2018-05-31 | Meeting Comments | Added outlets. Waiting for confirmation on light poles Need outlet layout. |  | no |  |  | 2018-06-01 |  |  | 2018-06-04 | Done
1689 | Jasco Security Gate | E180531a | 2018-05-31 | Final review set due |  |  | billed |  | 2018-06-04 | 2018-06-01 |  |  | 2018-06-04 | Done
1692 | Celeris (2018) | C180531 | 2018-05-31 | Lake Houston Parkway |  |  | no |  |  | 2018-05-31 |  | 0.5 | 2018-05-31 | Done
1629 | Heritage Glenn MOB Shell | E180531c | 2018-05-31 | final Comments |  |  | no |  |  | 2018-05-31 |  | 0.5 | 2018-05-31 | Done
1689 | Jasco Security Gate | E180601a | 2018-06-01 | WH changes | See email |  | no |  |  | 2018-06-01 |  | 0.5 | 2018-06-04 | Done
1730 | The Joint - Edmond OK | E180601b | 2018-06-01 | Comments / IFC |  |  | billed |  |  | 2018-06-04 |  | 0.5 | 2018-06-04 | Done
1734 | The Joint - Quail Springs | E180601c | 2018-06-04 | Existing building information |  |  | no |  |  | 2018-06-04 |  | 1 | 2018-06-05 | Done
1478 | Handley Meadowbrook Rec Center |  | 2018-05-30 | Invoice 12.5% per month |  |  | billed | [5 empty] | 2018-05-30 | Done
1477 | Eugene McCray Recreation Center |  | 2018-05-30 | Invoice 12.5% per month |  |  | billed | [5 empty] | 2018-05-30 | Done
1478 | Handley Meadowbrook Rec Center |  | 2018-06-30 | Invoice 12.5% per month |  |  | billed | [5 empty] | 2018-06-30 | Done
1477 | Eugene McCray Recreation Center |  | 2018-06-30 | Invoice 12.5% per month |  |  | billed | [5 empty] | 2018-06-30 | Done
1478 | Handley Meadowbrook Rec Center |  | 2018-07-30 | Invoice 12.5% per month |  |  | billed |  |  | 2018-07-30 |  |  | 2018-07-31 | Done
1477 | Eugene McCray Recreation Center |  | 2018-07-30 | Invoice 12.5% per month |  |  | billed |  |  | 2018-07-30 |  |  | 2018-07-31 | Done
1478 | Handley Meadowbrook Rec Center |  | 2018-08-30 | Invoice 12.5% per month |  |  | billed |  |  | 2018-08-30 |  |  | 2018-08-15 | Done
1477 | Eugene McCray Recreation Center |  | 2018-08-30 | Invoice 12.5% per month |  |  | billed |  |  | 2018-08-30 |  |  | 2018-08-15 | Done
1478 | Handley Meadowbrook Rec Center |  | 2018-09-30 | Invoice 12.5% per month |  |  | billed |  |  | 2018-09-30 |  |  | 2018-10-04 | Done
1477 | Eugene McCray Recreation Center |  | 2018-09-30 | Invoice 12.5% per month |  |  | billed |  |  | 2018-09-30 |  |  | 2018-10-04 | Done
1478 | Handley Meadowbrook Rec Center |  | 2018-10-30 | Invoice 12.5% per month |  |  | billed |  |  | 2018-11-02 |  |  | 2018-11-12 | Done
1477 | Eugene McCray Recreation Center |  | 2018-10-30 | Invoice 12.5% per month |  |  | billed |  |  | 2018-11-02 |  |  | 2018-11-12 | Done
1478 | Handley Meadowbrook Rec Center | E181206d | 2018-11-30 | Invoice 12.5% per month |  |  | billed |  |  | 2018-12-04 |  | 0 | 2018-12-06 | Done
1477 | Eugene McCray Recreation Center | E181206d | 2018-11-30 | Invoice 12.5% per month |  |  | billed |  |  | 2018-12-04 |  | 0 | 2018-12-06 | Done
1583 | 7 City Church |  |  | 50% CD billing |  |  | billed | [5 empty] | 2018-05-15 | Done
1734 | The Joint - Quail Springs | E180605a | 2018-06-05 | MP Sheets |  |  | no |  |  | 2018-06-05 |  | 2 | 2018-06-05 | Done
1734 | The Joint - Quail Springs | IFC markups | 2018-06-06 | Incorporate QC markups |  | IFC Work | no | [5 empty] | 2018-06-26 | Done
1477 | Eugene McCray Recreation Center | E180604a | 2018-06-06 | Submittals |  |  | no |  |  | 2018-06-06 |  | 2 | 2018-06-06 | Done
1707 | Ryan Schools | E180605b | 2018-06-06 | Submittals | Returned without review |  | no |  |  | 2018-06-06 |  | 0.5 | 2018-06-07 | Done
1582 | Northern Hills Elementary Safe Room | E180606a | 2018-06-06 | Shop Drawing Review |  |  | no |  |  | 2018-06-06 |  | 1 | 2018-06-08 | Done
1583 | 7 City Church | E180606b | 2018-06-06 | Site Visit | 6/11 @ 10 AM |  | no |  |  | 2018-06-11 | 3 | 4 | 2018-06-11 | Done
1583 | 7 City Church | E180606c | 2018-06-06 | Audio Drawings |  |  | no |  |  | 2018-06-06 |  |  | 2018-06-25 | Done
1689 | Jasco Security Gate | E180606d | 2018-06-06 | IFC due | 6/12 @ noon |  | no |  | 2018-06-12 | 2018-06-10 |  |  | 2018-06-11 | Done
1581 | Crescent Schools |  | 2018-06-06 | Fiber Optic Plan |  |  | no |  |  |  |  | 1 | 2018-06-06 | Done
1689 | Jasco Security Gate | E180606d | 2018-06-07 | Evaluate new indoor fixture |  |  | no |  |  |  |  | 1 | 2018-06-09 | Done
1689 | Jasco Security Gate | call | 2018-06-06 | revert to original pole lights |  |  | no |  |  |  |  | 1 | 2018-06-09 | Done
1538 | UNT Coliseum Concourse | E180608a | 2018-06-08 | Punch List SV | Need date |  | billed |  |  | 2018-06-11 |  |  | 2018-06-18 | Done
1689 | Jasco Security Gate | p12-11 | 2018-06-08 | Notes from Call with Glenn |  |  | no |  |  | 2018-06-08 |  | 1 | 2018-06-09 | Done
1583 | 7 City Church | E180606e | 2018-06-09 | AVL Lighting diagrams |  |  | no | [5 empty] | 2018-06-25 | Done
1583 | 7 City Church | E180607a | 2018-06-09 | Updated Revit model | Need to answer email Qs |  | no |  |  | 2018-06-09 |  |  | 2018-06-25 | Done
1735 | Staybridge Hotel | E180611a | 2018-06-11 | Proposal |  |  | no |  |  |  |  | 0.5 | 2018-06-11 | Done
1544 | The Community At Lake Ridge | E180611b | 2018-06-11 | Update site plan |  |  | no | Rev 6 |  | 2018-06-13 |  | 0.5 | 2018-06-14 | Done
1583 | 7 City Church | E180608b | 2018-06-11 | AVL Circuit needs |  |  | no | [5 empty] | 2018-06-25 | Done
1689 | Jasco Security Gate | E180611c | 2018-06-11 | New Spec go by |  |  | no |  |  |  |  | 2 | 2018-06-11 | Done
1689 | Jasco Security Gate | E180611d | 2018-06-11 | Strikes for doors |  |  | no |  |  |  |  | 0.5 | 2018-06-15 | Done
1689 | Jasco Security Gate | E180611e | 2018-06-11 | MP Sheets |  |  | no |  |  |  |  | 0.5 | 2018-06-12 | Done
1689 | Jasco Security Gate | E180611f | 2018-06-11 | Alternate |  |  | no |  |  |  |  | 0.5 | 2018-06-15 | Done
1538 | UNT Coliseum Concourse |  | 2018-06-11 | Punch List SV |  |  | no |  |  | 2018-06-18 | 6 | 6 | 2018-06-18 | Done
1583 | 7 City Church | E180613a | 2018-06-13 | Add coffee makers |  |  | no | PH 1 |  | 2018-06-27 |  | 0.5 | 2018-06-28 | Done
1544 | The Community At Lake Ridge | E180614b | 2018-06-14 | M Sheets |  |  | no | Rev 6 |  |  |  | 0.5 | 2018-06-14 | Done
1613 | Norman Hotel | E180614d | 2018-06-14 | FA Question | Answered |  | no |  |  |  |  | 0.5 | 2018-06-14 | Done
1544 | The Community At Lake Ridge |  | 2018-06-14 | Revision 6 due |  |  | billed | Rev 6 | 2018-06-15 | 2018-06-14 |  | 0.5 | 2018-06-14 | Done
1421 | KXAS Remodel | E180612a | 2018-06-14 | Change order assessment | Not needed |  | no |  |  | 2018-06-14 |  |  | 2018-06-27 | Done
1689 | Jasco Security Gate | E180613b | 2018-06-14 | 95CD comments |  |  | no |  |  | 2018-06-14 |  |  | 2018-06-15 | Done
1737 | The Joint - Champions Park | E180613c | 2018-06-14 | Review Set |  |  | no |  |  | 2018-06-15 |  | 2 | 2018-06-26 | Done
1394 | UNT Bruce Hall | E180613d | 2018-06-14 | Record drawings |  |  | no |  |  | 2018-06-20 |  | 1 | 2018-06-25 | Done
1538 | UNT Coliseum Concourse | E180613f | 2018-06-14 | Punch list item # 10 | Need to prepare list |  | no | [5 empty] | 2018-06-18 | Done
1738 | Rudys Power Monitor | E180613g | 2018-06-14 | Review Power Monitor information | Need Proposal |  | no |  |  | 2018-06-15 |  | 0.5 | 2018-06-21 | Done
1583 | 7 City Church | E180608b | 2018-06-14 | Connect house lights to DMX |  |  | no | FULL |  | 2018-06-27 |  | 0.5 | 2018-06-29 | Done
1421 | KXAS Remodel | E180613h | 2018-06-14 | Additional work analysis | Done |  | no |  |  | 2018-06-15 |  |  | 2018-06-27 | Done
1689 | Jasco Security Gate | E180614e | 2018-06-14 | Final IFC instructions | Add second gate operator. |  | no | IFC |  | 2018-06-14 |  | 0.5 | 2018-06-15 | Done
1739 | Moss Schools Concessions | E180614f | 2018-06-14 | Proposal |  |  | no |  |  | 2018-06-15 |  | 0.5 | 2018-06-15 | Done
1689 | Jasco Security Gate | E180615a | 2018-06-15 | Update Border |  |  | no | IFC |  | 2018-06-15 |  |  | 2018-06-15 | Done
1416 | DCCCD Eastfield Generator | E180618a | 2018-06-19 | Sign payment forms again |  |  | no |  |  |  |  | 0.5 | 2018-06-19 | Done
1715 | Modern Acupuncture - Kingwood | E180618b | 2018-06-19 | Questios from contractor |  |  | no |  |  |  |  | 0.5 | 2018-06-19 | Done
1592 | Deer Park Animal Shelter | E180618c | 2018-06-19 | Review Generator cut sheet |  |  | no |  |  |  |  | 0.5 | 2018-06-19 | Done
1583 | 7 City Church | E180619a | 2018-06-19 | Fixture mounting heights | Phase II issue. To be resolved later | IFC Work | no | FULL |  | 2018-06-27 |  |  | 2018-07-11 | Done
1697 | Moss Insurance Office Addition | E180620a | 2018-06-20 | Letter to City |  |  | no |  |  |  |  | 0.5 | 2018-06-21 | Done
1544 | The Community At Lake Ridge | E180621a | 2018-06-21 | Site lights and em light height |  |  | no | REV6 |  |  |  | 2 | 2018-06-21 | Done
1740 | Hill Residence | E180620b | 2018-06-21 | Proposal |  |  | no |  |  |  |  | 0.5 | 2018-06-21 | Done
1604 | Botanic Garden Assessment | E180621b | 2018-06-21 | Final meeting | Scheduled for 8/1 @ 11 AM |  | no |  |  | 2018-08-01 |  |  | 2018-07-17 | Done
1583 | 7 City Church | E180617e | 2018-06-24 | New type J |  |  | no | [5 empty] | 2018-06-21 | Done
1538 | UNT Coliseum Concourse | E180619b | 2018-06-24 | Punch List report | Template to be provided by Travis |  | no |  |  | 2018-06-27 |  | 2 | 2018-06-27 | Done
1689 | Jasco Security Gate | E180622a | 2018-06-24 | Substitution Request |  |  | no |  |  |  |  | 0.5 | 2018-06-25 | Done
1392 | UNT Clark Bakery | E180625a | 2018-06-25 | Record drawing base file | Not used |  | no |  |  | 2018-06-26 |  | 0 | 2018-06-25 | Done
1583 | 7 City Church | E180620c | 2018-06-25 | Photometrics from Jim |  |  | no |  |  | 2018-06-27 |  |  | 2018-06-27 | Done
1421 | KXAS Remodel | E180620d | 2018-06-25 | Markups |  |  | no | Rev 7 |  | 2018-06-29 |  |  | 2018-07-05 | Done
1583 | 7 City Church | E180622b | 2018-06-25 | Phase 1 recept layout to Leslie | incorporated into the review set |  | no | PH 1 |  | 2018-06-27 |  | 1 | 2018-06-28 | Done
1583 | 7 City Church | E180622c | 2018-06-25 | Phase 1 recept TV markups | See also email for more info |  | no | FULL |  | 2018-06-27 |  | 2 | 2018-06-28 | Done
1592 | Deer Park Animal Shelter | E180618c | 2018-06-25 | Another generator submittal |  |  | no |  | 2018-06-27 | 2018-06-27 |  | 0.5 | 2018-06-27 | Done
1421 | KXAS Remodel | E180622d | 2018-06-25 | Update base file for 2nd floor |  |  | no | Rev 7 |  | 2018-06-29 |  | 1 | 2018-07-05 | Done
1421 | KXAS Remodel | E180625b | 2018-06-25 | Review final scope |  |  | no | Rev 7 |  | 2018-06-29 |  |  | 2018-07-05 | Done
1737 | The Joint - Champions Park | E180625c | 2018-06-25 | Existing information available. | Prepared review set. Need MP info |  | no |  |  |  |  | 2 | 2018-06-25 | Done
1583 | 7 City Church | E180625d | 2018-06-26 | Update full model |  |  | no |  |  | 2018-06-27 |  |  | 2018-06-28 | Done
1583 | 7 City Church | E180626a | 2018-06-26 | More recept reqs | Located in email |  | no |  |  | 2018-06-27 |  | 1 | 2018-06-28 | Done
1737 | The Joint - Champions Park |  | 2018-06-26 | MP Info | Need MP Info |  | no | [5 empty] | 2018-06-26 | Done
1421 | KXAS Remodel | E180626b | 2018-06-26 | 2nd floor recept meeting | Monday 7/2 @ 1 PM |  | no |  |  | 2018-07-02 | 3 | 3 | 2018-07-02 | Done
1728 | The Joint - Park Forest | Phone call | 2018-06-26 | IFC Markups |  |  | no |  |  |  |  | 1 | 2018-06-26 | Done
1734 | The Joint - Quail Springs | E180626c | 2018-06-26 | IFC Markups |  |  | billed |  |  |  |  | 1 | 2018-06-26 | Done
1737 | The Joint - Champions Park | E180626e | 2018-06-26 | MP Sheets | Sent review set on 6/26 |  | no |  |  | 2018-06-27 |  |  | 2018-06-26 | Done
1421 | KXAS Remodel | E180626d | 2018-06-26 | Recept SV |  |  | no |  |  | 2018-07-02 | 4 | 3 | 2018-07-02 | Done
1737 | The Joint - Champions Park |  | 2018-06-26 | Final QC | Use IFR file |  | no |  |  | 2018-06-29 |  | 2 | 2018-06-29 | Done
1741 | Baytown Cabin | E180627a | 2018-06-27 | Proposal | p12-18 |  | no |  |  | 2018-06-28 |  | 0.5 | 2018-06-29 | Done
1421 | KXAS Remodel | E180625e | 2018-06-27 | LTG Scope |  |  | no | Rev 7 |  | 2018-06-29 |  | 1.5 | 2018-07-04 | Done
1559 | Southlake MOB Shell | E180626f | 2018-06-27 | Proposal for Photometric As-builts |  |  | no |  |  | 2018-06-27 |  | 1 | 2018-06-28 | Done
1421 | KXAS Remodel | E180627c | 2018-06-27 | Final Scope for Rev 7 |  |  | no | Rev 7 |  | 2018-06-29 |  | 1 | 2018-07-02 | Done
1544 | The Community At Lake Ridge | E180627b | 2018-06-27 | CAD Release |  |  | billed |  |  | 2018-06-27 |  | 0.5 | 2018-06-27 | Done
1738 | Rudys Power Monitor | E180627f | 2018-06-27 | Follow up on Siemens | 6/29 Called supplier (p12-18) |  | no |  |  | 2018-07-02 |  |  | 2018-08-16 | Done
1742 | City of Fort Worth Water Conservation Renovations | E180627d | 2018-06-27 | Proposal |  |  | no |  | 2018-07-02 | 2018-06-29 |  | 1 | 2018-07-02 | Done
1583 | 7 City Church | E180627e | 2018-06-27 | Update phase 1 model |  |  | no |  |  | 2018-06-27 |  | 4 | 2018-06-28 | Done
1582 | Northern Hills Elementary Safe Room | E180627g | 2018-06-27 | Shop Drawing Review |  |  | no |  |  | 2018-06-28 |  | 0.5 | 2018-06-28 | Done
1544 | The Community At Lake Ridge | E180627b | 2018-06-27 | Send CAD files |  |  | billed |  |  | 2018-06-27 |  | 1 | 2018-06-28 | Done
1583 | 7 City Church | E180628a | 2018-06-28 | Conduits from AVL | 6/29 got information |  | no | IFC |  |  |  | 0.5 | 2018-06-29 | Done
1583 | 7 City Church | E180628b | 2018-06-28 | Booth in phase 2 remains in center |  |  | no | IFC |  |  |  | 0.5 | 2018-06-29 | Done
1538 | UNT Coliseum Concourse | E180628c | 2018-06-28 | Prepare record drawings | Information available in files |  | no |  |  | 2018-07-18 |  | 3 | 2018-07-24 | Done
1737 | The Joint - Champions Park | E180626e | 2018-06-28 | Comments |  |  | billed | IFC |  | 2018-06-29 |  | 0.5 | 2018-06-29 | Done
1392 | UNT Clark Bakery | E180628d | 2018-06-28 | Record set comments |  |  | no |  |  | 2018-06-28 |  | 1 | 2018-06-28 | Done
1583 | 7 City Church | E180629a | 2018-06-29 | Additional Ceiling receptacles |  |  | no |  |  | 2018-06-29 |  | 0.5 | 2018-06-29 | Done
1583 | 7 City Church | E180629b | 2018-06-29 | Cube Shadows. | Fixed over the phone. |  | no |  |  |  |  | 0.5 | 2018-06-29 | Done
1583 | 7 City Church | E180628d | 2018-06-29 | Book specs | Need header and footer. See E180709c |  | no | IFC |  |  |  | 2 | 2018-07-11 | Done
1421 | KXAS Remodel | E180629c | 2018-06-29 | Copier locations, etc |  |  | no | Rev 7 |  | 2018-06-30 |  | 1 | 2018-07-04 | Done
1421 | KXAS Remodel | E180629d | 2018-06-29 | Receptacle photos | No action needed. FTR (for the record) |  | no | [5 empty] | 2018-06-29 | Done
1477 | Eugene McCray Recreation Center |  | 2018-06-15 | Billing |  |  | billed | [5 empty] | 2018-06-15 | Done
1478 | Handley Meadowbrook Rec Center |  | 2018-06-15 | Billing |  |  | billed | [5 empty] | 2018-06-15 | Done
1744 | Viandant Gelato Store - Denton | E180702a | 2018-07-02 | Proposal |  |  | no |  |  |  |  | 0.5 | 2018-07-02 | Done
1583 | 7 City Church | E180702b | 2018-07-02 | B-fixtures in café | Need to incorporate. Done | IFC Work | no | IFC |  |  |  | 0 | 2018-07-11 | Done
1583 | 7 City Church | E180702c | 2018-07-02 | Review set for QC |  |  | no | IFC |  |  |  | 1 | 2018-07-13 | Done
1670 | Brookhaven Generator | E180702d | 2018-07-02 | IFC set | Need feedback from Bo |  | no | [5 empty] | 2018-07-06 | Done
1583 | 7 City Church | E180702f | 2018-07-02 | Card reader details |  |  | no | IFC |  |  |  | 0.5 | 2018-07-11 | Done
1421 | KXAS Remodel | E180702g | 2018-07-02 | Update abase |  |  | no | REV 7 |  |  |  | 0.5 | 2018-07-04 | Done
1421 | KXAS Remodel | E180702h | 2018-07-02 | Receptacle markups |  |  | no | REV 7 |  |  |  | 2 | 2018-07-04 | Done
1733 | Nekter | E180702j | 2018-07-02 | Corporate information | Need due date |  | no | IFR |  | 2018-07-19 |  |  | 2018-08-16 | Done
1721 | Granite Schools | E180703a | 2018-07-03 | Submittal |  |  | no | CA |  | 2018-07-03 |  | 0.5 | 2018-07-05 | Done
1583 | 7 City Church | E180703b | 2018-07-03 | Café can addition |  |  | no | IFC |  |  |  | 0.5 | 2018-07-11 | Done
1583 | 7 City Church | E180703c | 2018-07-03 | update revit file for cans |  |  | no | IFC |  |  |  | 0.5 | 2018-07-11 | Done
1530 | Brennan Drop-off Changes | E180703d | 2018-07-03 | Instructions for Addendum 1 | Not needed |  | no | ADD 1 |  | 2018-07-05 |  | 0 | 2018-07-12 | Done
1531 | MLK Drop-off Changes | E180703d | 2018-07-03 | Instructions for Addendum 1 | Not needed |  | no | ADD 1 |  | 2018-07-05 |  | 0 | 2018-07-12 | Done
1532 | Old Hemphill Drop-off Changes | E180703d | 2018-07-03 | Instructions for Addendum 1 |  |  | no | ADD 1 |  | 2018-07-05 |  | 1 | 2018-07-09 | Done
1746 | Xpress Wellness Liberal KS | E180703e | 2018-07-03 | Proposal: Agree on fee with Tim | Use the original fee |  | no |  |  |  |  | 0 | 2018-07-12 | Done
1745 | Mellow Mushroom Round Rock Electrical Diagnostics | E180703f | 2018-07-03 | Proposal |  |  | no |  |  |  |  | 0.5 | 2018-07-03 | Done
1544 | The Community At Lake Ridge | E180703g | 2018-07-03 | Hand Dryer proposal |  |  | no |  |  |  |  | 0.5 | 2018-07-03 | Done
1736 | Varsity Orthopedics at Heritage Glen | E180703h | 2018-07-03 | Review set. Set up project |  |  | no |  |  | 2018-07-04 |  | 3 | 2018-07-14 | Done
1742 | City of Fort Worth Water Conservation Renovations | E180627d | 2018-07-03 | Proposal |  |  | no |  |  |  |  | 0 | 2018-07-03 | Done
1743 | Southlake MOB Photometrics |  | 2018-07-04 | CAD set up and data |  |  | no |  |  |  |  | 3 | 2018-07-04 | Done
1743 | Southlake MOB Photometrics |  | 2018-07-04 | Site Visit |  |  | no |  |  |  |  | 4 | 2018-07-02 | Done
1583 | 7 City Church | E180705a | 2018-07-05 | More recept reqs | Reqs in email |  | no | IFC |  | 2018-07-05 |  | 0.5 | 2018-07-05 | Done
1583 | 7 City Church | E180705b | 2018-07-05 | Update revit model |  |  | no | IFC |  | 2018-07-05 |  | 0 | 2018-07-10 | Done
1583 | 7 City Church | E180705b | 2018-07-05 | Address comments |  |  | no | IFC |  | 2018-07-05 |  | 2 | 2018-07-11 | Done
1421 | KXAS Remodel | E180705c | 2018-07-05 | Add gate operator | see email also |  | no | Rev 7 |  | 2018-07-05 |  |  | 2018-07-06 | Done
1421 | KXAS Remodel | E180705d | 2018-07-05 | MP Sheets |  |  | no | Rev 7 |  |  |  | 1 | 2018-07-05 | Done
1739 | Moss Schools Concessions | E180705e | 2018-07-05 | Set up project | LTG and Demo |  | no |  |  | 2018-07-17 |  | 2 | 2018-07-21 | Done
1670 | Brookhaven Generator | E180706a | 2018-07-06 | IFC |  |  | billed | IFC |  | 2018-07-06 |  | 4 | 2018-07-06 | Done
1594 | Pflugerville AS | E180706b | 2018-07-06 | ONCOR Form |  |  | no |  |  | 2018-07-06 |  | 1 | 2018-07-06 | Done
1711 | Funky Town Donut Shop |  | 2018-07-06 | Fault Calculations |  |  | no |  |  | 2018-07-06 |  | 1 | 2018-07-06 | Done
1421 | KXAS Remodel | E180707a | 2018-07-07 | final Comments |  |  | no | Rev 7 |  |  |  | 0 | 2018-07-12 | Done
1739 | Moss Schools Concessions | E180709a | 2018-07-09 | Design Site Visit | Be there at 10 AM |  | no |  |  | 2018-07-16 | 7 | 7 | 2018-07-16 | Done
1392 | UNT Clark Bakery | E180709b | 2018-07-09 | Add date to record drawings |  |  | no |  |  | 2018-07-09 |  | 0.5 | 2018-07-09 | Done
1583 | 7 City Church | E180709c | 2018-07-09 | Update Revit file |  |  | no | IFC |  | 2018-07-10 |  | 1 | 2018-07-10 | Done
1583 | 7 City Church | Phone call | 2018-07-09 | IFC due |  |  | billed | IFC | 2018-07-13 | 2018-07-12 |  | 1 | 2018-07-13 | Done
1544 | The Community At Lake Ridge | E180709d | 2018-07-09 | LTG Submittal |  |  | billed |  |  | 2018-07-10 |  | 1 | 2018-07-12 | Done
1745 | Mellow Mushroom Round Rock Electrical Diagnostics |  | 2018-07-09 | Site Visit |  |  | no |  |  | 2018-07-09 | 6 | 6 | 2018-07-09 | Done
1745 | Mellow Mushroom Round Rock Electrical Diagnostics |  | 2018-07-10 | Final Report |  |  | billed |  |  | 2018-07-10 | 2 | 2 | 2018-07-10 | Done
1743 | Southlake MOB Photometrics |  | 2018-07-10 | Second Site Visit |  |  | no |  |  | 2018-07-10 | 2 | 2 | 2018-07-10 | Done
1743 | Southlake MOB Photometrics |  | 2018-07-11 | As-built drawing | Working Docs in project #1559 |  | billed |  |  | 2018-07-11 |  | 4 | 2018-07-11 | Done
1604 | Botanic Garden Assessment | E180711a | 2018-07-11 | Final meeting | Wed 8/1 @ 11 AM |  | no |  |  | 2018-08-01 | 3 | 3 | 2018-08-01 | Done
1583 | 7 City Church | E180712 | 2018-07-12 | MP Set |  |  | no |  |  | 2018-07-12 |  | 1 | 2018-07-12 | Done
1421 | KXAS Remodel | E180713a | 2018-07-13 | R4 - Update site base file |  |  | no |  |  |  |  | 0.5 | 2018-07-13 | Done
1670 | Brookhaven Generator | E180713b | 2018-07-13 | Estimate of Probable Cost |  |  | no |  |  | 2018-07-13 |  | 2 | 2018-07-19 | Done
1745 | Mellow Mushroom Round Rock Electrical Diagnostics | E180713c | 2018-07-13 | Panel M spec |  |  | no |  |  |  |  | 0.5 | 2018-07-13 | Done
1583 | 7 City Church | E180713d | 2018-07-13 | Add fixture type K |  |  | no |  |  |  |  | 0.5 | 2018-07-13 | Done
1748 | Modern Acupuncture Las Colinas | E180713e | 2018-07-13 | Review Set Due |  |  | no | IFR | 2018-07-17 | 2018-07-17 |  | 3 | 2018-07-23 | Done
1748 | Modern Acupuncture Las Colinas | E180713f | 2018-07-13 | Review set materials |  |  | billed |  |  | 2018-07-17 |  | 4 | 2018-07-15 | Done
1748 | Modern Acupuncture Las Colinas | E180716a | 2018-07-16 | Titleblock |  |  | no |  |  | 2018-07-17 |  | 0 | 2018-07-25 | Done
1604 | Botanic Garden Assessment |  | 2018-07-17 | Prepare for final meeting |  |  | no |  | 2018-07-31 | 2018-07-30 |  | 2 | 2018-07-31 | Done
1739 | Moss Schools Concessions |  | 2018-07-17 | Document SV |  |  | no |  |  | 2018-07-17 |  | 1 | 2018-07-20 | Done
1736 | Varsity Orthopedics at Heritage Glen |  | 2018-07-17 | IFR work | Need LTG and PWR adapts |  | no |  |  | 2018-07-19 |  | 4 | 2018-07-20 | Done
1544 | The Community At Lake Ridge | E180709d | 2018-07-17 | Revised review |  |  | no |  |  | 2018-07-18 | 1 | 1 | 2018-07-18 | Done
1578 | WRMC Street Lighting | E180718a | 2018-07-18 | Revised IFC |  |  | no |  |  | 2018-07-18 |  | 1 | 2018-07-18 | Done
1421 | KXAS Remodel | E180718c | 2018-07-18 | Rev 8 to fix lights |  |  | no |  |  | 2018-07-19 |  | 1 | 2018-07-20 | Done
1621 | The Creek Church Phase II | E180718b | 2018-07-18 | PR004 |  |  | no |  |  | 2018-07-19 |  | 1 | 2018-07-19 | Done
1578 | WRMC Street Lighting | E180718a | 2018-07-18 | Final reduced scope IFC |  |  | no |  |  | 2018-07-18 |  | 1 | 2018-07-19 | Done
1692 | Celeris (2018) |  | 2018-07-18 | Projects |  |  | billed |  |  |  |  | 1 | 2018-07-15 | Done
1721 | Granite Schools | E180719c | 2018-07-19 | Photometrics submittal |  |  | no |  |  | 2018-07-19 |  | 2 | 2018-07-19 | Done
1421 | KXAS Remodel | E180719a | 2018-07-19 | Changes to new lighting |  |  | no |  |  | 2018-07-20 |  | 1 | 2018-07-20 | Done
1544 | The Community At Lake Ridge | E180720a | 2018-07-20 | Type L and F for PR004 |  |  | no |  |  | 2018-07-20 |  | 1 | 2018-07-20 | Done
1748 | Modern Acupuncture Las Colinas |  | 2018-07-20 | Change riser to 208V, update PWR schedules |  | IFC work | no | [5 empty] | 2018-07-25 | Done
1670 | Brookhaven Generator |  | 2018-07-20 | Add reimbursables to invoice |  |  | billed |  |  |  |  | 0 | 2018-07-12 | Done
1739 | Moss Schools Concessions |  | 2018-07-21 | Add A/C window unit |  | Tim's information | no |  |  |  |  | 1 | 2018-07-31 | Done
1736 | Varsity Orthopedics at Heritage Glen |  | 2018-07-23 | IFR work |  |  | no |  |  |  |  | 6 | 2018-07-25 | Done
1604 | Botanic Garden Assessment |  | 2018-07-23 | Prepare for SV meeting |  |  | no | [5 empty] | 2018-08-01 | Done
1538 | UNT Coliseum Concourse | E180723a | 2018-07-23 | Send LTG base to Mallori |  |  | no |  |  | 2018-07-24 |  | 2 | 2018-07-24 | Done
1736 | Varsity Orthopedics at Heritage Glen | E180724a | 2018-07-24 | Site Plan |  |  | no |  |  |  |  | 2 | 2018-07-25 | Done
1749 | Dove Church Remodel |  | 2018-07-23 | Proposal |  |  | no |  |  | 2018-07-24 |  |  | 2018-07-24 | Done
1538 | UNT Coliseum Concourse |  | 2018-07-24 | Add RFIs |  |  | no | [5 empty] | 2018-07-30 | Done
1538 | UNT Coliseum Concourse |  | 2018-07-24 | Add Fire Alarm documentation | See original RFI (#99) |  | no |  |  |  |  | 2 | 2018-07-26 | Done
1538 | UNT Coliseum Concourse |  | 2018-07-24 | Water heater |  |  | no | [5 empty] | 2018-07-30 | Done
1742 | City of Fort Worth Water Conservation Renovations | E180724b | 2018-07-24 | NTP |  |  | no | [5 empty] | 2018-07-24 | Done
1742 | City of Fort Worth Water Conservation Renovations | E180724b | 2018-07-24 | Site Visit | Scheduling |  | billed |  | 2018-08-06 | 2018-08-06 | 3 | 3 | 2018-08-06 | Done
1538 | UNT Coliseum Concourse |  | 2018-07-24 | Add Fire Marshal's Detectors | Need clarification from Mallori |  | no |  |  | 2018-07-25 |  |  | 2018-07-26 | Done
1538 | UNT Coliseum Concourse |  | 2018-07-24 | Security Camera locations |  |  | no | [5 empty] | 2018-07-24 | Done
1739 | Moss Schools Concessions | E180725a | 2018-07-25 | IFC due |  |  | billed |  | 2018-07-31 | 2018-07-30 |  | 2 | 2018-07-31 | Done
1736 | Varsity Orthopedics at Heritage Glen |  | 2018-07-25 | IFC due |  | Need date | billed | [5 empty] | 2018-08-27 | Done
1736 | Varsity Orthopedics at Heritage Glen | E180726a | 2018-07-26 | EF locations |  |  | no |  |  |  |  | 1 | 2018-07-26 | Done
1538 | UNT Coliseum Concourse |  | 2018-07-24 | Updated RCP |  |  | no |  |  | 2018-07-30 |  |  | 2018-07-30 | Done
1544 | The Community At Lake Ridge | E180725b | 2018-07-25 | Panelboard submittal |  |  | billed |  |  |  |  | 1 | 2018-07-26 | Done
1538 | UNT Coliseum Concourse |  | 2018-07-26 | Record Drawings |  |  | no |  | 2018-07-31 | 2018-07-30 |  |  | 2018-07-30 | Done
1736 | Varsity Orthopedics at Heritage Glen | E180730a | 2018-07-30 | Implement changes |  |  | no |  |  | 2018-07-31 |  | 2 | 2018-08-02 | Done
1736 | Varsity Orthopedics at Heritage Glen |  | 2018-07-30 | 100% CD IFR | Date to be confirmed |  | billed |  | 2018-08-03 | 2018-08-03 |  |  | 2018-07-31 | Done
1538 | UNT Coliseum Concourse | E180730b | 2018-07-30 | Record Drawings Due |  |  | billed |  | 2018-07-31 | 2018-07-30 |  | 2 | 2018-07-30 | Done
1530 | Brennan Drop-off Changes | E180730c | 2018-07-30 | Addendum 1 |  |  | no |  | 2018-07-30 | 2018-07-30 |  | 0.5 | 2018-07-30 | Done
1531 | MLK Drop-off Changes | E180730c | 2018-07-30 | Addendum 1 |  |  | no |  | 2018-07-30 | 2018-07-30 |  | 0.5 | 2018-07-30 | Done
1532 | Old Hemphill Drop-off Changes | E180730c | 2018-07-30 | Addendum 1 |  |  | no |  | 2018-07-30 | 2018-07-30 |  | 0.5 | 2018-07-30 | Done
1477 | Eugene McCray Recreation Center | E180730d | 2018-07-30 | Comments on FA proposal |  |  | no | [5 empty] | 2018-07-31 | Done
1750 | HG Finishout | E180731a | 2018-07-31 | Proposal |  |  | no |  |  |  |  | 0.5 | 2018-07-31 | Done
1693 | The Table Church | E180731b | 2018-07-31 | New Proposal |  |  | no |  |  |  |  | 1 | 2018-07-31 | Done
1736 | Varsity Orthopedics at Heritage Glen | E180801a | 2018-08-01 | Add suite numbers |  |  | no |  |  | 2018-08-02 |  | 2 | 2018-08-02 | Done
1672 | FBC Watauga - Phase 1 | E180802a | 2018-08-02 | LTG Submittal |  |  | no |  |  | 2018-08-03 |  | 1 | 2018-08-06 | Done
1751 | District 90 Salon | E180803a | 2018-08-03 | Proposal |  |  | no |  |  | 2018-08-03 |  |  | 2018-08-06 | Done
1583 | 7 City Church | E180803b | 2018-08-03 | Add 3rd conduit. See email | Need issue date |  | no | Add 2 |  | 2018-08-07 |  | 2 | 2018-08-08 | Done
1733 | Nekter | E180803c | 2018-08-07 | Set up project |  |  | no |  |  | 2018-08-07 |  | 1 | 2018-08-16 | Done
1693 | The Table Church | E180807a | 2018-08-07 | Contact AVL consultant | Info in email |  | no |  |  | 2018-08-08 |  | 0.5 | 2018-08-13 | Done
1746 | Xpress Wellness Liberal KS | E180805a | 2018-08-07 | Project CAD files coming this week |  |  | no |  |  | 2018-08-09 |  | 0 | 2018-10-01 | Done
1742 | City of Fort Worth Water Conservation Renovations | E180806a | 2018-08-07 | Existing drawings |  |  | no |  |  |  |  | 0 | 2018-08-07 | Done
1742 | City of Fort Worth Water Conservation Renovations | E180807b | 2018-08-07 | Update base file | Not done. | Project on hold | no | [5 empty] | 2018-10-30 | Done
1692 | Celeris (2018) |  | 2018-08-07 | Celeris Projects |  |  | billed |  |  |  |  | 1 | 2018-08-07 | Done
1752 | Parkwood Hill Addition | E180808a | 2018-08-08 | Proposal |  |  | no |  |  |  |  | 0.5 | 2018-08-10 | Done
1693 | The Table Church | E180809a | 2018-08-09 | Photometrics and LFS |  |  | no |  |  | 2018-08-10 |  | 2 | 2018-08-20 | Done
1742 | City of Fort Worth Water Conservation Renovations | E180809b | 2018-08-09 | SPC for 3 options |  |  | no |  |  | 2018-08-10 |  | 1 | 2018-08-10 | Done
1582 | Northern Hills Elementary Safe Room | E180810a | 2018-08-10 | FA Submittal |  |  | no | CA |  | 2018-08-10 |  | 1 | 2018-08-13 | Done
1738 | Rudys Power Monitor | E180807c | 2018-08-11 | Contact Contractor |  |  | no |  |  | 2018-08-11 |  | 0.5 | 2018-09-04 | Done
1693 | The Table Church | E180808b | 2018-08-11 | Update base files |  |  | no |  |  | 2018-08-11 |  | 2 | 2018-08-11 | Done
1614 | Euless Library | E180810b | 2018-08-11 | Review schedule and start QC |  |  | no |  |  | 2018-08-22 |  |  | 2018-09-04 | Done
1693 | The Table Church |  | 2018-08-11 | LTG definitions and layout |  |  | no |  |  |  |  | 2 | 2018-08-11 | Done
1693 | The Table Church | E180813a | 2018-08-13 | Update Revit File |  |  | no |  |  | 2018-08-13 |  | 2 | 2018-08-20 | Done
1733 | Nekter | E180813b | 2018-08-13 | Equipment cut sheets |  |  | no |  |  | 2018-08-13 |  | 1 | 2018-08-16 | Done
1753 | Modern Acupuncture Alliance | E180814a | 2018-08-14 | Review existing information |  |  | no |  |  | 2018-08-22 |  |  | 2018-08-28 | Done
1733 | Nekter | E180814b | 2018-08-14 | Implement answers |  |  | no |  |  |  |  | 0.5 | 2018-08-14 | Done
1746 | Xpress Wellness Liberal KS | E180812a | 2018-08-12 | Base files. | See instructions in email |  | no |  |  |  |  | 2 | 2018-10-01 | Done
1733 | Nekter | E180813c | 2018-08-14 | Contact building owner for coordination |  |  | no | [5 empty] | 2018-08-16 | Done
1670 | Brookhaven Generator | E180814c | 2018-08-14 | Bid Notice | Meeting on 8/29 |  | no |  | 2018-08-29 | 2018-08-29 | 3 | 3 | 2018-08-30 | Done
1672 | FBC Watauga - Phase 1 | E180815a | 2018-08-15 | LTG RE-sbumittal |  |  | no |  |  | 2018-08-15 |  | 0.5 | 2018-08-15 | Done
1707 | Ryan Schools | E180815b | 2018-08-15 | OSFM Letters |  |  | no |  |  | 2018-08-15 |  | 1 | 2018-08-15 | Done
1530 | Brennan Drop-off Changes | E180815c | 2018-08-15 | Addendum items | Applies to all DO stations | Didn't happen | no | [5 empty] | 2018-10-15 | Done
1733 | Nekter | E180816a | 2018-08-16 | MP Sheets |  |  | no |  |  | 2018-08-16 |  | 1 | 2018-08-16 | Done
1733 | Nekter |  | 2018-08-16 | LTG |  |  | no |  |  |  |  | 4 | 2018-08-16 | Done
1733 | Nekter |  | 2018-08-16 | PWR and Riser |  |  | no |  |  |  |  | 4 | 2018-08-16 | Done
1733 | Nekter |  | 2018-08-16 | KIT |  |  | billed |  |  |  |  | 4 | 2018-08-16 | Done
1614 | Euless Library | E180816b | 2018-08-16 | Meeting at OWT | Time: 9AM |  | no |  | 2018-08-21 | 2018-08-27 |  | 2 | 2018-08-27 | Done
1614 | Euless Library | E180816b | 2018-08-16 | Prepare for meeting. Update base files |  |  | no |  |  | 2018-08-20 |  |  | 2018-09-04 | Done
1693 | The Table Church |  | 2018-08-16 | Power |  |  | no |  |  |  |  | 2 | 2018-08-20 | Done
1744 | Viandant Gelato Store - Denton | E180815d | 2018-08-17 | Site Visit | Time: 10 AM in Gainsville |  | billed |  | 2018-08-22 | 2018-08-22 | 3 | 2 | 2018-08-24 | Done
1754 | Viandant Gelato Store - Gainsville | E180815d | 2018-08-17 | Site Visit | Time: 10 AM in Gainsville |  | billed |  | 2018-08-22 | 2018-08-22 | 3 | 2 | 2018-08-24 | Done
1753 | Modern Acupuncture Alliance | E180817a | 2018-08-23 | Project Files |  |  | no | [5 empty] | 2018-08-28 | Done
1733 | Nekter | E180819a | 2018-08-23 | Additional information | Assess |  | no |  |  |  |  | 1 | 2018-08-25 | Done
1738 | Rudys Power Monitor | E180819b | 2018-08-23 | Talk to Larry | See additional pictures |  | no |  |  | 2018-08-23 |  | 0.5 | 2018-09-04 | Done
1736 | Varsity Orthopedics at Heritage Glen | E180819c | 2018-08-23 | Architects comments | See email for comments |  | no |  |  | 2018-08-23 |  | 2 | 2018-08-23 | Done
1672 | FBC Watauga - Phase 1 | E180820a | 2018-08-23 | Submittal | By noon on 8/23 |  | billed |  | 2018-08-23 | 2018-08-23 |  | 1 | 2018-08-23 | Done
mkt | Marketing | E180821a | 2018-08-23 | Resume for Kerr 3 |  |  | no |  | 2018-08-23 |  |  |  | 2018-08-27 | Done
1733 | Nekter | E180821b | 2018-08-23 | Water filter needs power? |  |  | no |  |  |  |  | 1 | 2018-08-25 | Done
1733 | Nekter | E180822a | 2018-08-23 | Comments | See email for comments |  | no |  |  | 2018-08-23 |  | 1 | 2018-08-25 | Done
1614 | Euless Library | E180821c | 2018-08-23 | Schedule information | Add dates to calendar |  | no |  |  | 2018-08-23 |  |  | 2018-09-04 | Done
1755 | Decatur MOB | E180821c | 2018-08-23 | Process estimate |  |  | no |  |  |  |  | 0.5 | 2018-08-30 | Done
1746 | Xpress Wellness Liberal KS | E180817b | 2018-08-23 | Updated set |  |  | no |  |  |  |  | 0 | 2018-10-01 | Done
1477 | Eugene McCray Recreation Center | E180822b | 2018-08-23 | Fire Sprinkler submittal | Not mine |  | no | [5 empty] | 2018-08-23 | Done
1421 | KXAS Remodel | E180822c | 2018-08-23 | Gate Operatior Eval | Evaulate for power |  | no |  |  | 2018-08-23 |  |  | 2018-08-28 | Done
1733 | Nekter | E180822d | 2018-08-23 | Add plan with room names |  |  | no |  |  | 2018-08-23 |  | 1 | 2018-08-25 | Done
1744 | Viandant Gelato Store - Denton | E180822e | 2018-08-23 | Prepare for site visit |  |  | no |  |  | 2018-08-23 |  | 0.5 | 2018-08-24 | Done
1754 | Viandant Gelato Store - Gainsville | E180822e | 2018-08-23 | Prepare for site visit |  |  | no |  |  | 2018-08-23 |  | 0.5 | 2018-08-24 | Done
1746 | Xpress Wellness Liberal KS | E180822f | 2018-08-23 | Schedule information | Add new projects |  | no | [5 empty] | 2018-10-01 | Done
1478 | Handley Meadowbrook Rec Center | E180822g | 2018-08-23 | Transformer pad issue |  |  | no |  | 2018-08-23 | 2018-08-23 |  | 0.5 | 2018-08-23 | Done
1736 | Varsity Orthopedics at Heritage Glen | E180822h | 2018-08-23 | X-Ray information |  |  | no |  |  | 2018-08-23 |  | 2 | 2018-08-23 | Done
ops | Operations | E180823a | 2018-08-23 | AutoCAD webinar | Not attended |  | no |  | 2018-08-28 | 2018-08-28 | 1 |  | 2018-08-28 | Done
1733 | Nekter | E180823b | 2018-08-23 | Health Dept Reqs |  |  | no |  |  | 2018-08-23 |  | 1 | 2018-08-25 | Done
1614 | Euless Library | E180824a | 2018-08-24 | Meeting at OWT |  |  | no |  |  | 2018-08-27 | 3 | 2 | 2018-08-27 | Done
1693 | The Table Church | E180824b | 2018-08-24 | AVL information |  | Next issue | no |  |  |  |  | 3 | 2018-10-10 | Done
1736 | Varsity Orthopedics at Heritage Glen |  | 2018-08-26 | Final QC |  |  | billed |  |  |  |  | 2 | 2018-08-26 | Done
1753 | Modern Acupuncture Alliance | E180827a | 2018-08-27 | Update base file |  |  | no |  |  | 2018-08-27 |  | 0.5 | 2018-08-27 | Done
1756 | Brazilian Joes | E180827b | 2018-08-27 | Proposal |  |  | no |  |  | 2018-08-27 |  | 0.5 | 2018-08-27 | Done
1746 | Xpress Wellness Liberal KS | E180827c | 2018-08-27 | New Proposal |  |  | no |  |  |  |  | 0.5 | 2018-08-27 | Done
1757 | Blo Blow Dry Bar - Preston Village | E180827d | 2018-08-27 | Proposal |  |  | no |  |  | 2018-08-28 |  | 0.5 | 2018-08-29 | Done
1753 | Modern Acupuncture Alliance |  | 2018-08-27 | LTG COMCheck |  |  | no |  |  | 2018-08-28 |  | 1 | 2018-08-28 | Done
1753 | Modern Acupuncture Alliance |  | 2018-08-27 | PWR MP sheets |  |  | no |  |  | 2018-08-28 |  | 1 | 2018-08-28 | Done
1614 | Euless Library | E180827e | 2018-08-27 | Update Revit file |  |  | no | [5 empty] | 2018-09-04 | Done
1753 | Modern Acupuncture Alliance |  | 2018-08-28 | IFR QC |  |  | no |  |  | 2018-08-28 |  | 2 | 2018-08-28 | Done
1736 | Varsity Orthopedics at Heritage Glen | E180828b | 2018-08-28 | Letter sized COMCheck |  |  | no |  |  | 2018-08-28 |  | 0.5 | 2018-08-28 | Done
1614 | Euless Library | E180828d | 2018-08-28 | Underfloor conduit instructions | Needs QC |  | no | PWR |  | 2018-08-29 |  | 3 | 2018-09-08 | Done
1672 | FBC Watauga - Phase 1 | E180829a | 2018-08-29 | X2 fixture substitute | Due to delivery dates |  | no |  |  |  |  | 0.5 | 2018-08-29 | Done
1753 | Modern Acupuncture Alliance | E180829b | 2018-08-29 | Final Comments | IFC |  | billed |  | 2018-08-29 | 2018-08-29 |  | 1 | 2018-08-29 | Done
1614 | Euless Library | E180829c | 2018-08-30 | Coordinate with Jim Morrow |  |  | no | LTG |  | 2018-09-04 |  | 1 | 2018-09-05 | Done
1757 | Blo Blow Dry Bar - Preston Village |  | 2018-08-30 | Review Documents | get question list |  | no |  |  | 2018-08-30 |  | 2 | 2018-09-13 | Done
1759 | KHSH-Keller-Haslet Restaurant Shell | E180828e | 2018-08-30 | Proposal |  |  | no |  |  |  |  | 0.5 | 2018-08-30 | Done
1544 | The Community At Lake Ridge | E180829d | 2018-08-29 | Photometrics |  |  | no |  |  | 2018-08-30 |  | 1 | 2018-08-30 | Done
1734 | The Joint - Quail Springs | E180829e | 2018-08-30 | Revision 1 |  |  | no |  |  | 2018-08-30 |  | 2 | 2018-08-30 | Done
1670 | Brookhaven Generator | E180830a | 2018-08-30 | Process questions |  |  | no |  | 2018-08-31 | 2018-08-31 |  | 2 | 2018-08-31 | Done
1746 | Xpress Wellness Liberal KS |  | 2018-08-30 | 95% IFR due | See email for rest of schedule |  | billed |  | 2018-09-19 | 2018-09-15 |  |  | 2018-10-01 | Done
1614 | Euless Library | E180830c | 2018-08-30 | Motorized shades | Needs QC - Controls: wireless and hardwired |  | no | PWR |  | 2018-08-31 |  | 1 | 2018-09-08 | Done
1614 | Euless Library | E180831a | 2018-08-31 | Lighting changes | 3 emails: Type Z1 to Z4 plus… |  | no | LTG |  | 2018-08-31 |  | 4 | 2018-09-06 | Done
1614 | Euless Library | E180904a | 2018-09-04 | P fixtures in Youth area |  |  | no | LTG |  | 2018-09-04 |  |  | 2018-09-06 | Done
1614 | Euless Library | E180904b | 2018-09-04 | Update Revit model |  |  | no |  |  |  |  | 0.5 | 2018-09-05 | Done
1614 | Euless Library | E180901a | 2018-09-04 | Ltg Information from Jim Morrow | There are conflicts with Leslies |  | no | LTG |  |  |  |  | 2018-09-06 | Done
ops | Operations | E180904c | 2018-09-04 | NCTRCA Renewal |  |  | no |  |  | 2018-09-05 |  | 1 | 2018-09-18 | Done
1757 | Blo Blow Dry Bar - Preston Village | E180827d | 2018-09-04 | Answers to questions | See email |  | no |  |  |  |  | 2 | 2018-09-13 | Done
1757 | Blo Blow Dry Bar - Preston Village | E180904d | 2018-09-04 | Power information | See email |  | no |  |  |  |  | 2 | 2018-09-13 | Done
1746 | Xpress Wellness Liberal KS | E180904e | 2018-09-04 | Updatd Project files |  |  | no | [5 empty] | 2018-10-01 | Done
1738 | Rudys Power Monitor | E180904f | 2018-09-04 | Need cut sheets | Left over |  | no | [5 empty] | 2018-10-04 | Done
1592 | Deer Park Animal Shelter | E180904g | 2018-09-04 | Load Analysis |  |  | no |  |  |  |  | 0.5 | 2018-09-04 | Done
1614 | Euless Library |  | 2018-09-04 | Add Cable Trays |  |  | no | PWR |  |  |  | 1 | 2018-09-12 | Done
1693 | The Table Church |  |  | Project work |  |  | billed | [5 empty] | 2018-08-15 | Done
1733 | Nekter |  |  | Project work |  |  | billed | [5 empty] | 2018-08-15 | Done
1614 | Euless Library | E180905a | 2018-09-05 | Donor Plaque lighting | Type DP |  | no | LTG |  |  |  | 1 | 2018-09-11 | Done
1614 | Euless Library |  | 2018-09-06 | LTG Canopy options |  |  | no | LTG |  |  |  | 1 | 2018-09-12 | Done
1614 | Euless Library | E180906a | 2018-09-06 | Final RCP |  |  | no | LTG |  |  |  | 3 | 2018-09-06 | Done
1544 | The Community At Lake Ridge | E180906c | 2018-09-06 | Disconnect RFI |  |  | no |  |  |  |  | 0.5 | 2018-09-06 | Done
1583 | 7 City Church | E180907a | 2018-09-07 | VE items to submittals | Email contains accepted VE items |  | no |  |  | 2018-10-16 |  |  | 2018-10-16 | Done
1614 | Euless Library |  | 2018-09-07 | MP Sheets |  |  | no | PWR |  |  |  | 3 | 2018-09-11 | Done
1758 | The Joint - Amarillo |  | 2018-09-10 | Review Set |  |  | no |  |  |  |  | 3 | 2018-09-10 | Done
1614 | Euless Library | E180910a | 2018-09-10 | Additional Reqs from Leslie |  |  | no | LTG |  |  |  | 1 | 2018-09-11 | Done
1614 | Euless Library | E180911a | 2018-09-11 | Final MP Sheets |  |  | no |  |  |  |  | 2 | 2018-09-12 | Done
1614 | Euless Library | E180911b | 2018-09-11 | Dyson Faucets |  |  | no |  |  |  |  | 1 | 2018-09-12 | Done
1614 | Euless Library | E180911c | 2018-09-11 | Architect's comments |  |  | no |  |  |  |  | 1 | 2018-09-12 | Done
1477 | Eugene McCray Recreation Center | E180911d | 2018-09-11 | Power changes | See email for instructions |  | billed |  |  | 2018-09-13 |  | 1 | 2018-09-14 | Done
1478 | Handley Meadowbrook Rec Center | E180911d | 2018-09-11 | Power changes | See email for instructions |  | billed |  |  | 2018-09-13 |  | 1 | 2018-09-14 | Done
1614 | Euless Library | E180912a | 2018-09-12 | Update Revit model |  |  | no |  |  |  |  | 1 | 2018-09-12 | Done
1544 | The Community At Lake Ridge |  | 2018-09-12 | Disconnect RFI |  |  | no |  |  |  |  | 1 | 2018-09-12 | Done
1614 | Euless Library | E180912b | 2018-09-12 | Concealed emergency fixture |  |  | no | Add 01 |  |  |  | 1 | 2018-10-04 | Done
1614 | Euless Library |  |  | IFC Work |  |  | no |  |  |  |  | 6 | 2018-09-10 | Done
1614 | Euless Library |  |  | IFC Work |  |  | no |  |  |  |  | 2 | 2018-09-11 | Done
1421 | KXAS Remodel | E180913a | 2018-09-13 | Lamp at gate plus door locks |  |  | billed | Rev09 |  | 2018-09-13 |  | 2 | 2018-09-17 | Done
1758 | The Joint - Amarillo | E180913b | 2018-09-13 | Lana's comments |  |  | billed | IFC |  | 2018-09-13 |  | 1 | 2018-09-13 | Done
1757 | Blo Blow Dry Bar - Preston Village |  | 2018-09-14 | IFC |  | Comments | billed |  |  |  |  | 1 | 2018-09-14 | Done
1761 | 130K SF Warehouse |  | 2018-09-14 | Proposal |  |  | no |  |  |  |  | 0.5 | 2018-09-14 | Done
1762 | Stonebridge MOB Shells |  | 2018-09-14 | Proposal |  |  | no |  |  |  |  | 0.5 | 2018-09-14 | Done
1763 | Long Prairie Road MOB Shell |  | 2018-09-14 | Proposal |  |  | no |  |  |  |  | 0.5 | 2018-09-14 | Done
1583 | 7 City Church | E180914a | 2018-09-17 | Rev 3 |  |  | no |  |  |  |  | 1 | 2018-09-17 | Done
1764 | FWTA Body Shop Addition | E180917a | 2018-09-17 | Proposal |  |  | no |  | 2018-09-18 |  |  | 0.5 | 2018-09-18 | Done
1583 | 7 City Church | E180914a | 2018-09-18 | Rev 4 |  |  | no |  |  |  |  | 0.5 | 2018-09-18 | Done
1544 | The Community At Lake Ridge | E180918a | 2018-09-18 | Revision 4 |  |  | billed | Rev 4 |  |  |  | 1 | 2018-09-18 | Done
1544 | The Community At Lake Ridge |  | 2018-09-18 | Add fixture F to RR 129 |  |  | no | Rev 4 |  |  |  |  | 2018-09-18 | Done
1765 | Xpress Wellness Altus OK |  | 2018-09-19 | IFR by 11/6? |  |  | no |  |  | 2018-11-02 |  |  | 2018-11-08 | Done
1477 | Eugene McCray Recreation Center | E180920a | 2018-09-20 |  |  |  | no |  |  |  |  | 0.5 | 2018-09-21 | Done
1478 | Handley Meadowbrook Rec Center | E180920b | 2018-09-20 |  |  |  | no |  |  |  |  | 0.5 | 2018-09-21 | Done
1581 | Crescent Schools | E180918b | 2018-09-20 | Phase 1 Schedule | Superceded | Schedule to come | no | [5 empty] | 2018-10-30 | Done
1581 | Crescent Schools | E180918b | 2018-09-20 | Phase 2 50% CD Due | Superceded | schedule | no | [5 empty] | 2018-10-30 | Done
1581 | Crescent Schools | E180918b | 2018-09-20 | Phase 2 95% CD Due | Superceded | schedule | no | [5 empty] | 2018-10-30 | Done
1746 | Xpress Wellness Liberal KS | E180918c | 2018-09-20 | Update project files |  |  | no | [5 empty] | 2018-10-08 | Done
1746 | Xpress Wellness Liberal KS | E180921a | 2018-09-21 | Add strobes and smoke detectors |  |  | no | IFC |  |  |  |  | 2018-10-01 | Done
1766 | Xpress Wellness Duncan OK | E180921b | 2018-09-21 | Proposal |  |  | no |  |  |  |  | 0.5 | 2018-09-21 | Done
1544 | The Community At Lake Ridge | E180921c | 2018-09-21 | LTG to Morrow for EM LTG |  |  | no |  |  |  |  | 0.5 | 2018-09-21 | Done
1746 | Xpress Wellness Liberal KS | E180921a | 2018-09-21 | Site Plan |  |  | no | [5 empty] | 2018-10-08 | Done
1421 | KXAS Remodel | E180925a | 2018-09-25 | Add receptacle to truck bay |  |  | billed | Rev 10 |  |  |  | 1 | 2018-10-10 | Done
1600 | Gun Experience | E180926a | 2018-09-26 | Update revit file |  |  | no | IFC |  |  |  | 1 | 2018-09-27 | Done
1600 | Gun Experience | E180927a | 2018-09-27 | MP Sheets |  |  | no | IFC |  |  |  | 1 | 2018-09-27 | Done
1600 | Gun Experience | E180924a | 2018-09-27 | VE markups |  |  | no | IFC |  |  |  | 4 | 2018-09-27 | Done
1767 | FW Forest Park Pool Shed | E180926b | 2018-09-27 | Proposal |  |  | no |  |  |  |  | 0.5 | 2018-09-27 | Done
1746 | Xpress Wellness Liberal KS | E180927b | 2018-09-28 | Counter mods |  |  | no | IFC |  |  |  | 1 | 2018-09-28 | Done
1746 | Xpress Wellness Liberal KS | E180918c | 2018-09-28 | Markups |  |  | no | IFC |  |  |  | 1 | 2018-09-28 | Done
1746 | Xpress Wellness Liberal KS | E180927c | 2018-09-28 | Floor plan update |  |  | no | IFC |  |  |  | 1 | 2018-09-28 | Done
1693 | The Table Church | E180928a | 2018-09-28 | DD comments |  |  | no |  |  |  |  | 2 | 2018-10-10 | Done
1733 | Nekter | E180928c | 2018-09-28 | Owner requirements |  |  | no | Rev 2 |  |  |  | 1 | 2018-09-28 | Done
1768 | NRGV Volleyball Facility Mansfield | E181001b | 2018-10-02 | Proposal |  |  | no |  | 2018-10-02 | 2018-10-02 |  | 1 | 2018-10-02 | Done
1769 | Coolgreens Restaurant | E180928d | 2018-10-02 | Proposal |  |  | no |  | 2018-10-02 | 2018-10-02 |  | 0.5 | 2018-10-02 | Done
1614 | Euless Library | E181001a | 2018-10-02 | Move sink |  |  | no | Add 01 | 2018-10-03 |  |  | 0.5 | 2018-10-03 | Done
1614 | Euless Library | p12-36 | 2018-10-02 | Implement EM ltg changes | In other tasks. |  | no |  | 2018-10-03 |  |  |  | 2018-10-03 | Done
1538 | UNT Coliseum Concourse | E181002c | 2018-10-02 | Review Closeout Documents |  |  | billed |  | 2018-10-20 |  |  | 1 | 2018-10-10 | Done
1770 | Lake Dallas Project | E181002b | 2018-10-02 | Proposal |  |  | no |  | 2018-10-02 | 2018-10-02 |  | 0.5 | 2018-10-02 | Done
1530 | Brennan Drop-off Changes | E181002c | 2018-10-02 | Card reader addition |  |  | no | Add 4 | 2018-10-15 |  |  | 1 | 2018-10-25 | Done
1531 | MLK Drop-off Changes | E181002c | 2018-10-02 | Card reader addition |  |  | no | Add 4 | 2018-10-15 |  |  | 1 | 2018-10-25 | Done
1532 | Old Hemphill Drop-off Changes | E181002c | 2018-10-02 | Card reader addition |  |  | no | Add 4 | 2018-10-15 |  |  | 1 | 2018-10-25 | Done
1614 | Euless Library | E181002d | 2018-10-02 | Remove note by M34 |  |  | no | Add 01 | 2018-10-03 |  |  | 0.5 | 2018-10-03 | Done
1614 | Euless Library | p12-36 | 2018-10-03 | Show 6 track heads |  |  | no | Add 01 |  |  |  | 0.5 | 2018-10-03 | Done
1614 | Euless Library |  | 2018-10-03 | Add HT to RTU-4, 5 and 6. 300W 120V | From phone conversation with Tim |  | no | Add 01 |  |  |  | 0.5 | 2018-10-03 | Done
1614 | Euless Library |  | 2018-10-03 | Delete EDH-3 |  |  | no | Add 01 |  |  |  | 0.5 | 2018-10-03 | Done
1614 | Euless Library |  | 2018-10-03 | Add REF-6A, 1/4HP 120V |  |  | no | Add 01 |  |  |  | 1 | 2018-10-03 | Done
1614 | Euless Library |  | 2018-10-03 | Add PHP-3 by AHU-3 1/4HP 120V |  |  | no | Add 01 |  |  |  | 1 | 2018-10-03 | Done
1614 | Euless Library |  | 2018-10-03 | Add VFD for REF-6A in RTU-6 |  |  | no | Add 01 |  |  |  | 1 | 2018-10-03 | Done
1614 | Euless Library |  | 2018-10-03 | Update CHP-1, WHP-1 and 2 | Npt necessary. Loads are very similar. |  | no | Add 01 |  |  |  | 0.5 | 2018-10-03 | Done
1614 | Euless Library |  | 2018-10-04 | Issue Addendum 2 |  |  | no | Add 01 |  |  |  | 3 | 2018-10-03 | Done
1614 | Euless Library | E181004b | 2018-10-04 | Add VFD to CHP-1 and WHP-1,2 |  |  | no | Add 02 |  |  |  | 1 | 2018-10-04 | Done
1692 | Celeris (2018) |  |  | September Projects |  |  | billed | [5 empty] | 2018-09-20 | Done
1771 | Argyle Public Works | E181004a | 2018-10-04 | Proposal |  |  | no |  |  |  |  | 0.5 | 2018-04-13 | Done
ops | Operations |  | 2018-10-04 | Invoicing |  |  | no |  |  |  |  | 2 | 2018-10-04 | Done
1614 | Euless Library | E181005a | 2018-10-05 | New Addendum issue date |  |  | no | Add 02 | 2018-10-08 |  |  |  | 2018-10-09 | Done
1746 | Xpress Wellness Liberal KS | E181005c | 2018-10-05 | Implement comments |  |  | no | IFC | 2018-10-09 |  |  | 5 | 2018-10-08 | Done
1746 | Xpress Wellness Liberal KS | E181005c | 2018-10-05 | IFC |  |  | no | IFC | 2018-10-09 |  |  | 1 | 2018-10-08 | Done
1746 | Xpress Wellness Liberal KS | E181005e | 2018-10-05 | Add CAD release to Specs |  |  | no | IFC | 2018-10-06 |  |  | 1 | 2018-10-05 | Done
ops | Operations | E181005e | 2018-10-05 | Add CAD release to Specs |  |  | no |  | 2018-10-06 |  |  |  | 2018-10-05 | Done
1746 | Xpress Wellness Liberal KS | E181005d | 2018-10-05 | Update RCP | See email for changes |  | no | IFC | 2018-10-06 |  |  | 1 | 2018-10-08 | Done
1744 | Viandant Gelato Store - Denton | E181005b | 2018-10-05 | Project files | Project in limbo | Equipment info | no |  |  | 2018-12-04 |  |  | 2019-01-07 | Done
1754 | Viandant Gelato Store - Gainsville | E181005b | 2018-10-05 | Project files | Superceded |  | no |  |  | 2018-10-31 |  |  | 2018-11-16 | Done
1705 | North Fort Worth Baptist Church | E181005f | 2018-10-05 | New Proposal | No email |  | no |  | 2018-10-08 | 2018-10-06 |  | 0.5 | 2018-10-08 | Done
1772 | COFW North Tri-Ethnic CC TAS | E181009a | 2018-10-09 | Proposal |  |  | no |  | 2018-10-10 |  |  | 0.5 | 2018-10-10 | Done
1773 | COFW Worth Heights Multi-purpose TAS | E181009a | 2018-10-09 | Proposal |  |  | no |  | 2018-10-10 |  |  | 0.5 | 2018-10-10 | Done
1745 | Mellow Mushroom Round Rock Electrical Diagnostics | E181009b | 2018-10-10 | Follow up on invoice payment |  |  | no |  |  | 2018-11-05 |  | 1 | 2018-10-30 | Done
1732 | City of Lake Worth Projects | E181010a | 2018-10-10 | Project Files | Information on email. |  | no |  |  | 2018-10-16 |  | 1 | 2018-10-25 | Done
1732 | City of Lake Worth Projects | E181010a | 2018-10-10 | Review DD Set |  |  | no |  | 2018-10-26 | 2018-10-20 |  | 1 | 2018-10-25 | Done
1693 | The Table Church | E181015a | 2018-10-15 | MP Sheets |  |  | no |  |  |  |  | 1 | 2018-10-15 | Done
1620 | City of Weatherford Service Center |  | 2018-10-15 | ASA Proposal |  |  | no |  |  |  |  | 0.5 | 2018-10-15 | Done
1774 | FWPL East Branch Restroom Renovations | E181015b | 2018-10-15 | Proposal |  |  | no |  |  | 2018-10-16 |  | 1 | 2018-10-17 | Done
1583 | 7 City Church | E181015c | 2018-10-15 | Panel Submittal |  |  | billed |  |  | 2018-10-16 |  | 1 | 2018-10-16 | Done
1775 | The Joint Norman OK | E181015d | 2018-10-15 | Project files |  |  | no |  |  | 2018-10-16 |  | 4 | 2018-10-19 | Done
1707 | Ryan Schools | E181010c | 2018-10-15 | Gear Submittal |  |  | billed |  |  | 2018-10-16 |  | 1 | 2018-10-16 | Done
1581 | Crescent Schools | E181011a | 2018-10-16 | Project is back on. | New Project Files |  | no |  |  | 2018-11-02 |  |  | 2018-11-01 | Done
1707 | Ryan Schools | E181011b | 2018-10-16 | LTG Submittal |  |  | billed |  |  | 2018-10-16 |  | 1 | 2018-10-16 | Done
1693 | The Table Church | E181017a | 2018-10-17 | Add PWR to sign |  |  | no | IFC |  |  |  | 0.5 | 2018-01-17 | Done
1693 | The Table Church | E181017b | 2018-10-17 | Check DD set for coordination | Superceded |  | no | IFC |  | 2018-12-03 |  |  | 2018-12-12 | Done
1421 | KXAS Remodel | E181016a | 2018-10-18 | Dog Area Proposal | See emaiil |  | no |  |  | 2018-10-19 |  | 1 | 2018-10-20 | Done
1583 | 7 City Church | E181016b | 2018-10-18 | LTG Submittal |  |  | billed |  |  | 2018-10-18 |  | 1 | 2018-10-22 | Done
1765 | Xpress Wellness Altus OK | E181017c | 2018-10-18 | North points down |  |  | no | IFC |  | 2018-11-02 |  |  | 2018-11-08 | Done
1732 | City of Lake Worth Projects | E181017d | 2018-10-18 | Answers to questions and file update | (2) emails |  | no | IFC |  |  |  | 1 | 2018-10-25 | Done
1770 | Lake Dallas Project |  | 2018-10-18 | Description |  |  | no |  |  |  |  | 1 | 2018-10-19 | Done
1775 | The Joint Norman OK | E181018a | 2018-10-18 | MP data | See email |  | no | IFC |  | 2018-10-19 |  | 1 | 2018-10-19 | Done
1592 | Deer Park Animal Shelter | E181018b | 2018-10-18 | LTG Controls CC | @10:30 AM |  | no |  | 2018-10-19 | 2018-10-19 | 2 | 2 | 2018-10-19 | Done
1724 | TDC Parking Phase 1 | E181018c | 2018-10-18 | Site Photometrics | See email |  | no |  | 2018-10-19 | 2018-10-19 | 2 | 2 | 2018-10-19 | Done
1775 | The Joint Norman OK |  | 2018-10-19 | IFR |  |  | no |  |  |  |  | 4 | 2018-10-15 | Done
1768 | NRGV Volleyball Facility Mansfield | E181021a | 2018-10-22 | Answers to questions |  |  | no | B |  | 2018-12-03 |  | 0.5 | 2018-12-07 | Done
1530 | Brennan Drop-off Changes | E181019c | 2018-10-22 | IT Additions |  |  | no | Add 4 |  | 2018-10-22 |  | 1 | 2018-10-25 | Done
1531 | MLK Drop-off Changes | E181019c | 2018-10-22 | IT Additions |  |  | no | Add 4 |  | 2018-10-22 |  | 1 | 2018-10-25 | Done
1532 | Old Hemphill Drop-off Changes | E181019c | 2018-10-22 | IT Additions |  |  | no | Add 4 |  | 2018-10-22 |  | 1 | 2018-10-25 | Done
1693 | The Table Church | E181019d | 2018-10-22 | Baptistry reqs |  |  | no |  |  | 2018-11-02 |  | 1 | 2018-11-07 | Done
1776 | ECC Eitz Chaim Church | E181022b | 2018-10-22 | Proposal |  |  | no |  |  |  |  | 1 | 2018-10-22 | Done
1717 | Greenbriar CC Reception Desk | E181023a | 2018-10-23 | Markups |  |  | no |  |  | 2018-10-31 |  | 2 | 2018-10-31 | Done
1530 | Brennan Drop-off Changes | E181024a | 2018-10-24 | 1'C for cameras and between admin and swap shop |  |  | no | Add 4 |  |  |  | 1 | 2018-10-25 | Done
1531 | MLK Drop-off Changes | E181024a | 2018-10-24 | 1'C for cameras and between admin and swap shop |  |  | no | Add 4 |  |  |  | 1 | 2018-10-25 | Done
1532 | Old Hemphill Drop-off Changes | E181024a | 2018-10-24 | 1'C for cameras and between admin and swap shop |  |  | no | Add 4 |  |  |  | 1 | 2018-10-25 | Done
1775 | The Joint Norman OK | E181024b | 2018-10-24 | Review Comments |  |  | no |  |  | 2018-10-24 |  | 2 | 2018-10-24 | Done
1732 | City of Lake Worth Projects |  | 2018-10-25 | DD work |  |  | no |  |  |  |  | 5 | 2018-10-25 | Done
1600 | Gun Experience | E181024c | 2018-10-26 | Revision 1 - City Comments |  |  | no | Rev01 | 2018-10-26 | 2018-10-26 |  | 2 | 2018-10-26 | Done
ops | Operations | E181023b | 2018-10-26 | Check ATG express tools |  | Next training | no | V02 |  | 2018-12-06 |  |  | 2018-12-03 | Done
1600 | Gun Experience | E181024d | 2018-10-26 | LTG Submittal |  |  | billed |  |  | 2018-10-29 |  | 1 | 2018-10-29 | Done
1754 | Viandant Gelato Store - Gainsville | E181023c | 2018-10-27 | Update CAD file | Superceded |  | no | IFC |  | 2018-10-31 |  |  | 2018-11-16 | Done
1754 | Viandant Gelato Store - Gainsville | E181023c | 2018-10-27 | Review equipment cutsheets |  |  | no | IFC |  | 2018-10-29 |  | 2 | 2018-10-30 | Done
1754 | Viandant Gelato Store - Gainsville | E181026a | 2018-10-27 | LTG cut sheets |  |  | no |  |  | 2018-10-29 |  | 1 | 2018-10-30 | Done
1768 | NRGV Volleyball Facility Mansfield | E181024f | 2018-10-27 | Review Photometrics |  |  | no |  |  | 2018-10-29 |  | 1 | 2018-10-30 | Done
1705 | North Fort Worth Baptist Church | E181025a | 2018-10-27 | AVL information | Superseeded. See E181212e |  | no |  |  | 2019-02-14 | 3 |  | 2019-02-18 | Done
1705 | North Fort Worth Baptist Church | E181025b | 2018-10-27 | 50% DD set | See schedule. Narrative only |  | billed |  | 2018-11-16 | 2018-11-15 |  | 2 | 2018-11-15 | Done
1768 | NRGV Volleyball Facility Mansfield | E181023d | 2018-10-27 | Fixture information. | Assess with photo. Talk to Morrow |  | no | b |  | 2018-12-03 |  | 0.5 | 2018-12-07 | Done
1754 | Viandant Gelato Store - Gainsville | E181027a | 2018-10-27 | Updated CAD files + plumbing | Project in limbo |  | no |  |  | 2018-12-04 |  |  | 2018-12-20 | Done
1581 | Crescent Schools | E181029b | 2018-10-29 | Design Site Visit |  |  | billed |  |  | 2018-11-01 | 8 | 8 | 2018-11-01 | Done
1717 | Greenbriar CC Reception Desk | E181029a | 2018-10-29 | Final instructions |  |  | billed |  |  | 2018-10-31 |  | 1 | 2018-10-31 | Done
1746 | Xpress Wellness Liberal KS | E181030a | 2018-10-30 | Addendum 2 |  |  | no |  |  | 2018-10-31 |  | 1 | 2018-10-31 | Done
1592 | Deer Park Animal Shelter | E181031a | 2018-10-31 | Change order assessment |  |  | no |  |  | 2018-10-31 |  | 1 | 2018-10-31 | Done
1581 | Crescent Schools |  | 2018-10-31 | Prepare for SV |  |  | no |  |  | 2018-10-31 |  | 0.5 | 2018-10-31 | Done
1768 | NRGV Volleyball Facility Mansfield |  | 2018-10-31 | Assess info |  |  | no | b |  | 2018-12-03 |  | 1 | 2018-12-07 | Done
1777 | BALKO Cafeteria Changes | E181031b | 2018-10-31 | Proposal | Email has info |  | no |  |  | 2018-11-02 |  | 0.5 | 2018-11-02 | Done
1620 | City of Weatherford Service Center | E181031c | 2018-10-31 | Changes accepted |  |  | no |  |  | 2018-11-02 |  | 2 | 2018-11-08 | Done
1544 | The Community At Lake Ridge | E181101a | 2018-11-02 | RFI 60 |  |  | no |  |  |  |  | 1 | 2018-11-02 | Done
1732 | City of Lake Worth Projects | E181105a | 2018-11-05 | Card reader information | Implemented with gates |  | no | IFC |  | 2018-12-03 |  |  | 2019-01-07 | Done
1693 | The Table Church | E181031d | 2018-11-05 | Update Revit file |  |  | no |  |  | 2018-11-05 |  | 2 | 2018-11-07 | Done
1620 | City of Weatherford Service Center | E181031c | 2018-11-05 | Update base files |  |  | no |  |  |  |  | 1 | 2018-11-08 | Done
1544 | The Community At Lake Ridge | E181105b | 2018-11-05 | Pole outlet (277 to 120V issue) | Resolved |  | no |  |  | 2018-11-19 |  |  | 2018-12-03 | Done
1705 | North Fort Worth Baptist Church | E181105e | 2018-11-05 | Design Site Visit | 11/9 @ 10 AM |  | billed |  | 2018-11-09 | 2018-11-09 | 3 | 2 | 2018-11-09 | Done
1581 | Crescent Schools | E181105f | 2018-11-05 | Coordinate new transformer | See email |  | no |  |  | 2018-11-16 |  | 2 | 2018-11-17 | Done
ops | Operations | E181105g | 2018-11-05 | Pay Autodesk subscription |  |  | no |  |  |  |  | 0.5 | 2018-11-10 | Done
1544 | The Community At Lake Ridge | E181107b | 2018-11-07 | RFI 062 | Add type N fixture? |  | no | REV |  |  |  | 1 | 2018-11-07 | Done
1544 | The Community At Lake Ridge | E181107c | 2018-11-07 | RFI 064 | Remove hand dryers |  | no | REV |  |  |  | 1 | 2018-11-07 | Done
1693 | The Table Church |  | 2018-11-08 | Resolve backstage dimming | Need schematic |  | no | B |  | 2018-12-03 |  | 0.5 | 2018-12-04 | Done
1693 | The Table Church | e181105G | 2018-11-08 | Receptacles in the building |  |  | no |  |  |  |  | 3 | 2018-11-07 | Done
1693 | The Table Church |  | 2018-11-08 | Resolve soffit power outlets | Both corners |  | no | B |  | 2018-12-03 |  | 0.5 | 2018-12-14 | Done
1544 | The Community At Lake Ridge | E181107c | 2018-11-08 | Outlet revision |  |  | no |  |  |  |  | 3 | 2018-11-08 | Done
1781 | GRACE Revolution | E181109a | 2018-11-09 | Proposal |  |  | no |  |  |  |  | 0.5 | 2018-11-09 | Done
1581 | Crescent Schools | E181019a | 2018-11-10 | Demolition Package Deadline |  |  | billed | DEMO | 2018-11-19 | 2018-11-16 |  | 8 | 2018-11-20 | Done
ops | Operations | E181105h | 2018-11-10 | Renew AutoCAD |  |  | no |  |  |  |  | 0.5 | 2018-11-10 | Done
1746 | Xpress Wellness Liberal KS | E181107d | 2018-11-10 | City Comments | Need to talk to Tim |  | no |  |  | 2018-11-12 |  | 0.5 | 2018-11-10 | Done
1768 | NRGV Volleyball Facility Mansfield | E181107e | 2018-11-10 | Answers to Qs and updated file |  |  | no | b |  | 2018-12-03 | 1 | 1 | 2018-12-07 | Done
1768 | NRGV Volleyball Facility Mansfield | E181107f | 2018-11-10 | Review email information |  |  | no | b |  | 2018-12-03 | 1 | 1 | 2018-12-07 | Done
1768 | NRGV Volleyball Facility Mansfield | E181106a | 2018-11-10 | Follow up with Randy on LTG |  |  | no | b |  | 2018-12-03 |  | 1 | 2018-12-07 | Done
1583 | 7 City Church | E181108a | 2018-11-10 | ONCOR Form |  |  | no |  |  | 2018-11-12 |  | 1 | 2018-11-13 | Done
1583 | 7 City Church | E181108b | 2018-11-10 | LTG Controls Submittal |  |  | billed |  |  | 2018-11-12 |  | 1 | 2018-11-13 | Done
1600 | Gun Experience | E181112a | 2018-11-13 | Submittal |  |  | billed |  |  | 2018-11-16 |  | 3 | 2018-11-16 | Done
1581 | Crescent Schools | E181113a | 2018-11-13 | Project Files |  |  | no |  |  | 2018-11-16 |  | 2 | 2018-11-17 | Done
1544 | The Community At Lake Ridge | E181114a | 2018-11-14 | FA Submittal |  |  | billed |  |  | 2018-11-16 |  | 1 | 2018-11-16 | Done
1581 | Crescent Schools |  | 2018-11-16 | Add detailing |  |  | no |  |  | 2018-11-16 |  | 3 | 2018-11-17 | Done
1581 | Crescent Schools | E181116a | 2018-11-16 | Specs |  |  | no |  |  | 2018-11-16 |  | 2 | 2018-11-17 | Done
1705 | North Fort Worth Baptist Church | E181116b | 2018-11-19 | DD Set due |  |  | no |  | 2018-12-14 | 2018-12-11 |  | 6 | 2018-12-14 | Done
1600 | Gun Experience | E181116c | 2018-11-19 | Fixture K submittal | Requires arch approval |  | no |  |  | 2018-11-20 |  |  | 2018-11-20 | Done
1544 | The Community At Lake Ridge | E181116d | 2018-11-19 | LTG Control Submittal |  |  | billed |  |  | 2018-11-20 |  | 1 | 2018-11-20 | Done
1693 | The Table Church | E181116e | 2018-11-19 | LTG final coordination |  |  | no | B |  | 2018-12-03 |  | 1 | 2018-12-04 | Done
1772 | COFW North Tri-Ethnic CC TAS | E181009a | 2018-11-20 | Revise proposal to new info |  |  | no |  |  | 2018-11-21 |  | 1 | 2018-11-26 | Done
1773 | COFW Worth Heights Multi-purpose TAS | E181009a | 2018-11-20 | Revise proposal to new info |  |  | no |  |  | 2018-11-21 |  | 1 | 2018-11-26 | Done
1758 | The Joint - Amarillo | E181120a | 2018-11-20 | Final comments |  |  | billed | IFC |  | 2018-11-20 |  | 1 | 2018-11-20 | Done
1583 | 7 City Church | E181120b | 2018-11-20 | Raceway submittal |  |  | billed | A |  | 2018-12-03 |  | 1 | 2018-11-20 | Done
1693 | The Table Church | E181121a | 2018-11-21 | Update model |  |  | no | B |  | 2018-12-03 |  | 0.5 | 2018-12-04 | Done
1693 | The Table Church | E181121a | 2018-11-21 | Address comments |  |  | no | B |  | 2018-12-03 |  | 1 | 2018-12-04 | Done
1768 | NRGV Volleyball Facility Mansfield | E181126a | 2018-11-26 | Coordination Meeting | Week of 12/3. 11/18 @ 10 AM if possible |  | no | B | 2018-12-03 | 2018-12-03 |  | 1 | 2018-12-07 | Done
1782 | AETIO Biotherapy | E181126b | 2018-11-27 | Proposal |  |  | no |  |  | 2018-11-27 |  | 0.5 | 2018-11-28 | Done
1583 | 7 City Church | E181127a | 2018-11-27 | Rev 5 |  |  | no |  | 2018-11-27 | 2018-11-27 |  | 1 | 2018-11-27 | Done
1777 | BALKO Cafeteria Changes | E181128a | 2018-11-28 | Project Files | Set up whenever time allows |  | no |  |  | 2019-01-30 | 2 |  | 2019-02-10 | Done
1693 | The Table Church | T181127 | 2018-11-28 | Specs |  |  | no | B |  | 2018-12-03 |  | 1 | 2018-12-05 | Done
1779 | MEL5K Melissa 5.3K SF Shell | T181127 | 2018-11-28 | Project Files |  |  | no |  |  | 2018-12-04 |  |  | 2019-01-07 | Done
1768 | NRGV Volleyball Facility Mansfield | E181127b | 2018-11-28 | LTG Cut sheets form Morrow |  |  | no | B |  | 2018-12-03 |  | 1 | 2018-12-07 | Done
1783 | CLEBRV Cleburne RV | E181128c | 2018-11-28 | Proposal | Seep12-53 |  | no | A |  | 2018-12-03 |  | 0.5 | 2018-12-03 | Done
1693 | The Table Church | E181112b | 2018-11-28 | Follow up on AVL Qs |  |  | no | B |  | 2018-12-03 |  | 0.5 | 2018-12-04 | Done
1765 | Xpress Wellness Altus OK | E181127c | 2018-11-28 | Submittal |  |  | no | A |  | 2018-12-03 |  | 1 | 2018-12-03 | Done
1707 | Ryan Schools | E181128d | 2018-11-28 | PWR Submittal | Duplicate review. Sent original back |  | no | A |  | 2018-12-03 |  | 0.5 | 2018-12-03 | Done
1717 | Greenbriar CC Reception Desk | E181128e | 2018-11-28 | Finish Project |  |  | billed | IFC |  | 2018-12-03 |  | 0.5 | 2018-12-03 | Done
ops | Operations | E181127e | 2018-11-30 | Renew NM License |  |  | no |  |  | 2018-12-10 |  | 0.5 | 2018-12-09 | Done
ops | Operations |  | 2018-11-30 | PDHs |  |  | no | C |  | 2018-12-03 |  | 8 | 2018-12-09 | Done
1732 | City of Lake Worth Projects | E181128f | 2018-11-30 | Comments | Add a note about pole |  | no | A |  | 2018-12-03 |  | 0.5 | 2018-12-03 | Done
1777 | BALKO Cafeteria Changes |  | 2018-11-30 | Site Visit |  |  | billed |  |  | 2018-11-29 | 12 | 12 | 2018-11-29 | Done
1768 | NRGV Volleyball Facility Mansfield | E181129a | 2018-11-30 | Additional layouts |  |  | no | B |  | 2018-12-03 |  | 1 | 2018-12-07 | Done
1784 | ITPWR DCCCD IT Closet Upgrades | E181130a | 2018-11-30 | Proposals |  |  | no |  |  | 2018-12-05 |  | 1 | 2018-12-13 | Done
1544 | The Community At Lake Ridge | E181129b | 2018-11-30 | RFI 78 |  |  | no |  |  |  |  | 0.5 | 2018-11-30 | Done
1583 | 7 City Church | E181129c | 2018-11-30 | Q regarding X2x1 fixture |  |  | no |  |  |  |  | 0.5 | 2018-11-30 | Done
1765 | Xpress Wellness Altus OK | E181130b | 2018-11-30 | Submittal | Duplicate. |  | no | A |  | 2018-12-03 |  | 0 | 2018-12-03 | Done
1693 | The Table Church | E181112b | 2018-11-30 | Follow up on Qs | See DMX issue. |  | no | B |  | 2018-12-03 |  | 1 | 2018-12-04 | Done
1581 | Crescent Schools | E181130c | 2018-11-30 | Review set due | Postponed |  | no |  | 2018-12-14 | 2018-12-13 |  |  | 2018-12-13 | Done
1786 | OFF Office Addition | E181201a | 2018-12-01 | Proposal | Waiting for answers |  | no | A |  | 2018-12-04 |  | 0.5 | 2018-12-05 | Done
1732 | City of Lake Worth Projects | E181128f | 2018-11-30 | Comments | Implement comments |  | no |  |  | 2018-12-05 |  | 0.5 | 2018-12-05 | Done
1732 | City of Lake Worth Projects | E181203a | 2018-12-03 | New pole location |  |  | no |  |  | 2018-12-03 |  | 0.5 | 2018-12-03 | Done
1693 | The Table Church | E181203b | 2018-12-03 | Final instructions |  |  | no |  |  | 2018-12-03 |  | 1 | 2018-12-04 | Done
1693 | The Table Church | E181203c | 2018-12-04 | Final decision on type D fixtures |  |  | no |  |  | 2018-12-04 |  | 1 | 2018-12-04 | Done
1693 | The Table Church |  | 2018-12-04 | Resolve the DMX compatibility issue |  |  | no |  |  | 2018-12-04 |  | 1 | 2018-12-04 | Done
1693 | The Table Church |  | 2018-12-04 | MP Sheets |  |  | no |  |  | 2018-12-04 |  | 1 | 2018-12-04 | Done
1732 | City of Lake Worth Projects | E181205a | 2018-12-05 | Updated plans |  |  | no |  |  |  |  | 0.5 | 2018-12-12 | Done
1693 | The Table Church |  | 2018-12-05 | IFC |  |  | billed |  |  |  |  | 3 | 2018-12-05 | Done
1692 | Celeris (2018) |  | 2018-11-30 | Celeris Projects |  |  | billed |  |  |  |  | 2 | 2018-11-15 | Done
1788 | HONDA Denton | E181206a | 2018-12-06 | Proposal |  |  | no |  |  |  |  | 0.5 | 2018-12-06 | Done
1789 | TJTR - The Joint Timber Ridge | E181206b | 2018-12-06 | Existing plans | Plans show shell info. OK. |  | no |  |  |  |  | 0.5 | 2018-12-06 | Done
1787 | MANS Mansfield Shell | E181205b | 2018-12-06 | Proposal |  |  | no |  |  |  |  | 0.5 | 2018-12-05 | Done
1768 | NRGV Volleyball Facility Mansfield | E181205c | 2018-12-06 | New Site plan | Courts relocated. Asked for a meeting |  | no |  |  |  |  | 0.5 | 2018-12-06 | Done
1705 | North Fort Worth Baptist Church | E181205d | 2018-12-06 | AVL requirements | Provided | Design | no | [5 empty] | 2019-01-07 | Done
1693 | The Table Church | E181112b | 2018-12-06 | Lighting controls revision | Waiting for revision instructions. Didn't happen |  | no |  |  |  | 2 |  | 2019-02-12 | Done
1779 | MEL5K Melissa 5.3K SF Shell | E181206f | 2018-12-06 | Coordinate with utility. | Civil is taking care of it.Need gas/electric |  | no | [5 empty] | 2018-12-12 | Done
1705 | North Fort Worth Baptist Church | E181206g | 2018-12-06 | Update Revit file | Set up project |  | no |  |  | 2018-12-07 |  | 3 | 2018-02-10 | Done
1600 | Gun Experience | E181207a | 2018-12-07 | New type A-1 fixture | 1/28 Item closed. Will reopen when needed. 12/7 Jim Tharp called. Wait for instructions for upcoming revision. | Jim's instructions | no | [5 empty] | 2019-01-28 | Done
1781 | GRACE Revolution | E181207b | 2018-12-10 | Site Visit |  |  | billed |  | 2018-12-17 | 2018-12-17 |  | 4 | 2018-12-17 | Done
1581 | Crescent Schools | E181207c | 2018-12-10 | Project Files | Set project up |  | no | [5 empty] | 2019-01-03 | Done
1779 | MEL5K Melissa 5.3K SF Shell | E181210a | 2018-12-10 | Project Files | Set project up |  | no |  |  |  |  | 2 | 2018-12-11 | Done
1768 | NRGV Volleyball Facility Mansfield | E181210b | 2018-12-10 | Updated photometrics from Morrow | No action needed. |  | no | [5 empty] | 2018-12-10 | Done
1705 | North Fort Worth Baptist Church |  | 2018-12-11 | DD LTG |  |  | no |  |  | 2018-12-11 |  | 2 | 2018-12-12 | Done
1705 | North Fort Worth Baptist Church |  | 2018-12-11 | DD PWR |  |  | no |  |  | 2018-12-11 |  | 2 | 2018-12-12 | Done
1705 | North Fort Worth Baptist Church |  | 2018-12-11 | DD OL |  |  | no |  |  | 2019-02-14 | 2 | 2 | 2019-02-25 | Done
1544 | The Community At Lake Ridge | E181211a | 2018-12-11 | Reply to RFI078 |  |  | no |  |  |  |  | 0.5 | 2018-12-11 | Done
1600 | Gun Experience | E181211b | 2018-12-11 | Floor box submittal |  |  | no |  |  |  |  | 0.5 | 2018-12-11 | Done
1620 | City of Weatherford Service Center | E181211c | 2018-12-11 | IFC |  |  | billed |  |  |  |  | 1 | 2018-12-11 | Done
1733 | Nekter | E181211d | 2018-12-11 | Scoop machine changes | Waiting for Lana's clarification. Didn't happen | Lana's clarifications | no | [5 empty] | 2019-02-12 | Done
1766 | Xpress Wellness Duncan OK | E181211e | 2018-12-11 | NTP |  |  | no | [5 empty] | 2018-12-11 | Done
1705 | North Fort Worth Baptist Church | E181211f | 2018-12-11 | AVL requirements | Redundant |  | no | [5 empty] | 2019-01-07 | Done
1732 | City of Lake Worth Projects | E181212a | 2018-12-12 | Comments/IFC |  |  | billed |  | 2018-12-14 |  |  | 6 | 2018-12-12 | Done
1581 | Crescent Schools | E181212c | 2018-12-12 | Addendum 1 |  |  | no |  |  |  |  | 1 | 2018-12-12 | Done
1784 | ITPWR DCCCD IT Closet Upgrades | E181212d | 2018-12-12 | Proposal |  |  | no |  | 2018-12-12 | 2018-12-12 |  |  | 2018-12-13 | Done
1785 | RCIT Richland College IT Closets | E181212d | 2018-12-12 | Proposal | Included in 1784 |  | no |  | 2018-12-12 | 2018-12-12 |  |  | 2018-12-13 | Done
1705 | North Fort Worth Baptist Church | E181212e | 2018-12-12 | Updated AVL Set | Superseded |  | no |  |  | 2019-02-14 | 2 |  | 2019-03-16 | Done
1789 | TJTR - The Joint Timber Ridge | E181212f | 2018-12-12 | Comments/IFC |  |  | billed |  | 2018-12-13 | 2018-12-12 |  | 1 | 2018-12-13 | Done
1581 | Crescent Schools | E181212g | 2018-12-12 | IFR due |  |  | no |  | 2019-01-03 |  |  |  | 2019-01-03 | Done
1581 | Crescent Schools | E181212g | 2018-12-12 | IFC due |  |  | no |  | 2019-02-15 | 2019-02-15 | 3 |  | 2019-02-28 | Done
1693 | The Table Church | E181212h | 2018-12-12 | RFI 1 |  |  | no |  |  |  |  | 1 | 2018-12-12 | Done
1692 | Celeris (2018) |  | 2018-12-12 | Project |  |  | billed |  |  |  |  | 0.5 | 2018-12-12 | Done
1705 | North Fort Worth Baptist Church | E181213a | 2018-12-13 | MP Sheets |  |  | no |  |  |  |  | 1 | 2018-12-13 | Done
1779 | MEL5K Melissa 5.3K SF Shell | E181213b | 2018-12-13 | ONCOR Form |  |  | no |  |  |  |  | 1 | 2018-12-13 | Done
1784 | ITPWR DCCCD IT Closet Upgrades | E1812017a | 2018-12-17 | Sign Contract |  |  | no |  |  |  |  | 0.5 | 2018-12-17 | Done
1788 | HONDA Denton | E181217c | 2018-12-17 | Proposal |  |  | no |  |  | 2018-12-17 |  | 0.5 | 2018-12-18 | Done
1600 | Gun Experience | E181217d | 2018-12-17 | Revision Materials |  |  | billed |  |  |  |  | 6 | 2018-12-20 | Done
1790 | TJPP - The Joint Pinnacle Park | E181218a | 2018-12-18 | Prepare review set |  |  | billed |  |  | 2018-12-18 |  | 4 | 2018-12-19 | Done
1732 | City of Lake Worth Projects | E181212a | 2018-12-19 | Re issue IFC |  |  | no |  |  | 2018-12-19 |  | 0.5 | 2018-12-19 | Done
1544 | The Community At Lake Ridge | E181219b | 2018-12-19 | Rev 9 Description |  |  | no |  |  |  |  | 0.5 | 2018-12-19 | Done
1791 | RIGHT - Righteous Food | E181219c | 2018-12-19 | Proposal |  |  | no |  |  |  |  | 0.5 | 2018-12-20 | Done
1781 | GRACE Revolution | E181218b | 2018-12-20 | Schedule information |  |  | no | [5 empty] | 2018-12-20 | Done
1781 | GRACE Revolution | E181218b | 2018-12-20 | IFC Due | TBD Follow up on 1/15 |  | billed |  | 2019-02-13 | 2019-02-12 | 1 | 3 | 2019-02-12 | Done
1544 | The Community At Lake Ridge | E181218c | 2018-12-20 | Questions and answers | Email only |  | no | [5 empty] | 2019-01-07 | Done
1790 | TJPP - The Joint Pinnacle Park | E181218a | 2018-12-21 | IFC |  |  | billed |  |  |  |  | 0.5 | 2018-12-21 | Done
1581 | Crescent Schools | E181219d | 2018-12-21 | Updated base file |  |  | no | [5 empty] | 2019-01-03 | Done
1530 | Brennan Drop-off Changes | E181219e | 2018-12-21 | City Comments | Need new sign location |  | no | [5 empty] | 2019-01-15 | Done
1531 | MLK Drop-off Changes | E181219e | 2018-12-21 | City Comments | No comments |  | no |  |  |  |  | 0.5 | 2018-12-21 | Done
1532 | Old Hemphill Drop-off Changes | E181219e | 2018-12-21 | City Comments | Need feedback from the City |  | no |  |  | 2018-12-26 |  |  | 2019-01-03 | Done
1583 | 7 City Church | E181221a | 2018-12-21 | Office Revision Proposal |  |  | no |  |  |  |  | 0.5 | 2018-12-21 | Done
1788 | HONDA Denton | E181221b | 2018-12-21 | NTP | 1/2 Cancelled. Need to talk to Rob |  | no | [5 empty] | 2019-01-02 | Done
1532 | Old Hemphill Drop-off Changes | E190102a | 2019-01-02 | New COMCheck report for stor bldg |  |  | no | [5 empty] | 2019-01-15 | Done
1530 | Brennan Drop-off Changes | E181219a | 2019-01-02 | New sign relo confirmation | Not needed |  | no |  |  | 2019-01-02 |  |  | 2019-01-15 | Done
1707 | Ryan Schools | E190102b | 2019-01-02 | PWR re-submittal |  |  | no |  |  |  |  | 1 | 2019-01-03 | Done
1705 | North Fort Worth Baptist Church | E190102d | 2019-01-02 | Review 100% DD set |  |  | no |  |  | 2019-02-14 | 1 |  | 2019-03-16 | Done
1581 | Crescent Schools | E190102g | 2019-01-02 | Kitchen info |  |  | no | [5 empty] | 2019-01-05 | Done
1581 | Crescent Schools | E190102h | 2019-01-02 | Submittal |  |  | no |  |  | 2019-01-07 |  | 1.5 | 2019-01-07 | Done
1784 | ITPWR DCCCD IT Closet Upgrades | E190102j | 2019-01-02 | RC Site Visit |  |  | no |  |  | 2019-01-05 |  | 3 | 2019-01-07 | Done
1766 | Xpress Wellness Duncan OK | E190102k | 2019-01-02 | Site Visit Materials |  |  | no |  |  | 2019-01-08 |  | 0.5 | 2019-01-08 | Done
1614 | Euless Library | E190102j | 2019-01-07 | LTG Submittal |  |  | billed |  |  | 2019-01-07 |  | 1 | 2019-01-08 | Done
1530 | Brennan Drop-off Changes | E190103a | 2019-01-07 | ASA CA Proposal |  |  | no |  |  | 2019-01-07 |  | 1 | 2019-01-07 | Done
1581 | Crescent Schools | E190105a | 2019-01-07 | Architect's comments |  |  | no |  |  | 2019-01-14 |  |  | 2019-01-27 | Done
1779 | MEL5K Melissa 5.3K SF Shell | p12-66 | 2019-01-07 | IFR Work |  |  | no |  | 2019-01-16 | 2019-01-14 | 4 |  | 2019-01-15 | Done
1581 | Crescent Schools |  | 2019-01-07 | Get question list |  |  | no |  |  | 2019-01-08 |  | 1 | 2019-01-08 | Done
1784 | ITPWR DCCCD IT Closet Upgrades |  | 2019-01-07 | Request USF info from Ken |  |  | no |  |  | 2019-01-07 |  |  | 2019-01-07 | Done
1784 | ITPWR DCCCD IT Closet Upgrades |  | 2019-01-07 | Request help from Mike Havens |  |  | no |  |  | 2019-01-07 |  |  | 2019-01-07 | Done
1779 | MEL5K Melissa 5.3K SF Shell | E190102a | 2019-01-07 | Some answers |  |  | no |  |  | 2019-01-14 | 2 |  | 2019-01-15 | Done
1477 | Eugene McCray Recreation Center | E190102b | 2019-01-07 | Invoices at 84.4% |  |  | billed |  |  |  |  | 0.5 | 2019-01-08 | Done
1768 | NRGV Volleyball Facility Mansfield | E190107b | 2019-01-07 | Coordinate with Randy | Send Qs again. |  | no |  |  | 2019-01-07 |  | 1 | 2019-01-07 | Done
1797 | FWLAB - Tactical Center Lab Renovations |  | 2019-01-07 | Design Narrative and Estimate |  |  | no |  |  | 2019-01-08 |  | 2 | 2019-01-08 | Done
1581 | Crescent Schools |  | 2019-01-07 | Send RCP to Baginda |  |  | no |  |  | 2019-01-08 |  | 2 | 2019-01-08 | Done
1581 | Crescent Schools | E190108a | 2019-01-08 | Relo generator to xfrmr | See email |  | no |  |  | 2019-02-13 | 1 |  | 2019-02-14 | Done
1797 | FWLAB - Tactical Center Lab Renovations |  | 2019-01-08 | Site Visit to North Service Center |  |  | no |  |  | 2019-01-08 |  | 2 | 2019-01-08 | Done
1794 | FREEFORM - Freeform Chiropractic | E190107d | 2019-01-08 | Proposal |  |  | no |  |  | 2019-01-08 |  | 0.5 | 2019-01-08 | Done
1795 | CURTIS - Curtis Drive Warehouses | E190107d | 2019-01-08 | Proposal |  |  | no |  |  | 2019-01-08 |  | 0.5 | 2019-01-08 | Done
1544 | The Community At Lake Ridge | E190107e | 2019-01-08 | Type P and V submittal |  |  | no |  |  | 2019-01-08 |  | 0.5 | 2019-01-08 | Done
1796 | IAGULLI - Castle NRH MOB | E190107d | 2019-01-08 | Proposal |  |  | no |  |  | 2019-01-08 |  | 0.5 | 2019-01-08 | Done
1541 | Rudy's New Equipment | E190110a | 2019-01-14 | RFI 89 |  |  | no |  |  |  |  | 0.5 | 2019-01-14 | Done
1705 | North Fort Worth Baptist Church | E190109a | 2019-01-15 | Answer AVL questions | Done. |  | no |  |  | 2019-02-14 | 2 |  | 2019-03-16 | Done
1544 | The Community At Lake Ridge | E190109b | 2019-01-15 | FA Submittal |  |  | no |  |  | 2019-01-15 |  | 0.5 | 2019-01-16 | Done
1784 | ITPWR DCCCD IT Closet Upgrades | E190109c | 2019-01-15 | Richland College IFR |  |  | no |  |  | 2019-01-16 |  | 2 | 2019-01-19 | Done
1799 | NEKARB - Nekter Arboretum | E190110c | 2019-01-15 | Review existing information | Done. Two existing panels L1 and L2. |  | no |  |  | 2019-01-15 |  | 0.5 | 2019-01-28 | Done
1581 | Crescent Schools | E190110d | 2019-01-15 | Review Answers |  |  | no |  |  | 2019-01-16 |  |  | 2019-01-27 | Done
1797 | FWLAB - Tactical Center Lab Renovations | E190107c | 2019-01-15 | Set up project | Superceded |  | no |  |  | 2019-02-19 | 2 |  | 2019-02-28 | Done
1544 | The Community At Lake Ridge | E190114a | 2019-01-15 | RFI 089 |  |  | no |  |  | 2019-01-14 |  | 1 | 2019-01-14 | Done
1773 | COFW Worth Heights Multi-purpose TAS | E190110e | 2019-01-15 | Review Comments |  |  | no |  |  | 2019-02-18 | 1 | 1 | 2019-03-27 | Done
1532 | Old Hemphill Drop-off Changes | E190115a | 2019-01-15 | Issue COMCheck revision |  |  | no |  |  | 2019-01-15 |  | 2 | 2019-01-15 | Done
1600 | Gun Experience | E190115b | 2019-01-15 | Revision 4 Delta 4 |  |  | no |  |  | 2019-01-15 |  | 2 | 2019-01-15 | Done
ops | Operations | E190114b | 2019-01-17 | HUB renewal | See 2019 in HUB folder |  | no |  |  | 2019-04-27 | 2 | 4 | 2019-05-02 | Done
1581 | Crescent Schools | E190114d | 2019-01-17 | Update CAD files |  |  | no |  |  | 2019-01-18 |  |  | 2019-01-27 | Done
1772 | COFW North Tri-Ethnic CC TAS | E190115c | 2019-01-17 | Added requirements | In email |  | no |  |  | 2019-02-18 | 2 |  | 2019-07-02 | Done
1784 | ITPWR DCCCD IT Closet Upgrades | E190109c | 2019-01-17 | RC DEHA |  |  | no |  |  | 2019-01-18 |  | 1 | 2019-01-28 | Done
1581 | Crescent Schools | E190116c | 2019-01-17 | Updated Kitchen docs |  |  | no |  |  | 2019-02-13 | 1 |  | 2019-02-14 | Done
1600 | Gun Experience | E190116d | 2019-01-17 | FA Submittal |  |  | no |  |  | 2019-01-18 |  | 1 | 2019-01-28 | Done
1768 | NRGV Volleyball Facility Mansfield | E190116b | 2019-01-17 | Review updated documents |  |  | no | y |  | 2019-01-31 | 2 |  | 2019-02-08 | Done
1781 | GRACE Revolution | E190117b | 2019-01-17 | Electrical Coordination | See email for info |  | no |  |  | 2019-02-12 | 1 |  | 2019-02-12 | Done
1781 | GRACE Revolution | E190117c | 2019-01-17 | Schedule information |  |  | no |  |  | 2019-02-12 | 1 |  | 2019-02-12 | Done
1581 | Crescent Schools | E190118a | 2019-01-19 | Updated drawings |  |  | no |  |  | 2019-01-19 |  |  | 2019-01-27 | Done
1781 | GRACE Revolution | E190110f | 2019-01-21 | Project setup |  |  | no |  |  | 2019-02-04 | 1 | 2 | 2019-02-07 | Done
1768 | NRGV Volleyball Facility Mansfield | E190123a | 2019-01-23 | Civil Set |  |  | no |  |  | 2019-01-29 | 2 | 1 | 2019-01-30 | Done
1766 | Xpress Wellness Duncan OK | E190121a | 2019-01-24 | Existing RTU information |  |  | no |  |  | 2019-02-20 | 1 | 1 | 2019-02-28 | Done
1581 | Crescent Schools | E190121b | 2019-01-24 | Update Roof plan |  |  | no |  |  | 2019-01-24 |  |  | 2019-01-27 | Done
1614 | Euless Library | E190122a | 2019-01-24 | Submittal |  |  | no |  |  | 2019-01-24 |  | 2 | 2019-01-24 | Done
1581 | Crescent Schools | E190122b | 2019-01-24 | MP Sheets |  |  | no |  |  | 2019-01-24 |  |  | 2019-01-27 | Done
1581 | Crescent Schools | E190123b | 2019-01-24 | Kitchen answers | See email |  | no |  |  | 2019-01-24 |  |  | 2019-01-27 | Done
1799 | NEKARB - Nekter Arboretum | E190124a | 2019-01-24 | Added information | See dropbox |  | no |  |  | 2019-02-12 | 2 |  | 2019-03-14 | Done
1581 | Crescent Schools | E190124b | 2019-01-24 | Updated base files | See email for summary of changes |  | no |  |  | 2019-01-25 |  |  | 2019-01-27 | Done
1581 | Crescent Schools | E190124c | 2019-01-24 | Questions and answers | See email for answers |  | no | E |  | 2019-02-13 | 1 |  | 2019-02-17 | Done
1797 | FWLAB - Tactical Center Lab Renovations | E190124d | 2019-01-24 | Comments on SD package |  |  | no |  |  | 2019-02-19 | 2 |  | 2019-02-28 | Done
1768 | NRGV Volleyball Facility Mansfield | E190124e | 2019-01-24 | Update architectural |  |  | no | y |  | 2019-01-31 | 2 |  | 2019-02-08 | Done
1705 | North Fort Worth Baptist Church | E190125a | 2019-01-25 | Select House fixture | 11/28 Sent to Andrew for approval See emails |  | no |  |  | 2019-02-14 | 1 | 0.5 | 2019-03-16 | Done
1581 | Crescent Schools | E190124f | 2019-01-25 | Review wall heights |  |  | no |  |  | 2019-01-25 |  |  | 2019-01-27 | Done
1544 | The Community At Lake Ridge | E190125b | 2019-01-25 | Rev 12 |  |  | no |  |  | 2019-01-25 |  | 1 | 2019-01-25 | Done
1768 | NRGV Volleyball Facility Mansfield | E190125c | 2019-01-25 | Conversation with morrow |  |  | no |  |  |  |  | 2 | 2019-01-25 | Done
1581 | Crescent Schools | E190127a | 2019-01-27 | Multipurpose MP Sheets |  |  | no |  |  | 2019-01-27 |  |  | 2019-01-27 | Done
1581 | Crescent Schools | E190126a | 2019-01-27 | Specifications |  |  | no |  |  | 2019-02-13 | 1 |  | 2019-02-17 | Done
1670 | Brookhaven Generator |  | 2019-01-28 | KO Mtg |  |  | no |  |  | 2019-01-28 | 4 | 3 | 2019-01-28 | Done
1581 | Crescent Schools |  | 2019-01-28 | Add Alternate 1 |  |  | no |  |  | 2019-02-13 | 2 | 2 | 2019-02-14 | Done
1581 | Crescent Schools | E190128a | 2019-01-28 | Update base file | No apparent changes |  | no |  |  | 2019-01-28 | 1 | 0 | 2019-01-28 | Done
1670 | Brookhaven Generator | E190128b | 2019-01-28 | Generator Submittal |  |  | no |  |  | 2019-01-28 | 1 | 1 | 2019-01-28 | Done
1797 | FWLAB - Tactical Center Lab Renovations | E190124d | 2019-01-28 | Revise proposal | Bid vs JOC |  | no |  |  | 2019-01-28 |  | 1 | 2019-01-29 | Done
1779 | MEL5K Melissa 5.3K SF Shell | E190128c | 2019-01-28 | Relo wall packs |  |  | no |  |  | 2019-01-28 | 1 | 1 | 2019-01-28 | Done
1581 | Crescent Schools | E190128d | 2019-01-28 | Add entrance lights |  |  | no |  |  | 2019-01-28 | 0.5 | 0.5 | 2019-01-28 | Done
1581 | Crescent Schools |  | 2019-01-28 | Add UC lights |  |  | no |  |  | 2019-02-13 | 2 | 2 | 2019-02-15 | Done
1581 | Crescent Schools |  | 2019-01-28 | valve controls from Tim | Need Tim's markups |  | no | M |  | 2019-02-13 |  |  | 2019-02-17 | Done
1779 | MEL5K Melissa 5.3K SF Shell | E190128c | 2019-01-29 | IFC |  |  | billed |  | 2019-01-30 | 2019-01-29 | 1 |  | 2019-01-30 | Done
1781 | GRACE Revolution | E190129a | 2019-01-29 | Update files |  |  | no |  |  | 2019-01-29 | 2 | 2 | 2019-01-29 | Done
1768 | NRGV Volleyball Facility Mansfield |  | 2019-01-29 | Design Work |  |  | no | y |  | 2019-01-29 | 4 |  | 2019-02-08 | Done
1768 | NRGV Volleyball Facility Mansfield | E190130a | 2019-01-30 | Specs on drawings |  |  | no | y |  | 2019-01-31 |  |  | 2019-02-08 | Done
1800 | SALON - Lana's Hair Salon | E190131a | 2019-01-31 |  |  |  | no |  |  | 2019-01-31 |  | 0.5 | 2019-01-31 | Done
1799 | NEKARB - Nekter Arboretum | E190131b | 2019-01-31 | Project files |  |  | no |  |  | 2019-02-12 | 1 |  | 2019-03-05 | Done
1768 | NRGV Volleyball Facility Mansfield | E190131c | 2019-01-31 | Update civil base file |  |  | no | y |  | 2019-01-31 |  |  | 2019-02-08 | Done
1768 | NRGV Volleyball Facility Mansfield | T190201 | 2019-02-01 | MP Sheets |  |  | no | y |  | 2019-02-01 |  |  | 2019-02-08 | Done
1781 | GRACE Revolution | E190129a | 2019-02-01 | Receptacles for workstations | See email for instructions |  | no |  |  | 2019-02-04 |  | 1 | 2019-02-08 | Done
1777 | BALKO Cafeteria Changes | E190201a | 2019-02-01 | Project files |  |  | no |  |  | 2019-02-01 |  |  | 2019-02-10 | Done
1777 | BALKO Cafeteria Changes | E190201b | 2019-02-01 | Kitchen materials | See email for additional info |  | no |  |  | 2019-02-04 |  |  | 2019-02-10 | Done
1581 | Crescent Schools | E190203a | 2019-02-05 | Update MP base file | Superceded by E190217b |  | no | M |  | 2019-02-13 |  | 0 | 2019-02-17 | Done
1766 | Xpress Wellness Duncan OK | E190204a | 2019-02-05 | Base files. | Superseeded by E190222a |  | no |  |  | 2019-02-20 |  |  | 2019-02-25 | Done
1777 | BALKO Cafeteria Changes | E190201b | 2019-02-05 | E19 has changed from 35A to 30A | See email. |  | no | [5 empty] | 2019-02-10 | Done
1773 | COFW Worth Heights Multi-purpose TAS | E190110e | 2019-02-05 | Prepare ASA proposal |  |  | no |  | 2019-02-06 | 2019-02-06 |  | 1 | 2019-02-06 | Done
1581 | Crescent Schools | E190205a | 2019-02-05 | Canopy data | Add canopy lighting |  | no | E |  | 2019-02-13 |  |  | 2019-02-17 | Done
1705 | North Fort Worth Baptist Church | E190205b | 2019-02-05 | Add surge suppression to building | See email |  | no |  |  | 2019-02-14 | 2 | 0.5 | 2019-03-16 | Done
1777 | BALKO Cafeteria Changes | E190205c | 2019-02-05 | New kitchen ceiling at 8'-6" |  |  | no |  |  | 2019-02-05 |  |  | 2019-02-10 | Done
1801 | HOU -- Univ of Houston Transmitter | E190205d | 2019-02-06 | Prepare proposal |  |  | no |  |  | 2019-02-06 |  | 1 | 2019-02-08 | Done
1705 | North Fort Worth Baptist Church | E190205e | 2019-02-06 | Add baptistry |  |  | no |  |  | 2019-02-14 | 1 | 1 | 2019-03-16 | Done
1781 | GRACE Revolution | E190206a | 2019-02-06 | Cameras are POE | No action needed on design |  | no |  |  | 2019-02-06 |  |  | 2019-02-06 | Done
1799 | NEKARB - Nekter Arboretum | E190206b | 2019-02-06 | Update border |  |  | no |  |  | 2019-02-12 | 1 |  | 2019-03-14 | Done
1777 | BALKO Cafeteria Changes | E190207b | 2019-02-07 | Heat Lamp discussion |  |  | no |  |  | 2019-02-11 |  | 1 | 2019-02-11 | Done
1777 | BALKO Cafeteria Changes | E190207c | 2019-02-07 | TOC to James |  |  | no |  |  | 2019-02-08 | 1 |  | 2019-02-08 | Done
1777 | BALKO Cafeteria Changes | E190207c | 2019-02-07 | New border |  |  | no |  |  | 2019-02-08 |  |  | 2019-02-10 | Done
1477 | Eugene McCray Recreation Center | E190201c | 2019-02-08 | Punch List SV | Plus report |  | billed |  |  | 2019-02-07 | 3 | 4 | 2019-02-08 | Done
1781 | GRACE Revolution |  | 2019-02-08 | Are we keeping the disposal |  |  | no |  |  | 2019-02-12 | 1 |  | 2019-02-12 | Done
1777 | BALKO Cafeteria Changes | E190208a | 2019-02-10 | Add EWC |  |  | no |  |  | 2019-02-10 |  |  | 2019-02-10 | Done
1777 | BALKO Cafeteria Changes | E190208b | 2019-02-10 | Update RCP |  |  | no | [5 empty] | 2019-02-10 | Done
1777 | BALKO Cafeteria Changes | E190208b | 2019-02-10 | Update KIT plan |  |  | no |  |  |  |  | 2 | 2019-02-10 | Done
1777 | BALKO Cafeteria Changes | E190208d | 2019-02-10 | Replace all outlets and covers |  |  | no | [5 empty] | 2019-02-10 | Done
1777 | BALKO Cafeteria Changes | E190208e | 2019-02-10 | Protect wiring devices and exit signs during construction |  |  | no | [5 empty] | 2019-02-10 | Done
1777 | BALKO Cafeteria Changes | E190209a | 2019-02-10 | LTG goes North South |  |  | no | [5 empty] | 2019-02-10 | Done
1777 | BALKO Cafeteria Changes | E190209b | 2019-02-10 | Hood fan info + MP set | In MP |  | no | [5 empty] | 2019-02-10 | Done
1777 | BALKO Cafeteria Changes | E190209c | 2019-02-10 | Update base files |  |  | no | [5 empty] | 2019-02-10 | Done
1781 | GRACE Revolution | E190211a | 2019-02-12 | Furniture Plan |  |  | no |  |  | 2019-02-12 | 1 |  | 2019-02-12 | Done
1781 | GRACE Revolution | E190211b | 2019-02-12 | IT goes on Counseling 105 | See markups |  | no |  |  | 2019-02-12 | 1 |  | 2019-02-12 | Done
1693 | The Table Church | E190211c | 2019-02-12 | LTG Submittal |  |  | billed |  |  | 2019-02-12 |  | 1 | 2019-02-12 | Done
1581 | Crescent Schools | E190207d | 2019-02-12 | Canopy update |  |  | no | E |  | 2019-02-13 |  |  | 2019-02-17 | Done
mkt | Marketing | E190208g | 2019-02-12 | Prepare forms 330 |  |  | no |  |  | 2019-02-13 |  |  | 2019-03-15 | Done
1797 | FWLAB - Tactical Center Lab Renovations | E190209d | 2019-02-12 | Schedule DSV |  |  | no |  |  | 2019-02-19 |  |  | 2019-03-05 | Done
1797 | FWLAB - Tactical Center Lab Renovations | E190209d | 2019-02-12 | Set up project |  |  | no |  |  | 2019-02-19 |  |  | 2019-03-05 | Done
1614 | Euless Library | E190208h | 2019-02-12 | Review manual transfer switch |  |  | no |  |  | 2019-02-12 |  | 1 | 2019-02-12 | Done
1693 | The Table Church | E190211e | 2019-02-12 | Submittals |  |  | no |  |  | 2019-02-12 |  | 1 | 2019-02-12 | Done
1478 | Handley Meadowbrook Rec Center | E190212a | 2019-02-12 | Punch List SV and report | Scheduled for 2/13 @ 9 AM |  | billed |  |  | 2019-02-13 | 3 | 4 | 2019-02-13 | Done
1804 | HIGHLAND - Office Bldg and Shell | E1902112b | 2019-02-12 | Proposal |  |  | no |  |  |  |  | 1 | 2019-02-12 | Done
1799 | NEKARB - Nekter Arboretum | E181211d | 2019-02-12 | Need scoop clarification |  |  | no |  |  | 2019-02-12 |  |  | 2019-03-14 | Done
1801 | HOU -- Univ of Houston Transmitter | E190212c | 2019-02-12 | Pre-proposal meeting |  |  | no |  | 2019-02-19 | 2019-02-19 | 8 | 8 | 2019-02-12 | Done
1581 | Crescent Schools | E190213b | 2019-02-13 | Update base files |  |  | no |  |  | 2019-02-13 |  | 2 | 2019-02-14 | Done
1781 | GRACE Revolution | E190213c | 2019-02-13 | Data reqs |  |  | no |  |  | 2019-02-13 |  | 2 | 2019-02-13 | Done
1581 | Crescent Schools | E190213d | 2019-02-13 | 42 computers in elementary |  |  | no |  |  | 2019-02-13 |  | 2 | 2019-02-14 | Done
1705 | North Fort Worth Baptist Church | E190213e | 2019-02-13 | See email reqs | No action needed |  | no | [5 empty] | 2019-03-16 | Done
1581 | Crescent Schools | E190213f | 2019-02-13 | MP Set |  |  | no | M |  |  |  | 2 | 2019-02-17 | Done
mkt | Marketing | E190213g | 2019-02-13 | Texas State IDIQ |  |  | no |  |  | 2019-02-18 |  |  | 2019-03-15 | Done
1805 | TJMID - The Joint Midland | E190214a | 2019-02-14 | Set up project | Prepared IFR |  | no |  |  | 2019-02-18 | 1 | 3 | 2019-02-23 | Done
1581 | Crescent Schools | E190214b | 2019-02-14 | Specs |  |  | no |  |  | 2019-02-15 |  | 0.5 | 2019-02-17 | Done
1777 | BALKO Cafeteria Changes | E190215a | 2019-02-14 | OSFM Letter |  |  | no |  |  | 2019-02-14 |  | 1 | 2019-02-14 | Done
1807 | WCG - Weatherford Church of God Office Building | E190214c | 2019-02-14 | Proposal |  |  | no |  |  |  |  | 0.5 | 2019-02-14 | Done
1614 | Euless Library | E190215b | 2019-02-15 | Lighting controls submittal |  |  | no |  |  | 2019-02-15 |  | 0.5 | 2019-02-15 | Done
1421 | KXAS Remodel | E190215c | 2019-02-15 | Review Record Drawings |  |  | no |  |  | 2019-03-20 |  | 2 | 2019-03-22 | Done
1581 | Crescent Schools | E190215d | 2019-02-15 | Final Comments |  |  | no | M |  | 2019-02-15 |  | 0.5 | 2019-02-15 | Done
1581 | Crescent Schools | E190215e | 2019-02-15 | Add emergency lightis to elem |  |  | no | E |  | 2019-02-17 |  | 0.5 | 2019-02-17 | Done
1581 | Crescent Schools | E190215f | 2019-02-17 | MP items from Tim |  |  | no | M |  | 2019-02-17 |  | 0.5 | 2019-02-17 | Done
1581 | Crescent Schools | E190215g | 2019-02-17 | Elem items from Tim |  |  | no | E |  | 2019-02-17 |  | 0.5 | 2019-02-17 | Done
1581 | Crescent Schools | E190217a | 2019-02-17 | New EUH-107 location |  |  | no | E |  | 2019-02-17 |  | 0.5 | 2019-02-17 | Done
1581 | Crescent Schools | E190217b | 2019-02-17 | New wheelchair lift |  |  | no | M |  | 2019-02-17 |  | 0.5 | 2019-02-17 | Done
1581 | Crescent Schools | E190217b | 2019-02-17 | Update MP base file |  |  | no | M |  | 2019-02-17 |  | 0.5 | 2019-02-17 | Done
1581 | Crescent Schools | E190217c | 2019-02-17 | Soleniod Valve |  |  | no | M |  | 2019-02-17 |  | 0.5 | 2019-02-17 | Done
1583 | 7 City Church | E190215h | 2019-02-18 | Office revision changes |  |  | billed |  |  | 2019-02-20 |  | 1 | 2019-02-22 | Done
1583 | 7 City Church | E190215j | 2019-02-18 | FA Submittal |  |  | billed |  |  | 2019-02-20 |  | 0.5 | 2019-02-18 | Done
1544 | The Community At Lake Ridge | E190219a | 2019-02-20 | New plugs - Rev ? |  |  | no |  |  | 2019-02-20 |  | 2 | 2019-02-20 | Done
1805 | TJMID - The Joint Midland | E190220a | 2019-02-20 | Review existing information |  |  | no |  |  | 2019-02-20 |  | 1 | 2019-02-20 | Done
1600 | Gun Experience | E190220b | 2019-02-21 | RFIs |  |  | no |  |  | 2019-02-21 |  | 1 | 2019-02-21 | Done
1801 | HOU -- Univ of Houston Transmitter | E190220c | 2019-02-21 | Revised proposal |  |  | no |  |  | 2019-02-21 |  | 1 | 2019-02-20 | Done
1693 | The Table Church | E190220d | 2019-02-21 | ASI01 Revision |  |  | billed |  |  | 2019-02-21 |  | 2 | 2019-02-22 | Done
1797 | FWLAB - Tactical Center Lab Renovations | E190221b | 2019-02-21 | Base files. |  |  | no |  |  | 2019-02-21 |  | 1 | 2019-02-23 | Done
1583 | 7 City Church | E190221c | 2019-02-22 | Rev 8 receptacles |  |  | no |  |  | 2019-02-22 |  | 3 | 2019-02-22 | Done
1797 | FWLAB - Tactical Center Lab Renovations | E190223a | 2019-02-23 | MP Equipment |  |  | no |  |  | 2019-02-23 |  | 2 | 2019-02-23 | Done
1805 | TJMID - The Joint Midland | E190225a | 2019-02-25 | IFC |  |  | billed |  |  | 2019-02-25 |  | 0.5 | 2019-02-25 | Done
1766 | Xpress Wellness Duncan OK | E190222a | 2019-02-25 | Set up project |  |  | no |  |  | 2019-02-25 |  | 1 | 2019-02-28 | Done
1777 | BALKO Cafeteria Changes | E190222b | 2019-02-26 | LTG Submittal | Revise and resubmit |  | billed |  |  | 2019-02-26 |  | 1 | 2019-02-26 | Done
1808 | PCN-Putnam City North HS | E190225b | 2019-02-26 | Proposal |  |  | no |  |  |  |  | 0.5 | 2019-02-26 | Done
1594 | Pflugerville AS | E190227a | 2019-02-27 | TVSS issue |  |  | no | [5 empty] | 2019-02-27 | Done
1797 | FWLAB - Tactical Center Lab Renovations | E190227b | 2019-02-27 | Architect's comments |  |  | no |  |  | 2019-02-27 |  |  | 2019-02-28 | Done
1781 | GRACE Revolution | E190227d | 2019-02-27 | Revision 1 |  |  | no |  |  | 2019-02-27 | 1 | 0.5 | 2019-02-27 | Done
1705 | North Fort Worth Baptist Church | E190227e | 2019-02-27 | House lights definition |  |  | no |  |  | 2019-02-27 |  |  | 2019-03-16 | Done
1705 | North Fort Worth Baptist Church | E190227f | 2019-02-27 | Update Revit file | Superseded |  | no |  |  | 2019-02-28 |  |  | 2019-03-16 | Done
1766 | Xpress Wellness Duncan OK | E190228a | 2019-02-28 | Signs and Wall packs |  |  | no |  |  | 2019-02-28 |  | 1 | 2019-02-28 | Done
1766 | Xpress Wellness Duncan OK | E190228b | 2019-02-28 | Update base file and IFC |  |  | no |  |  |  |  | 2 | 2019-02-28 | Done
1705 | North Fort Worth Baptist Church | E190228c | 2019-02-28 | LTG study for worship center | See email for AIs |  | no |  |  | 2019-03-01 |  |  | 2019-03-16 | Done
1798 | OAK-Oak Knoll Office | E190301a | 2019-03-01 | Set up project |  |  | no |  |  | 2019-03-01 |  | 2 | 2019-03-07 | Done
1799 | NEKARB - Nekter Arboretum | E190301b | 2019-03-01 | MP Sheets |  |  | no |  |  | 2019-03-01 |  | 1 | 2019-03-01 | Done
1581 | Crescent Schools | E190301c | 2019-03-01 | Submittals | LTG |  | no |  |  | 2019-03-02 |  | 0.5 | 2019-03-15 | Done
1581 | Crescent Schools | E190301d | 2019-03-01 | Submittals | LTG |  | no |  |  | 2019-03-02 |  | 0.5 | 2019-03-01 | Done
1799 | NEKARB - Nekter Arboretum | E190304a | 2019-03-04 | Updated equipment and base file |  |  | no |  |  | 2019-03-04 |  |  | 2019-03-14 | Done
1705 | North Fort Worth Baptist Church | E190304c | 2019-03-04 | Update Revit file | superseded |  | no |  |  | 2019-03-05 |  |  | 2019-03-16 | Done
1773 | COFW Worth Heights Multi-purpose TAS | E190228a | 2019-03-05 | Set up project |  |  | no |  |  | 2019-03-06 |  | 4 | 2019-05-20 | Done
1773 | COFW Worth Heights Multi-purpose TAS | E190228a | 2019-03-05 | Provide schedule for SD |  |  | no |  |  | 2019-03-05 |  |  | 2019-03-15 | Done
1705 | North Fort Worth Baptist Church | E190301e | 2019-03-05 | Review 50% CD | Superseded |  | no |  |  | 2019-03-05 |  |  | 2019-03-13 | Done
1806 | XWGUT - Xpress Wellness Guthrie OK | E190304e | 2019-03-05 | Schedule saved on XWGUT |  |  | no |  |  |  |  | 0 | 2019-03-14 | Done
1809 | XWARD-Xpress Wellness Ardmore OK | E190304e | 2019-03-05 | IFC due | Schedule saved on XWGUT |  | billed |  | 2019-04-11 | 2019-04-10 |  | 6 | 2019-04-10 | Done
1810 | XWGUY-Xpress Wellness Guymon OK | E190304e | 2019-03-05 | IFC due | Schedule saved on XWGUT |  | billed |  | 2019-05-10 | 2019-05-10 |  |  | 2019-05-08 | Done
1811 | XWDGE-Xpress Wellness Dodge City OK | E190304e | 2019-03-05 | IFC due | Schedule saved on XWGUT |  | billed |  | 2019-05-10 | 2019-05-10 |  |  | 2019-05-08 | Done
1812 | XWGB-Xpress Wellness Great Bend OK | E190304e | 2019-03-05 | IFC due | Schedule saved on XWGUT |  | billed |  | 2019-05-10 | 2019-05-10 |  |  | 2019-05-08 | Done
1805 | TJMID - The Joint Midland | E190305a | 2019-03-05 | Review comments |  |  | no |  |  | 2019-03-05 |  |  | 2019-03-05 | Done
1784 | ITPWR DCCCD IT Closet Upgrades | E190305b | 2019-03-05 | Pre bid Meeting |  |  | no |  |  | 2019-03-19 |  | 4 | 2019-03-19 | Done
1705 | North Fort Worth Baptist Church | E190305c | 2019-03-05 | Kids Assembly equipment |  |  | no |  |  | 2019-03-06 |  | 2 | 2019-03-16 | Done
1798 | OAK-Oak Knoll Office | E190307a | 2019-03-07 | MP Sheets |  |  | no |  |  |  |  | 1 | 2019-03-07 | Done
1798 | OAK-Oak Knoll Office |  | 2019-03-07 | IFR |  |  | no |  |  |  |  | 3 | 2019-03-07 | Done
1693 | The Table Church | E190306a | 2019-03-07 | Revision 4 |  |  | no |  |  | 2019-03-08 |  | 2 | 2019-03-08 | Done
1705 | North Fort Worth Baptist Church | E190308a | 2019-03-08 | EM lighting in worship center |  |  | no |  |  | 2019-03-11 |  | 2 | 2019-03-16 | Done
1798 | OAK-Oak Knoll Office | E190311a | 2019-03-11 | IFC due 3/12 |  |  | billed |  | 2019-03-12 | 2019-03-12 |  | 4 | 2019-03-12 | Done
1772 | COFW North Tri-Ethnic CC TAS | E190306b | 2019-03-12 | SD materials |  |  | no |  |  |  |  | 2 | 2019-04-18 | Done
1806 | XWGUT - Xpress Wellness Guthrie OK | E190310a | 2019-03-12 | Set up project |  |  | no |  |  |  |  | 4 | 2019-03-13 | Done
ops | Operations | E190309a | 2019-03-13 | Look into generators from On Site Energy | Not done |  | no | [5 empty] | 2019-07-20 | Done
1705 | North Fort Worth Baptist Church | E190312a | 2019-03-13 | Update base files | superseded |  | no | [5 empty] | 2019-03-16 | Done
1705 | North Fort Worth Baptist Church | E190312b | 2019-03-13 | Dual lighting in stage support areas |  |  | no |  |  |  |  | 2 | 2019-03-27 | Done
1583 | 7 City Church | E190316b | 2019-03-13 | Rev 8 receptacles |  |  | no |  |  |  |  | 1 | 2019-03-13 | Done
1806 | XWGUT - Xpress Wellness Guthrie OK | E190313c | 2019-03-13 | Add light poles |  |  | no |  |  |  |  | 1 | 2019-03-15 | Done
1705 | North Fort Worth Baptist Church | E190313d | 2019-03-13 | Updated AVL Set | Superseded by 190315d |  | no | [5 empty] | 2019-03-16 | Done
1808 | PCN-Putnam City North HS | E190314a | 2019-03-14 | Requirements |  | NTP | no | [5 empty] | 2019-08-23 | Done
1808 | PCN-Putnam City North HS | E190314b | 2019-03-14 | Generator Specs |  | MTP | no | [5 empty] | 2019-08-23 | Done
1813 | KODAK | E190314c | 2019-03-14 | Proposal |  |  | no |  |  | 2019-03-15 |  | 1 | 2019-03-15 | Done
1787 | MANS Mansfield Shell | E190314d | 2019-03-14 | Update site plan |  |  | no |  |  |  |  | 1 | 2019-03-21 | Done
1814 | MRGUN-Gun Range | E190315a | 2019-03-15 | Proposal |  |  | no |  |  | 2019-03-15 |  | 0.5 | 2019-03-15 | Done
1806 | XWGUT - Xpress Wellness Guthrie OK | E190315b | 2019-03-15 | Updated border |  |  | no |  |  | 2019-03-15 |  | 0.5 | 2019-03-15 | Done
1705 | North Fort Worth Baptist Church | E190315c | 2019-03-15 | Update Revit file | Invalid link. Tim provided copy |  | no |  |  |  |  | 0.5 | 2019-03-16 | Done
1705 | North Fort Worth Baptist Church | E190315d | 2019-03-15 | Updated AVL Set |  |  | no | [5 empty] | 2019-04-06 | Done
1815 | TJME-The Joint Market East Mesquite | E190315e | 2019-03-15 | Base files. |  |  | no |  |  |  |  | 2 | 2019-03-19 | Done
1815 | TJME-The Joint Market East Mesquite | E190317b | 2019-03-18 | MP Set |  |  | no |  |  |  |  | 2 | 2019-03-19 | Done
1787 | MANS Mansfield Shell | E190317a | 2019-03-18 | MP Set |  |  | no |  |  |  |  | 2 | 2019-03-21 | Done
1787 | MANS Mansfield Shell | E180315f | 2019-03-18 | Site plan |  |  | no |  |  |  |  | 2 | 2019-03-21 | Done
1787 | MANS Mansfield Shell | E180315g | 2019-03-18 | Elevations and fixture cut sheets | Also floor plan update |  | no |  |  |  |  | 2 | 2019-03-21 | Done
1795 | CURTIS - Curtis Drive Warehouses | E190315h | 2019-03-18 | Amended Proposal |  |  | no |  |  |  |  | 0.5 | 2019-03-18 | Done
1801 | HOU -- Univ of Houston Transmitter | E190319a | 2019-03-19 | Amended Proposal |  |  | no |  |  | 2019-03-19 |  |  | 2019-03-19 | Done
1815 | TJME-The Joint Market East Mesquite | E190319b | 2019-03-19 | Comments |  |  | no |  |  |  |  | 2 | 2019-03-19 | Done
1600 | Gun Experience | E190320a | 2019-03-20 | RFI 26 |  |  | no |  |  |  |  | 0.5 | 2019-03-20 | Done
1773 | COFW Worth Heights Multi-purpose TAS | E190318b | 2019-03-20 | SD materials |  |  | no |  |  |  |  | 1 | 2019-03-27 | Done
1705 | North Fort Worth Baptist Church | E190319d | 2019-03-20 | Provide Accuroll connections |  |  | no |  |  |  |  | 1 | 2019-04-02 | Done
1705 | North Fort Worth Baptist Church | E190319e | 2019-03-20 | MechoShades |  |  | no |  |  |  |  | 1 | 2019-04-02 | Done
1705 | North Fort Worth Baptist Church | E190320c | 2019-03-20 | 90% CD set for coordination |  |  | no | [5 empty] | 2019-04-06 | Done
1784 | ITPWR DCCCD IT Closet Upgrades | E190319f | 2019-03-20 | Addendum 1 floor plan |  |  | no | [5 empty] | 2019-03-22 | Done
ops | Operations | E190320d | 2019-03-20 | Pay insurance invoice |  |  | no |  |  | 2019-03-20 |  |  | 2019-03-20 | Done
1778 | HGOS Heritage Glenn Oral Surgery | E190320e | 2019-03-20 | Study Preliminary Set | In Reference folder |  | no | [5 empty] | 2019-04-25 | Done
1779 | MEL5K Melissa 5.3K SF Shell | E190320f | 2019-03-20 | Permit Comments |  |  | no |  |  | 2019-03-21 |  |  | 2019-03-21 | Done
1784 | ITPWR DCCCD IT Closet Upgrades | E190320g | 2019-03-20 | Addendum 1 question |  |  | no | [5 empty] | 2019-03-22 | Done
1781 | GRACE Revolution | E190325b | 2019-03-25 | Rev 2 |  |  | no |  |  |  |  | 0.5 | 2019-03-25 | Done
1778 | HGOS Heritage Glenn Oral Surgery | E190320e | 2019-03-25 | Set up project |  |  | no |  |  |  |  | 4 | 2019-04-25 | Done
1705 | North Fort Worth Baptist Church | E190322a | 2019-03-25 | 95% CD AVL |  |  | no | [5 empty] | 2019-04-06 | Done
1670 | Brookhaven Generator | E190322b | 2019-03-25 | Concrete Submittal |  |  | no |  |  |  |  | 1 | 2019-03-27 | Done
1705 | North Fort Worth Baptist Church | E190322c | 2019-03-25 | 95% CD | Problems downloading. |  | no | [5 empty] | 2019-04-06 | Done
1670 | Brookhaven Generator | E190322d | 2019-03-25 | Plan site visits | Fp mid april to schedule |  | no |  |  | 2019-07-22 |  |  | 2019-08-23 | Done
1818 | FWPL-FW Public Library Assessment | E190323a | 2019-03-26 | Proposal Materials |  |  | no |  |  |  |  | 1 | 2019-03-26 | Done
1808 | PCN-Putnam City North HS | E190326a | 2019-03-26 | Site Visit | superseded |  | no |  | 2019-04-01 |  |  | 0 | 2019-04-09 | Done
1819 | DHHS - Weatherford | E190327a | 2019-03-27 | Proposal |  |  | no |  |  |  |  | 0.5 | 2019-03-27 | Done
1787 | MANS Mansfield Shell |  | 2019-03-21 | IFC |  |  | billed |  | 2019-03-21 |  |  |  | 2019-03-21 | Done
1815 | TJME-The Joint Market East Mesquite |  | 2019-03-19 | IFC |  |  | billed |  | 2019-03-19 | 2019-03-19 |  |  | 2019-03-19 | Done
1705 | North Fort Worth Baptist Church | E190326b | 2019-03-27 | Select House fixture |  |  | no | [5 empty] | 2019-04-06 | Done
1781 | GRACE Revolution | E190326c | 2019-03-27 | Connectrack submittal |  |  | no |  | 2019-03-28 |  |  | 1 | 2019-03-27 | Done
1817 | DCSG - Dickie Carr Sand & Gravel | E190327a | 2019-03-27 | Signed Proposal |  |  | no | [5 empty] | 2019-03-27 | Done
1820 | MATA - DISD Mata ES Swing Space | E190327b | 2019-03-27 | Preliminary fee |  |  | no | [5 empty] | 2019-03-27 | Done
1781 | GRACE Revolution | E190327c | 2019-03-27 | Controls Submittal |  |  | no |  |  |  |  | 1 | 2019-03-27 | Done
1705 | North Fort Worth Baptist Church | E190327d | 2019-03-27 | Type D fixture | Wait for final decision |  | no | [5 empty] | 2019-04-06 | Done
1614 | Euless Library | E190328b | 2019-03-28 | CAD Release |  |  | no |  |  |  |  | 0.5 | 2019-04-01 | Done
1778 | HGOS Heritage Glenn Oral Surgery | E190320e | 2019-04-02 | Replies to Qs |  |  | no |  |  | 2019-05-01 |  | 1 | 2019-05-08 | Done
1797 | FWLAB - Tactical Center Lab Renovations | E190328c | 2019-04-02 | Comments |  |  | no |  |  |  |  | 2 | 2019-04-05 | Done
1821 | AGRA - Agra Hitting Building | E190402a | 2019-04-02 | Proposal |  |  | No |  |  |  |  | 0.5 | 2019-04-03 | Done
1792 | CELERIS - Celeris (2019) |  | 2019-03-15 | Projects |  |  | billed | [5 empty] | 2019-03-15 | Done
1705 | North Fort Worth Baptist Church |  | 2019-03-18 | 95% CD Due |  |  | billed |  | 2019-03-18 | 2019-03-18 |  |  | 2019-03-18 | Done
1705 | North Fort Worth Baptist Church | E190403a | 2019-04-03 | Update Revit file |  |  | no |  |  | 2019-04-03 |  |  | 2019-04-27 | Done
1705 | North Fort Worth Baptist Church | E190403b | 2019-04-03 | Comments |  |  | no |  |  | 2019-04-03 |  | 5 | 2019-04-06 | Done
1614 | Euless Library | E190404a | 2019-04-04 | LTG RFI |  |  | no |  |  |  |  | 0.5 | 2019-04-04 | Done
1705 | North Fort Worth Baptist Church | E190404b | 2019-04-04 | Specs |  |  | NO | [5 empty] | 2019-04-06 | Done
1806 | XWGUT - Xpress Wellness Guthrie OK | E190402b | 2019-04-02 | Evaluate Fire Alarm system | Request ignored |  | no | [5 empty] | 2019-05-17 | Done
1809 | XWARD-Xpress Wellness Ardmore OK | E190403c | 2019-04-03 | Base files. |  |  | no |  |  |  |  | 0 | 2019-04-10 | Done
1693 | The Table Church | E190404d | 2019-04-04 | Submittal |  |  | no |  |  |  |  | 1 | 2019-04-24 | Done
1809 | XWARD-Xpress Wellness Ardmore OK | E190405c | 2019-04-04 | Updated base files |  |  | no |  |  |  |  | 1 | 2019-04-10 | Done
1705 | North Fort Worth Baptist Church | E190405a | 2019-04-05 | Electric Sign |  |  | NO | [5 empty] | 2019-04-06 | Done
1705 | North Fort Worth Baptist Church | E190405b | 2019-04-05 | Change cans to 2x2s + |  |  | no | [5 empty] | 2019-04-06 | Done
1822 | ROANOKE - Gun Range | E190405c | 2019-04-08 | Proposal |  |  | no |  |  |  |  | 0.5 | 2019-04-08 | Done
1808 | PCN-Putnam City North HS | E190408a | 2019-04-08 | Site Visit |  |  | billed |  | 2019-04-09 | 2019-04-09 |  | 8 | 2019-04-09 | Done
1809 | XWARD-Xpress Wellness Ardmore OK | E190408c | 2019-04-08 | Specs goby |  |  | no |  |  |  |  | 0 | 2019-04-10 | Done
1799 | NEKARB - Nekter Arboretum | E190408d | 2019-04-08 | Comments |  |  | no |  | 2019-04-12 |  |  | 2 | 2019-04-23 | Done
1773 | COFW Worth Heights Multi-purpose TAS | E190408e | 2019-04-08 | Revise cost estimate |  |  | no |  | 2019-04-12 |  |  | 1 | 2019-04-12 | Done
1809 | XWARD-Xpress Wellness Ardmore OK | E190410a | 2019-04-10 | New TB |  |  | no |  |  |  |  | 1 | 2019-04-10 | Done
1809 | XWARD-Xpress Wellness Ardmore OK | E190410c | 2019-04-10 | MP sheets |  |  | no |  |  |  |  | 1 | 2019-04-10 | Done
1768 | NRGV Volleyball Facility Mansfield | E190410b | 2019-04-10 | Permit Comments |  |  | no |  |  | 2019-04-10 |  | 1 | 2019-04-11 | Done
1823 | 360CW-360 Commerce Warehouse | E190415a | 2019-04-15 | Proposal |  |  | no |  |  |  |  | 0.5 | 2019-04-15 | Done
1778 | HGOS Heritage Glenn Oral Surgery |  | 2019-04-15 | LTG Schedule |  |  | no |  |  |  |  | 4 | 2019-04-15 | Done
1793 | VERDEN - Verden Schools Elec Upgrade | E190416a | 2019-04-16 | Site Visit |  |  | no |  | 2019-04-30 | 2019-04-30 | 8 | 8 | 2019-04-03 | Done
1772 | COFW North Tri-Ethnic CC TAS | E190403b | 2019-04-16 | SD due |  |  | no |  | 2019-04-18 | 2019-04-17 |  | 4 | 2019-04-18 | Done
1792 | CELERIS - Celeris (2019) |  | 2019-04-16 | Dallas DAS calculations |  |  | no |  |  |  |  | 1 | 2019-04-16 | Done
1778 | HGOS Heritage Glenn Oral Surgery |  | 2019-04-16 | LTG PAL PHOTO and LAYOUT |  |  | no |  |  |  |  | 3 | 2019-04-16 | Done
1778 | HGOS Heritage Glenn Oral Surgery |  | 2019-04-16 | LTG CTR Daylight Zones |  |  | no |  |  |  |  | 1 | 2019-04-16 | Done
1789 | TJTR - The Joint Timber Ridge | E190417a | 2019-04-17 | Revision 1 |  |  | billed |  | 2019-04-17 | 2019-04-17 |  | 1 | 2019-04-17 | Done
1799 | NEKARB - Nekter Arboretum | E190417b | 2019-04-17 | Revision 1 materals |  |  | no |  |  |  |  | 1 | 2019-04-23 | Done
1772 | COFW North Tri-Ethnic CC TAS | E190306b | 2019-04-17 | Narrative and SPC |  |  | billed |  |  |  |  | 2 | 2019-04-17 | Done
1824 | CYL - Sauna Studio | E190418b | 2019-04-18 | Proposal |  |  | no |  |  |  |  | 0.5 | 2019-04-18 | Done
1746 | Xpress Wellness Liberal KS | E180417c | 2019-04-18 | Submittal |  |  | billed |  |  |  |  | 2 | 2019-04-18 | Done
1814 | MRGUN-Gun Range | E190418c | 2019-04-22 | Air Handler Submittal |  |  | no | AI | [5 empty] | Not Done
1778 | HGOS Heritage Glenn Oral Surgery | E190419a | 2019-04-22 | X-Ray equipment information |  |  | no |  |  | 2019-05-01 |  | 1 | 2019-05-08 | Done
1796 | IAGULLI - Castle NRH MOB | E190419b | 2019-04-22 | Civil set. Need photometrics for submittal |  |  | yes | later |  |  |  | 6 | 2019-04-25 | Done
1825 | NWCC - North West Church of Christ | E190419c | 2019-04-22 | Proposal |  |  | no |  |  |  |  | 0.5 | 2019-04-22 | Done
1811 | XWDGE-Xpress Wellness Dodge City OK | E190419d | 2019-04-22 | Project files |  |  | no |  |  |  |  | 2 | 2019-05-02 | Done
1810 | XWGUY-Xpress Wellness Guymon OK | E190419e | 2019-04-22 | Project files |  |  | no |  |  |  |  | 2 | 2019-05-02 | Done
1812 | XWGB-Xpress Wellness Great Bend OK | E190419f | 2019-04-22 | Project files |  |  | no |  |  |  |  | 2 | 2019-05-02 | Done
1778 | HGOS Heritage Glenn Oral Surgery | E190419g | 2019-04-22 | Updated floor plan | Separate AI for email |  | no |  |  | 2019-05-01 |  | 1 | 2019-05-08 | Done
1778 | HGOS Heritage Glenn Oral Surgery | E190419g | 2019-04-22 | Email w/ Ais | Separate AI for floor plan update |  | no |  |  | 2019-05-01 |  | 1 | 2019-05-08 | Done
1778 | HGOS Heritage Glenn Oral Surgery | E190420a | 2019-04-22 | X-ray photos |  |  | no |  |  | 2019-05-01 |  | 1 | 2019-05-08 | Done
1810 | XWGUY-Xpress Wellness Guymon OK | E190422a | 2019-04-22 | Site plan |  |  | no |  |  |  |  | 2 | 2019-05-02 | Done
1810 | XWGUY-Xpress Wellness Guymon OK | E190422b | 2019-04-22 | RCP |  |  | no |  |  |  |  | 1 | 2019-05-02 | Done
1810 | XWGUY-Xpress Wellness Guymon OK | E190422c | 2019-04-22 | Roof Plan |  |  | no |  |  |  |  | 1 | 2019-05-02 | Done
1799 | NEKARB - Nekter Arboretum | E190422d | 2019-04-22 | Office elevation |  |  | no |  |  |  |  | 1 | 2019-04-23 | Done
1826 | RI - Resource Industries | E190422e | 2019-04-22 | Proposal |  |  | no |  |  |  |  | 0.5 | 2019-04-22 | Done
1814 | MRGUN-Gun Range | E190422f | 2019-04-22 | Update Revit file | Superceeded |  | no | [5 empty] | 2019-07-17 | Done
1814 | MRGUN-Gun Range | E190422g | 2019-04-23 | Workroom Instructions |  |  | no | AI | [5 empty] | Not Done
1810 | XWGUY-Xpress Wellness Guymon OK | E190422i | 2019-04-23 | M Roof information |  |  | no |  |  |  |  | 0.5 | 2019-05-02 | Done
1811 | XWDGE-Xpress Wellness Dodge City OK | E190422i | 2019-04-23 | M Roof information |  |  | no |  |  |  |  | 0.5 | 2019-05-02 | Done
1812 | XWGB-Xpress Wellness Great Bend OK | E190422i | 2019-04-23 | M Roof information |  |  | no |  |  |  |  | 0.5 | 2019-05-02 | Done
1765 | Xpress Wellness Altus OK | E190422j | 2019-04-23 | Submittal |  |  | no |  |  |  |  | 2 | 2019-05-02 | Done
1810 | XWGUY-Xpress Wellness Guymon OK | E19423a | 2019-04-23 | Update RCP |  |  | no |  |  |  |  | 1 | 2019-05-02 | Done
1773 | COFW Worth Heights Multi-purpose TAS | E19423b | 2019-04-23 | Project files and alternates |  |  | no | 5 |  | 2019-05-02 |  | 4 | 2019-05-20 | Done
1773 | COFW Worth Heights Multi-purpose TAS | E19423b | 2019-04-23 | 95% Due |  |  | billed |  | 2019-05-21 | 2019-05-21 |  | 3 | 2019-05-21 | Done
1773 | COFW Worth Heights Multi-purpose TAS | E19423b | 2019-04-23 | IFC due |  |  | billed |  | 2019-06-26 | 2019-06-05 |  |  | 2019-06-26 | Done
1799 | NEKARB - Nekter Arboretum | E190424a | 2019-04-24 | Final Comments |  |  | no |  |  |  |  | 1 | 2019-04-24 | Done
1705 | North Fort Worth Baptist Church | E190424b | 2019-04-24 | RFI 4 |  |  | no |  |  |  |  | 0.5 | 2019-04-24 | Done
1629 | Heritage Glenn MOB Shell | E190425a | 2019-04-25 | RFI 4 |  |  | no |  |  |  |  | 0.5 | 2019-04-25 | Done
1796 | IAGULLI - Castle NRH MOB | E190425ab | 2019-04-25 | Boundaries |  |  | no |  |  |  |  | 0.5 | 2019-04-26 | Done
1778 | HGOS Heritage Glenn Oral Surgery | E190425c | 2019-04-25 | Site Visit |  |  | no |  | 2019-04-29 | 2019-04-29 |  | 2 | 2019-05-08 | Done
1629 | Heritage Glenn MOB Shell | E190425d | 2019-04-25 | RFI 5 |  |  | no |  |  | 2019-04-28 |  | 0.5 | 2019-04-29 | Done
1705 | North Fort Worth Baptist Church | E190426a | 2019-04-26 | Inverter clarification. |  |  | no |  |  |  |  | 0.5 | 2019-04-26 | Done
1823 | 360CW-360 Commerce Warehouse |  | 2019-04-29 | Proposal |  |  | no |  |  |  |  | 0.5 | 2019-04-29 | Done
1827 | 360CO-360 Commerce Office |  | 2019-04-29 | Proposal |  |  | no |  |  |  |  | 0.5 | 2019-04-29 | Done
1778 | HGOS Heritage Glenn Oral Surgery | E190429a | 2019-04-29 | Updated floor plan | Superseeded |  | no | [5 empty] | 2019-05-01 | Done
1828 | NUVO-Desk Project | E190430a | 2019-04-30 | Proposal |  |  | no |  |  |  |  | 0.5 | 2019-04-30 | Done
1797 | FWLAB - Tactical Center Lab Renovations | E190430b | 2019-04-30 | Final comments and IFC |  |  | billed |  | 2019-05-03 | 2019-05-01 |  | 3 | 2019-05-02 | Done
1797 | FWLAB - Tactical Center Lab Renovations | E190307b | 2019-03-07 | Specs |  |  | no |  |  |  |  | 3 | 2019-03-07 | Done
1746 | Xpress Wellness Liberal KS | E190501a | 2019-05-01 | Rev 4 materials |  |  | no |  |  |  |  | 2 | 2019-05-01 | Done
1778 | HGOS Heritage Glenn Oral Surgery | E190501b | 2019-05-01 | Updated base files |  |  | no |  |  |  |  | 0 | 2019-05-08 | Done
1421 | KXAS Remodel | E190501c | 2019-05-01 | Check record drawings |  |  | no |  |  |  |  | 1 | 2019-05-02 | Done
1629 | Heritage Glenn MOB Shell | E190501d | 2019-05-01 | LV Panel location Revision |  |  | no |  |  |  |  | 0.5 | 2019-05-01 | Done
1811 | XWDGE-Xpress Wellness Dodge City OK | E190501e | 2019-05-01 | New x-ray floor plan |  |  | no |  |  |  |  | 1 | 2019-05-02 | Done
1812 | XWGB-Xpress Wellness Great Bend OK | E190501e | 2019-05-01 | New x-ray floor plan |  |  | no |  |  |  |  | 1 | 2019-05-02 | Done
1829 | CALHB-Calumet Hitting Building | E190501f | 2019-05-01 | Proposal |  |  | no |  |  |  |  | 0.5 | 2019-05-01 | Done
1793 | VERDEN - Verden Schools Elec Upgrade |  | 2019-05-02 | Proposal |  |  | no |  |  |  |  | 0.5 | 2019-05-02 | Done
1778 | HGOS Heritage Glenn Oral Surgery | E190502b | 2019-05-02 | Update base file |  |  | no |  |  |  |  | 1 | 2019-05-08 | Done
1778 | HGOS Heritage Glenn Oral Surgery | E190505a | 2019-05-05 | HVAC set | Clarify FCU-6 |  | no |  |  |  |  | 2 | 2019-05-08 | Done
1778 | HGOS Heritage Glenn Oral Surgery |  | 2019-05-05 | PWR | ` |  | no |  |  |  |  | 3 | 2019-05-05 | Done
1778 | HGOS Heritage Glenn Oral Surgery |  | 2019-05-04 | LTG |  |  | no |  |  |  |  | 3 | 2019-05-04 | Done
1773 | COFW Worth Heights Multi-purpose TAS | E190506a | 2019-05-06 | Roof base file |  |  | no |  |  |  |  | 1 | 2019-05-20 | Done
1614 | Euless Library | E190506b | 2019-05-06 | ASI 2 Instructions | Got furniture plan |  | billed |  |  |  |  | 2 | 2019-05-15 | Done
1778 | HGOS Heritage Glenn Oral Surgery | E190506d | 2019-05-06 | Sconces |  |  | no |  |  |  |  | 2 | 2019-05-08 | Done
1809 | XWARD-Xpress Wellness Ardmore OK | E190506c | 2019-05-06 | X-ray addendum |  |  | no |  |  |  |  | 1 | 2019-05-07 | Done
1614 | Euless Library | E190507b | 2019-05-07 | RFI 33 |  |  | no | Now |  |  |  | 1 | 2019-05-07 | Done
1792 | CELERIS - Celeris (2019) | E190507c | 2019-05-07 | DXL03512 |  |  | billed |  |  |  |  | 1 | 2019-05-07 | Done
1778 | HGOS Heritage Glenn Oral Surgery | E190507d | 2019-05-07 | Updated M Schedule |  |  | no |  |  |  |  | 0.5 | 2019-05-07 | Done
1716 | Humane Society Animal Shelter | E190507f | 2019-05-07 | LTG fixture submittal |  |  | billed | 3 |  |  |  | 1 | 2019-05-09 | Done
1716 | Humane Society Animal Shelter | E190507g | 2019-05-07 | LTG Controls Submittal |  |  | no | 3 |  |  |  | 1 | 2019-05-09 | Done
1778 | HGOS Heritage Glenn Oral Surgery | E190507h | 2019-05-07 | Site plan |  |  | no |  |  |  |  | 2 | 2019-05-08 | Done
1581 | Crescent Schools | E190507j | 2019-05-07 | Submittals |  |  | billed | 2 |  |  |  | 2 | 2019-05-09 | Done
1732 | City of Lake Worth Projects | E190507k | 2019-05-07 | Revision 2 Addendum 2 | Approved |  | billed | 1 | 2019-05-10 |  |  | 2 | 2019-05-09 | Done
1629 | Heritage Glenn MOB Shell | E190507l | 2019-05-07 | RFI 8 |  |  | no | Now |  |  |  | 1 | 2019-05-08 | Done
1778 | HGOS Heritage Glenn Oral Surgery | E190508a | 2019-05-07 | Updated base file |  |  | no |  |  |  |  | 0.5 | 2019-05-08 | Done
1811 | XWDGE-Xpress Wellness Dodge City OK | E190508b | 2019-05-08 | Updated Site plan |  |  | no |  |  |  |  | 0.5 | 2019-05-08 | Done
1810 | XWGUY-Xpress Wellness Guymon OK | E190508c | 2019-05-08 | Revised site plan |  |  | no |  |  |  |  | 0.5 | 2019-05-08 | Done
1830 | LWPW-Lake Worth Public Works | E190508e | 2019-05-08 | Proposal |  |  | no |  |  |  |  | 1 | 2019-05-08 | Done
ops | Operations |  | 2019-05-09 | Invoicing |  |  | no | 4 |  |  |  | 2 | 2019-05-10 | Done
1811 | XWDGE-Xpress Wellness Dodge City OK | E190509a | 2019-05-09 | Revised site plan |  |  | no |  |  |  |  | 1 | 2019-05-10 | Done
1581 | Crescent Schools |  | 2019-05-13 | Revised PWR submittal |  |  | no |  |  |  |  | 1 | 2019-05-13 | Done
1693 | The Table Church | E190513b | 2019-05-13 | FA Submittal |  |  | no | Now |  |  |  | 1 | 2019-05-15 | Done
1787 | MANS Mansfield Shell | E190514a | 2019-05-14 | City Comments |  |  | no |  |  |  |  | 2 | 2019-07-19 | Done
1831 | 1217-8TH-Funkytown Redevelopment | E190514b | 2019-05-14 | Proposal |  |  | no |  |  |  |  | 0.5 | 2019-05-15 | Done
1832 | TCEC-Munday | E190514c | 2019-05-14 | Proposal |  |  | no |  |  |  |  | 0.5 | 2019-05-15 | Done
1765 | Xpress Wellness Altus OK | E190515a | 2019-05-15 | X-Ray changes |  |  | no | Now |  |  |  | 1 | 2019-05-16 | Done
1806 | XWGUT - Xpress Wellness Guthrie OK | E190515b | 2019-05-15 | X-Ray changes |  |  | no | Now |  |  |  | 1 | 2019-05-16 | Done
1833 | GS-Goose and Stinky | E190515c | 2019-05-15 | Proposal |  |  | no |  |  |  |  | 0.5 | 2019-05-15 | Done
1705 | North Fort Worth Baptist Church | E190516a | 2019-05-16 | FA Substitution Request |  |  | no | Now |  |  |  | 1 | 2019-05-16 | Done
1793 | VERDEN - Verden Schools Elec Upgrade |  | 2019-05-17 | Plan project |  |  | no |  |  |  |  | 3 | 2019-05-31 | Done
1773 | COFW Worth Heights Multi-purpose TAS |  | 2019-05-17 | LTG |  |  | no |  |  |  |  | 4 | 2019-05-20 | Done
1773 | COFW Worth Heights Multi-purpose TAS |  | 2019-05-17 | PWR |  |  | no |  |  |  |  | 3 | 2019-05-20 | Done
1773 | COFW Worth Heights Multi-purpose TAS | E190518a | 2019-05-17 | MP Set |  |  | no |  |  |  |  | 2 | 2019-05-20 | Done
1824 | CYL - Sauna Studio | E190520a | 2019-05-20 | NTP and files |  |  | no |  |  |  |  | 2 | 2019-06-20 | Done
1773 | COFW Worth Heights Multi-purpose TAS | E190520b | 2019-05-20 | Modular furniture | Need layout in ACAD. Per Mike, place connections at the center |  | no | [5 empty] | 2019-06-26 | Done
1834 | TEMPLE - Temple High School | E190520c | 2019-05-20 | Proposal | Superceeded |  | no | [5 empty] | 2019-06-03 | Done
1629 | Heritage Glenn MOB Shell | E190517a | 2019-05-20 | LTG Submittal |  |  | no | Now |  |  |  | 1 | 2019-05-22 | Done
1835 | JUMBO Hills Warehouse | E190517b | 2019-05-20 | Proposal |  |  | no | Now |  |  |  | 0.5 | 2019-05-20 | Done
1777 | BALKO Cafeteria Changes | E190520d | 2019-05-20 | LTG Submittal |  |  | no | Now |  |  |  | 1 | 2019-05-22 | Done
1773 | COFW Worth Heights Multi-purpose TAS | E190521b | 2019-05-20 | Revisions to alternate 2 |  |  | no |  |  |  |  | 2 | 2019-05-22 | Done
1766 | Xpress Wellness Duncan OK | E190521a | 2019-05-21 | X-ray changes |  |  | no |  |  |  |  | 5 | 2019-05-23 | Done
1799 | NEKARB - Nekter Arboretum | E190524a | 2019-05-24 | Revision 1 |  |  | no |  |  |  |  | 8 | 2019-05-29 | Done
1806 | XWGUT - Xpress Wellness Guthrie OK | E190527a | 2019-05-27 | CAD Release. | 5/27 CAD release sent. Need payment. |  | no | [5 empty] | 2019-05-28 | Done
1629 | Heritage Glenn MOB Shell | E190524c | 2019-05-27 | ASI 002 |  |  | billed |  |  |  |  | 2 | 2019-05-27 | Done
1693 | The Table Church | E190529a | 2019-05-30 | FA Battery Submittal |  |  | no | Now |  |  |  | 1 | 2019-05-30 | Done
1600 | Gun Experience | E190529b | 2019-05-30 | Floor box submittal |  |  | no | Now |  |  |  | 1 | 2019-05-30 | Done
1824 | CYL - Sauna Studio | E190529c | 2019-05-30 | New base file and instructions |  |  | no |  |  |  |  | 1 | 2019-06-20 | Done
1836 | FFB First Financial Bank |  | 2019-05-30 | Review Set |  |  | no |  |  |  |  | 4 | 2019-05-30 | Done
1806 | XWGUT - Xpress Wellness Guthrie OK | E190531a | 2019-05-31 | Submittal |  |  | billed |  |  |  |  | 2 | 2019-05-31 | Done
1814 | MRGUN-Gun Range | E190531b | 2019-05-31 | Meeting at OWT |  |  | no |  | 2019-06-03 | 2019-06-03 | 3 | 3 | 2019-06-03 | Done
1793 | VERDEN - Verden Schools Elec Upgrade |  | 2019-05-31 | IFR due 6/6 |  |  | no |  | 2019-06-06 | 2019-06-05 |  | 2 | 2019-06-18 | Done
1838 | THURMAN - Camp Thurman | E190603a | 2019-06-03 | Proposal |  |  | no |  |  |  |  | 0.5 | 2019-06-03 | Done
1834 | TEMPLE - Temple High School | E190603b | 2019-06-03 | New Scope need proposal |  |  | no |  |  |  |  | 1 | 2019-06-11 | Done
1839 | HUNT - Hunt Regional Cardiovascular | E190603c | 2019-06-03 | Proposal |  |  | no |  |  |  |  | 0.5 | 2019-06-03 | Done
1836 | FFB First Financial Bank | E190603d | 2019-06-03 | IFC |  |  | billed |  | 2019-06-03 | 2019-06-03 |  | 1 | 2019-06-03 | Done
1799 | NEKARB - Nekter Arboretum | E190603e | 2019-06-03 | Rev 1 final |  |  | no |  |  |  |  | 0.5 | 2019-06-03 | Done
1792 | CELERIS - Celeris (2019) |  | 2019-06-04 | One-line to Brandon | DFW DAS |  | billed |  |  |  |  | 2 | 2019-06-04 | Done
1792 | CELERIS - Celeris (2019) |  | 2019-05-31 | Site Visit | DFW DAS |  | billed |  |  |  |  | 4 | 2019-05-31 | Done
1772 | COFW North Tri-Ethnic CC TAS | E190604b | 2019-06-04 | SD Approved. | Set up and plan |  | no |  |  |  |  | 2 | 2019-07-02 | Done
1762 | Stonebridge MOB Shells | E190604c | 2019-06-04 | Set up project | Superceeded |  | no | [5 empty] | 2019-07-15 | Done
1777 | BALKO Cafeteria Changes | E190604d | 2019-06-04 | Rev 1 |  |  | no |  |  |  |  | 3 | 2019-06-05 | Done
1797 | FWLAB - Tactical Center Lab Renovations | E190604e | 2019-06-04 | Addendum 2 |  |  | no |  |  |  |  | 1 | 2019-06-05 | Done
1841 | TJCH - The Joint Cedar Hill | E190605a | 2019-06-05 | Preliminary files | Sent questions |  | no |  |  |  |  | 0.5 | 2019-06-05 | Done
1842 | KSMY - KidsStrong McKinney | E190605b | 2019-06-05 | Proposal |  |  | no |  |  |  |  | 0.5 | 2019-06-05 | Done
1835 | JUMBO Hills Warehouse | E190606a | 2019-06-05 | Project Requirements |  |  | no | AI | [5 empty] | Not Done
1670 | Brookhaven Generator | E190606b | 2019-06-06 | RFIs 1 and 2 | Rfi 2 solved |  | no | Now |  |  |  | 3 | 2019-06-10 | Done
1843 | AIM-Artistry In Motion | E190610a | 2019-06-10 | Proposal |  |  | no |  |  |  |  | 0.5 | 2019-06-10 | Done
1793 | VERDEN - Verden Schools Elec Upgrade | E190610c | 2019-06-11 | M sheets |  |  | no |  |  |  |  | 4 | 2019-06-18 | Done
1793 | VERDEN - Verden Schools Elec Upgrade |  | 2019-06-11 | IFC |  |  | billed |  | 2019-06-18 | 2019-06-18 |  | 2 | 2019-06-18 | Done
1814 | MRGUN-Gun Range | E190611a | 2019-06-11 | Gun range plan |  |  | no | AI | [5 empty] | Not Done
1834 | TEMPLE - Temple High School |  | 2019-06-11 | Proposal |  |  | NO |  |  |  |  | 0.5 | 2019-06-11 | Done
1744 | Viandant Gelato Store - Denton | E190607b | 2019-06-13 | Proposed lighting fixtures | Sent request to Morrow |  | no |  |  |  |  | 1 | 2019-06-13 | Done
1793 | VERDEN - Verden Schools Elec Upgrade | E190614a | 2019-06-14 | M Equipment specs |  |  | no |  |  |  |  | 0.5 | 2019-06-14 | Done
1777 | BALKO Cafeteria Changes | E190614b | 2019-06-14 | PWR Submittal |  |  | no |  |  |  |  | 0.5 | 2019-06-14 | Done
1793 | VERDEN - Verden Schools Elec Upgrade | E190617b | 2019-06-17 | Final MP set |  |  | no |  |  |  |  | 2 | 2019-06-18 | Done
1766 | Xpress Wellness Duncan OK | E190617a | 2019-06-17 | changes to X-Ray room |  |  | no | [5 empty] | 2019-07-01 | Done
1768 | NRGV Volleyball Facility Mansfield | E190617c | 2019-06-17 | restroom changes | For permit comments |  | no | [5 empty] | 2019-06-28 | Done
1824 | CYL - Sauna Studio | E190617e | 2019-06-18 | Implement comments |  |  | no |  |  |  |  | 1 | 2019-06-20 | Done
1824 | CYL - Sauna Studio | E190618a | 2019-06-18 | Mirror light | Don't do it for now |  | billed |  |  |  |  | 0 | 2019-06-20 | Done
1808 | PCN-Putnam City North HS | E190618b | 2019-06-18 | Cafeteria Drawings | Cancelled |  | no | [5 empty] | 2019-07-20 | Done
1808 | PCN-Putnam City North HS | E190618c | 2019-06-18 | Kitchen Drawings | Cancelled |  | no | [5 empty] | 2019-07-20 | Done
1808 | PCN-Putnam City North HS | E190619a | 2019-06-19 | List of Equipment | Cancelled |  | no | [5 empty] | 2019-07-20 | Done
1845 | PADEN Schools | E190619c | 2019-06-19 | Proposal SV | TBC. Need to schedule |  | no |  |  | 2019-07-22 |  |  | 2019-08-23 | Done
1693 | The Table Church | E190619b | 2019-06-19 | New service routing revision | Revision 6 |  | no |  |  | 2019-06-20 |  | 0.5 | 2019-06-20 | Done
1792 | CELERIS - Celeris (2019) |  | 2019-06-20 | DFW DAS Markups |  |  | billed |  |  |  |  | 1 | 2019-06-20 | Done
1773 | COFW Worth Heights Multi-purpose TAS | E190611b | 2019-06-21 | Email contains comments |  |  | no |  |  |  |  | 2 | 2019-06-25 | Done
1773 | COFW Worth Heights Multi-purpose TAS | E190621a | 2019-06-21 | Alternates to verify |  |  | no |  |  |  |  | 1 | 2019-06-25 | Done
1766 | Xpress Wellness Duncan OK | E190621c | 2019-06-21 | ASI # 6 materials |  |  | billed |  |  |  |  | 2 | 2019-07-01 | Done
1784 | ITPWR DCCCD IT Closet Upgrades | E190626a | 2019-06-26 | Pre-construction Meeting |  |  | billed |  | 2019-06-28 | 2019-06-28 | 4 | 4 | 2019-06-28 | Done
1784 | ITPWR DCCCD IT Closet Upgrades | E190626a | 2019-06-26 | Submittals | Need to send review. |  | billed |  | 2019-06-25 |  |  | 2 | 2019-07-01 | Done
1629 | Heritage Glenn MOB Shell | E190627a | 2019-06-27 | LTG CTRLS Submittal |  |  | no |  |  |  |  | 1 | 2019-06-27 | Done
1772 | COFW North Tri-Ethnic CC TAS | E190620a | 2019-06-29 | Updated abase |  |  | no | [5 empty] | 2019-06-29 | Done
1797 | FWLAB - Tactical Center Lab Renovations | E190701a | 2019-07-01 | City Comments |  |  | no |  |  |  |  | 1 | 2019-07-09 | Done
1766 | Xpress Wellness Duncan OK | E190701b | 2019-07-01 | Split system info | ASI # 6 |  | billed |  |  |  |  | 1 | 2019-07-01 | Done
1772 | COFW North Tri-Ethnic CC TAS |  |  | IFR due 7/2 |  |  | billed | [5 empty] | 2019-07-02 | Done
1846 | BCFPE-Brookhaven College Switchgear | E190701c | 2019-07-02 | Proposal |  |  | no |  |  |  |  | 2 | 2019-07-03 | Done
1847 | TJGP-The Joint Grand Prairie | E190627b | 2019-06-27 | Existing Drawings |  |  | no |  |  |  |  | 2 | 2019-07-18 | Done
1797 | FWLAB - Tactical Center Lab Renovations | E190702a | 2019-07-02 | City Comments |  |  | no |  |  |  |  | 1 | 2019-07-08 | Done
1848 | FRS- Forney Retail Shell | E190702b | 2019-07-02 | Proposal |  |  | no |  |  |  |  | 0.5 | 2019-07-02 | Done
1844 | BLKELEM Balko Elementary |  | 2019-07-03 | Proposal |  |  | no |  |  |  |  | 1 | 2019-07-03 | Done
1581 | Crescent Schools | E190703a | 2019-07-03 | Panelboard submittal |  |  | no |  |  |  |  | 1 | 2019-07-03 | Done
1808 | PCN-Putnam City North HS | E190702e | 2019-07-08 | Generator Sizing | Prelim size= 50kw |  | no | [5 empty] | 2019-08-06 | Done
1849 | HEMP - Hemphill St Church | E190708a | 2019-07-08 | Proposal |  |  | no |  |  |  |  | 1 | 2019-07-08 | Done
1844 | BLKELEM Balko Elementary | E190708b | 2019-07-08 | Section dimensions |  |  | no |  |  |  |  | 0.5 | 2019-07-08 | Done
1845 | PADEN Schools | E190708c | 2019-07-08 | SV | PDF on email. Need to reschedule |  | no |  | 2019-07-10 | 2019-07-10 | 8 | 0 | 2019-07-10 | Done
1835 | JUMBO Hills Warehouse | E190708d | 2019-07-08 | CAD files | Need questions for architect |  | no |  |  | 2019-07-09 |  | 1 | 2019-07-09 | Done
1531 | MLK Drop-off Changes | E190708e | 2019-07-08 | Submittals |  |  | billed |  |  | 2019-07-09 |  | 2 | 2019-07-09 | Done
1787 | MANS Mansfield Shell | E190708f | 2019-07-08 | Updated plans and base files | For permit comments |  | no |  |  |  |  | 2 | 2019-07-18 | Done
1850 | CFWC - Calvary Family Worship Center | E190708g | 2019-07-08 | Proposal |  |  | no |  |  |  |  | 0.5 | 2019-07-09 | Done
1808 | PCN-Putnam City North HS | E190708h | 2019-07-09 | Is Generator gas or diesel? | Gas |  | no | [5 empty] | 2019-07-10 | Done
1825 | NWCC - North West Church of Christ | E190709b | 2019-07-11 | Site Visit |  |  | yes | later | 2019-07-12 | 2019-07-12 | 4 | 4 | 2019-07-12 | Done
1851 | SGCM-Sovereign Grace Church Midland | E190709c | 2019-07-11 | Proposal |  |  | no |  |  |  |  | 1 | 2019-07-11 | Done
1808 | PCN-Putnam City North HS | E190710a | 2019-07-11 | Generator is Natural Gas |  |  | no | [5 empty] | 2019-08-06 | Done
1808 | PCN-Putnam City North HS | E190710b | 2019-07-11 | Base files. |  |  | no |  |  | 2019-07-20 |  |  | 2019-08-01 | Done
1531 | MLK Drop-off Changes | E190709d | 2019-07-11 | LTG and LTG Controls Submittals |  |  | no |  | 2019-07-11 | 2019-07-11 |  | 3 | 2019-07-15 | Done
1845 | PADEN Schools |  | 2019-07-11 | Proposal |  |  | no |  |  |  |  | 1 | 2019-07-24 | Done
1847 | TJGP-The Joint Grand Prairie | E190710d | 2019-07-11 | Base files. |  |  | no |  |  | 2019-07-12 |  | 3 | 2019-07-18 | Done
1811 | XWDGE-Xpress Wellness Dodge City OK | E190711a | 2019-07-11 | Submittal |  |  | billed |  |  | 2019-07-11 |  | 1 | 2019-07-11 | Done
1810 | XWGUY-Xpress Wellness Guymon OK | E190711b | 2019-07-11 | Submittal |  |  | billed |  |  | 2019-07-11 |  | 1 | 2019-07-11 | Done
1754 | Viandant Gelato Store - Gainsville | E190711d | 2019-07-15 | Base files. |  |  | no | AI |  | 2019-07-21 |  | 3 | 2019-09-09 | Done
1852 | AFCC-Armed Forces Career Center | E190715a | 2019-07-15 | Proposal |  |  | no |  |  |  |  | 0.5 | 2019-07-15 | Done
1762 | Stonebridge MOB Shells | E190715b | 2019-07-15 | Updated base files |  |  | no | AI |  | 2019-07-20 |  |  |  | Not Done
1787 | MANS Mansfield Shell | E190716a | 2019-07-16 | ASA Proposal |  |  | no |  |  |  |  | 0.5 | 2019-07-16 | Done
1847 | TJGP-The Joint Grand Prairie | E190717a | 2019-07-17 | IFC due | See email for final instructions |  | billed |  | 2019-07-18 | 2019-07-18 |  | 2 | 2019-07-18 | Done
1812 | XWGB-Xpress Wellness Great Bend OK | E190717b | 2019-07-17 | FA Letter |  |  | no |  |  |  |  | 1 | 2019-07-18 | Done
1814 | MRGUN-Gun Range | E190716b | 2019-07-17 | Updated model |  |  | no | AI |  | 2019-07-20 |  |  |  | Not Done
1835 | JUMBO Hills Warehouse | E190716c | 2019-07-17 | Answers to questions | See email |  | no | AI | [5 empty] | Not Done
1808 | PCN-Putnam City North HS | E190717c | 2019-07-17 | Updated shelter model | Provide feedback - See reference folder |  | no | [5 empty] | 2019-07-25 | Done
1754 | Viandant Gelato Store - Gainsville | E190717d | 2019-07-17 | Coffee Maker info | In Reference folder |  | no | AI |  |  |  | 3 | 2019-09-09 | Done
1754 | Viandant Gelato Store - Gainsville | E190717e | 2019-07-17 | Answers to questions | See email + Ais |  | no | AI |  |  |  | 3 | 2019-09-09 | Done
1835 | JUMBO Hills Warehouse | E190717f | 2019-07-19 | Break room equipment |  |  | no | AI | [5 empty] | Not Done
1853 | TJMP-The Joint Montgomery Plaza | E190718a | 2019-07-19 | Base files. |  |  | no |  |  | 2019-07-21 |  |  | 2019-07-23 | Done
1835 | JUMBO Hills Warehouse | E190718b | 2019-07-19 | More Reqs |  |  | no | AI | [5 empty] | Not Done
1835 | JUMBO Hills Warehouse | E190718c | 2019-07-19 | Arch set for review |  |  | no | AI | [5 empty] | Not Done
1531 | MLK Drop-off Changes | E190719b | 2019-07-19 | PWR Submittal |  |  | no |  |  | 2019-07-20 | 1 | 1 | 2019-07-20 | Done
1835 | JUMBO Hills Warehouse | E190718d | 2019-07-19 | Base files. |  |  | no | AI |  | 2019-07-20 |  |  |  | Not Done
1808 | PCN-Putnam City North HS | E190722a | 2019-07-22 | Updated information | Need to make comments |  | no | Now |  |  |  |  | 2019-07-22 | Done
1808 | PCN-Putnam City North HS | E190722b | 2019-07-22 | Need questions for maintenance |  |  | no | Now |  |  |  |  | 2019-07-22 | Done
1812 | XWGB-Xpress Wellness Great Bend OK | E190722c | 2019-07-22 | LTG Submittal |  |  | billed |  |  |  |  | 1 | 2019-07-23 | Done
1716 | Humane Society Animal Shelter | E190722d | 2019-07-22 | Proposal for new HVAC |  |  | no |  |  |  |  | 1 | 2019-07-24 | Done
1600 | Gun Experience | E190724a | 2019-07-24 | Shop Equipment Narrative |  |  | billed |  |  |  |  | 3 | 2019-07-24 | Done
1600 | Gun Experience | E190724c | 2019-07-24 | More changes | Rev 5? |  | NO | [5 empty] | 2019-07-31 | Done
1762 | Stonebridge MOB Shells | E190726a | 2019-07-26 | Sconce informaton | See email |  | no |  |  |  |  | 1 | 2019-07-28 | Done
1844 | BLKELEM Balko Elementary | E190725a | 2019-07-25 | Prelim Lighting | See email and ACAD folder |  | yes | AI | [5 empty] | Not Done
1808 | PCN-Putnam City North HS | E190725b | 2019-07-25 | Update base files |  |  | no | [5 empty] | 2019-07-25 | Done
1808 | PCN-Putnam City North HS | E190725c | 2019-07-25 | Update base files |  |  | no | [5 empty] | 2019-07-25 | Done
1812 | XWGB-Xpress Wellness Great Bend OK | E190725d | 2019-07-25 | Gear Submittal |  |  | billed | Now |  |  |  | 1 | 2019-07-31 | Done
1614 | Euless Library | E190726b | 2019-07-26 | Revision to ASI # 2 |  |  | no |  |  |  |  | 0.5 | 2019-07-26 | Done
1614 | Euless Library | E190726c | 2019-07-26 | RFI # 38 |  |  | no |  |  |  |  | 0.5 | 2019-07-26 | Done
1581 | Crescent Schools | E190731a | 2019-07-31 | LTG Submittal |  |  | billed |  |  |  |  | 1 | 2019-07-31 | Done
1837 | DRALCO | E190731b | 2019-07-31 | Proposal |  |  | no |  |  |  |  | 1 | 2019-07-31 | Done
1808 | PCN-Putnam City North HS | E190725e | 2019-07-25 | Email comments |  |  | no | [5 empty] | 2019-08-06 | Done
1808 | PCN-Putnam City North HS | E190729a | 2019-07-29 | Email comments |  |  | no | [5 empty] | 2019-08-06 | Done
1808 | PCN-Putnam City North HS | E190729b | 2019-07-29 | Answers to questions |  |  | no | [5 empty] | 2019-08-06 | Done
1808 | PCN-Putnam City North HS | E190729c | 2019-07-29 | Fixture requests |  |  | no | [5 empty] | 2019-08-06 | Done
1808 | PCN-Putnam City North HS | E190730b | 2019-07-30 | Section updates |  |  | no | [5 empty] | 2019-08-06 | Done
1808 | PCN-Putnam City North HS | E190731c | 2019-07-31 | Drain updates |  |  | no | [5 empty] | 2019-08-06 | Done
1808 | PCN-Putnam City North HS | E190731d | 2019-07-31 | Plumbing questions |  |  | no | [5 empty] | 2019-08-06 | Done
1808 | PCN-Putnam City North HS | E190731e | 2019-07-31 | Updated RCP and base file |  |  | no | [5 empty] | 2019-08-01 | Done
1808 | PCN-Putnam City North HS | E190731f | 2019-07-31 | Updated base file |  |  | no | [5 empty] | 2019-08-01 | Done
1841 | TJCH - The Joint Cedar Hill | E190801b | 2019-08-01 | Updated base file + border |  |  | no |  |  |  |  | 3 | 2019-08-06 | Done
1808 | PCN-Putnam City North HS | E190801c | 2019-08-01 | Base file update |  |  | no | [5 empty] | 2019-08-01 | Done
1808 | PCN-Putnam City North HS | E190801d | 2019-08-01 | Data + reqs |  |  | no | [5 empty] | 2019-08-06 | Done
1705 | North Fort Worth Baptist Church | E190801e | 2019-08-01 | Submittals | LTG + CRTLS |  | no | Now |  |  |  | 1 | 2019-08-05 | Done
1835 | JUMBO Hills Warehouse | E190801f | 2019-08-01 | New location for panels |  |  | no | AI | [5 empty] | Not Done
1808 | PCN-Putnam City North HS | E190801g | 2019-08-01 | Qs and As |  |  | no | [5 empty] | 2019-08-06 | Done
1808 | PCN-Putnam City North HS | E190729c | 2019-08-01 | IFR 95% CD |  |  | yes |  | 2019-08-07 | 2019-08-07 |  |  | 2019-08-06 | Done
1808 | PCN-Putnam City North HS | E190729c | 2019-08-01 | IFC due | Need better date |  | yes | IFC | 2019-08-14 | 2019-08-14 |  |  |  | Not Done
1855 | KECO Lab | E190802a | 2019-08-02 | Proposal |  |  | no |  |  |  |  | 0.5 | 2019-08-02 | Done
1762 | Stonebridge MOB Shells | E190726a | 2019-08-02 | Changes are coming |  |  | no | AI | [5 empty] | Not Done
1762 | Stonebridge MOB Shells | E190802b | 2019-08-02 | Civil permit comments | See email for files |  | no |  |  |  |  | 0 | 2019-08-02 | Done
1844 | BLKELEM Balko Elementary | E190802c | 2019-08-02 | Border |  |  | no | AI | [5 empty] | Not Done
1853 | TJMP-The Joint Montgomery Plaza |  | 2019-07-15 | IFC due |  |  | billed | [5 empty] | 2019-07-23 | Done
1854 | TJMK - The Joint McKinney |  | 2019-07-15 | IFC |  |  | billed | [5 empty] | 2019-07-30 | Done
1792 | CELERIS - Celeris (2019) |  | 2019-07-15 | Project |  |  | billed | [5 empty] | 2019-07-15 | Done
1814 | MRGUN-Gun Range | E190802 | 2019-08-02 | Revit update |  |  | no | AI | [5 empty] | Not Done
1857 | SUMMIT-Summit Middle Schools | E190805a | 2019-08-05 | LTG Calcs |  |  | no |  |  |  |  | 2 | 2019-08-05 | Done
1600 | Gun Experience | E190805c | 2019-08-05 | FA Submittal |  |  | no | [5 empty] | 2019-08-05 | Done
1847 | TJGP-The Joint Grand Prairie | E190805d | 2019-08-06 | Rev 1 materials |  |  | no |  |  |  |  | 0.5 | 2019-08-06 | Done
1754 | Viandant Gelato Store - Gainsville | E190806b | 2019-08-06 | Dishwasher information |  |  | no | AI |  |  |  | 3 | 2019-09-09 | Done
1845 | PADEN Schools | E190806a | 2019-08-06 | Scope of work |  |  | no | AI |  |  |  | 2 | 2019-09-24 | Done
1762 | Stonebridge MOB Shells | E190806c | 2019-08-06 | Service wireway location |  |  | no | AI | [5 empty] | Not Done
1841 | TJCH - The Joint Cedar Hill | E190806d | 2019-08-06 | Lana's comments |  |  | no |  |  |  |  | 1 | 2019-08-06 | Done
1754 | Viandant Gelato Store - Gainsville | E190807b | 2019-08-07 | FA by owners contractor |  |  | no | AI |  |  |  | 3 | 2019-09-09 | Done
1762 | Stonebridge MOB Shells | E190807d | 2019-08-07 | Xfrmr Location |  |  | no | AI | [5 empty] | Not Done
1845 | PADEN Schools | E190807c | 2019-08-07 | Prelim kitchen info |  |  | no | AI |  |  |  | 2 | 2019-09-24 | Done
1766 | Xpress Wellness Duncan OK | E190812a | 2019-08-12 | ASI 10 |  |  | yes |  |  |  |  | 1.5 | 2019-08-13 | Done
1845 | PADEN Schools | E190812b | 2019-08-12 | Site Visit |  |  | no |  |  |  |  | 10 | 2019-08-23 | Done
1859 | GARDEN-Garden Park Apartments | E190812c | 2019-08-12 | Proposal |  |  | no |  |  |  |  | 0.5 | 2019-08-12 | Done
1583 | 7 City Church | E190814a | 2019-08-14 | Fault Calcs |  |  | no |  |  |  |  | 0.5 | 2019-08-14 | Done
1840 | SUPERIOR - Livestock Auction | E190813a | 2019-08-15 | Base files |  |  | no | AI | [5 empty] | Not Done
1705 | North Fort Worth Baptist Church | E190814b | 2019-08-15 | LTG re submittal |  |  | no |  |  |  |  | 0.5 | 2019-08-15 | Done
1814 | MRGUN-Gun Range | E190814c | 2019-08-15 | Qs and As |  |  | no | AI | [5 empty] | Not Done
1772 | COFW North Tri-Ethnic CC TAS | E190815a | 2019-08-15 | Final Comments and base update |  |  | no |  |  |  |  | 1 | 2019-08-23 | Done
1772 | COFW North Tri-Ethnic CC TAS | E190815a | 2019-08-15 | IFC |  |  | yes |  | 2019-08-23 |  |  | 1 | 2019-08-23 | Done
1861 | SERVE-Serve Denton | E190816a | 2019-08-16 | Proposal |  |  | no |  |  |  |  | 0.5 | 2019-08-16 | Done
1840 | SUPERIOR - Livestock Auction | E190813a | 2019-08-15 | Generate questions |  |  | no |  |  |  |  | 1.5 | 2019-08-16 | Done
1853 | TJMP-The Joint Montgomery Plaza | E190819a | 2019-08-19 | IFC | comments |  | no |  |  |  |  | 1 | 2019-08-19 | Done
1600 | Gun Experience | E190820c | 2019-08-20 | Wiring Devices Submittal |  |  | no |  |  |  |  | 0.5 | 2019-08-20 | Done
1840 | SUPERIOR - Livestock Auction | E190820a | 2019-08-20 | LTG Calcs | Requested from Jim |  | no | AI | [5 empty] | Not Done
1864 | AKP-Amazing Kids Pediatric | E190820d | 2019-08-20 | Proposal | Meeting on 8/22 @ 1:30 PM |  | no | PROP |  |  |  | 1 | 2019-08-26 | Done
1829 | CALHB-Calumet Hitting Building | E190821a | 2019-08-21 | OSFM Letter |  |  | no |  |  |  |  | 0.5 | 2019-08-21 | Done
1754 | Viandant Gelato Store - Gainsville | E190821b | 2019-08-21 | CC to discuss equipment | Review materials |  | no | AI |  | 2019-08-21 | 3 | 3 | 2019-09-09 | Done
1835 | JUMBO Hills Warehouse | E190821c | 2019-08-21 | Change voltage and final comments |  |  | no | AI | [5 empty] | Not Done
1847 | TJGP-The Joint Grand Prairie | E190821d | 2019-08-21 | D2 to LT change |  |  | no |  |  |  |  | 0.5 | 2019-08-21 | Done
1808 | PCN-Putnam City North HS | E190817a | 2019-08-21 | Review meeting notes |  |  | no | AI | [5 empty] | Not Done
1840 | SUPERIOR - Livestock Auction | E190820e | 2019-08-21 | Fober Optic Instructions |  |  | no | AI | [5 empty] | Not Done
1840 | SUPERIOR - Livestock Auction | E190820f | 2019-08-21 | Qs and As |  |  | no | AI | [5 empty] | Not Done
1840 | SUPERIOR - Livestock Auction | E190821e | 2019-08-21 | LTG info from Jim |  |  | no | AI | [5 empty] | Not Done
1844 | BLKELEM Balko Elementary | E190820g | 2019-08-21 | Temporary Power | Need background |  | no | RFI |  |  |  | 6 | 2019-09-09 | Done
1809 | XWARD-Xpress Wellness Ardmore OK | E190821f | 2019-08-21 | Submittal |  |  | yes | SUB |  |  |  | 1 | 2019-08-25 | Done
1773 | COFW Worth Heights Multi-purpose TAS | E190821g | 2019-08-21 | Addendum items | from pre-bid |  | no | AI | 2019-08-30 |  |  |  |  | Not Done
1834 | TEMPLE - Temple High School | E190821h | 2019-08-21 | Base files |  |  | no | AI | [5 empty] | Not Done
1841 | TJCH - The Joint Cedar Hill | E190822a | 2019-08-22 | Revision 1 |  |  | no |  |  |  |  | 1 | 2019-08-22 | Done
1705 | North Fort Worth Baptist Church | E190822b | 2019-08-23 | Submittal |  |  | no | SUB |  |  |  | 1 | 2019-08-25 | Done
1801 | HOU -- Univ of Houston Transmitter | E190822d | 2019-08-23 | Base files |  |  | no | AI | [5 empty] | Not Done
1801 | HOU -- Univ of Houston Transmitter | E190822c | 2019-08-23 | Generator calcs |  |  | no | RFI |  |  |  | 1 | 2019-08-25 | Done
1862 | TWUBUS-TWU Bus Stop | E190822e | 2019-08-23 | Proposal |  |  | no | PROP |  |  |  | 1 | 2019-08-25 | Done
1863 | TWU-Locust Office Renovation | E190822f | 2019-08-23 | Proposal | Time includes mkt sv |  | no | PROP |  |  |  | 3 | 2019-08-26 | Done
1600 | Gun Experience | E190823a | 2019-08-23 | RFI 66 |  |  | no | RFI |  |  |  | 0.5 | 2019-08-23 | Done
1865 | FC-Fort Capital Addison | E190823b | 2019-08-23 | Proposal |  |  | no | PROP |  |  |  | 1 | 2019-08-26 | Done
1837 | DRALCO | E190822g | 2019-08-23 | Project Information |  |  | no | AI | [5 empty] | Not Done
1814 | MRGUN-Gun Range | E190823c | 2019-08-23 | Dominator information |  |  | no | AI | [5 empty] | Not Done
1840 | SUPERIOR - Livestock Auction | E190823d | 2019-08-23 | Generator requirements |  |  | no | AI | [5 empty] | Not Done
1840 | SUPERIOR - Livestock Auction | E190823f | 2019-08-23 | Generator specific reqs |  |  | no | AI | [5 empty] | Not Done
1829 | CALHB-Calumet Hitting Building | E190823e | 2019-08-23 | Base Files |  |  | no | AI |  |  |  | 1 | 2019-09-01 | Done
1844 | BLKELEM Balko Elementary | E190826a | 2019-08-26 | Utility Package IFC |  |  | no | IFC | 2019-09-05 |  |  |  | 2019-09-07 | Done
1844 | BLKELEM Balko Elementary | E190826a | 2019-08-26 | IFC |  |  | no | IFC | 2019-09-19 |  |  |  | 2019-09-07 | Done
1834 | TEMPLE - Temple High School | E190826a | 2019-08-26 | IFC |  |  | yes | IFC | 2019-09-10 |  |  |  |  | Not Done
1808 | PCN-Putnam City North HS | E190826a | 2019-08-26 | IFC |  |  | yes | IFC | 2019-09-12 |  |  |  |  | Not Done
1845 | PADEN Schools | E190826a | 2019-08-26 | IFC |  |  | yes | IFC | 2019-09-26 |  |  |  |  | Not Done
1860 | TURPIN-Turpin Schools | E190826a | 2019-08-26 | IFC |  |  | yes | IFC | 2019-10-03 |  |  |  |  | Not Done
1829 | CALHB-Calumet Hitting Building | E190826a | 2019-08-26 | IFC |  |  | yes | IFC | 2019-09-05 |  |  |  |  | Not Done
1866 | WLM-WL McNatt | E190826a | 2019-08-26 | IFC |  |  | yes | IFC | 2019-09-30 |  |  |  |  | Not Done
1829 | CALHB-Calumet Hitting Building | E190826b | 2019-08-26 | Reqs |  |  | no | AI |  |  |  | 1 | 2019-09-01 | Done
1801 | HOU -- Univ of Houston Transmitter | E190826c | 2019-08-26 | Size generator | Based on new information |  | no | RFI |  |  |  |  | 2019-09-09 | Done
1844 | BLKELEM Balko Elementary | E190826d | 2019-08-26 | CAD files for utilities package |  |  | no | AI | [5 empty] | Not Done
1762 | Stonebridge MOB Shells | E190826e | 2019-08-26 | Base file update |  |  | no | AI | [5 empty] | Not Done
1705 | North Fort Worth Baptist Church | E190826f | 2019-08-26 | RFI # 5 |  |  | no | RFI |  |  |  | 0.5 | 2019-08-26 | Done
1814 | MRGUN-Gun Range | E190826g | 2019-08-26 | Data + reqs |  |  | no | AI | [5 empty] | Not Done
1840 | SUPERIOR - Livestock Auction | E190826h | 2019-08-26 | Review Photometrics |  |  | no | AI | [5 empty] | Not Done
1773 | COFW Worth Heights Multi-purpose TAS | E190821g | 2019-08-28 | Addendum 3 dated 8/30 | Wait for more Qs |  | no | IFC | 2019-08-30 |  |  |  |  | Not Done
1801 | HOU -- Univ of Houston Transmitter | E190827a | 2019-08-29 | Cut sheet |  |  | no | AI | [5 empty] | Not Done
1829 | CALHB-Calumet Hitting Building | PH190828 | 2019-08-29 | Voltage 240/120V 1ph | Per phone conversation with Tim |  | no | AI |  |  |  | 1 | 2019-09-01 | Done
1865 | FC-Fort Capital Addison | E190823b | 2019-08-30 | SV |  |  | no | SV | 2019-09-06 |  |  | 3 | 2019-09-06 | Done
1705 | North Fort Worth Baptist Church | E190828a | 2019-08-30 | Xfrmr TP submittal |  |  | no | SUB |  |  |  | 0.5 | 2019-08-30 | Done
1844 | BLKELEM Balko Elementary | E190828b | 2019-08-30 | Review arch floor plan |  |  | no | AI | [5 empty] | Not Done
1779 | MEL5K Melissa 5.3K SF Shell | E190828c | 2019-08-30 | Shunt trip issue | Issued revision 2 |  | no | RFI |  |  |  | 2 | 2019-09-05 | Done
1705 | North Fort Worth Baptist Church | E190822b | 2019-08-30 | FA Submittal |  |  | no | SUB |  |  |  | 1 | 2019-09-05 | Done
1829 | CALHB-Calumet Hitting Building | E190828d | 2019-08-30 | Reqs |  |  | no | AI |  |  |  | 1 | 2019-09-01 | Done
1829 | CALHB-Calumet Hitting Building | E190828e | 2019-08-30 | Specs on drawings |  |  | no | AI |  |  |  | 1 | 2019-09-01 | Done
1705 | North Fort Worth Baptist Church | E190903c | 2019-09-04 | LTG Submittal |  |  | no | SUB |  |  |  | 1 | 2019-09-05 | Done
1858 | GP-Glamour Paws | E190903d | 2019-09-04 | Proposal |  |  | no | PROP |  |  |  | 1 | 2019-09-10 | Done
1779 | MEL5K Melissa 5.3K SF Shell | E190905b | 2019-09-05 | Rev 2 |  |  | no | IFC |  | 2019-09-05 |  | 1 | 2019-09-05 | Done
1868 | HULEN Park Place Office | E190905c | 2019-09-05 | MP Set |  |  | no | AI |  |  |  | 2 | 2019-09-09 | Done
1865 | FC-Fort Capital Addison | E190905d | 2019-09-05 | SV |  |  | yes | SV | 2019-09-06 |  |  | 0 | 2019-09-06 | Done
1844 | BLKELEM Balko Elementary | E190906a | 2019-09-06 | Utility Package IFC | By 9/9 @ 10 AM |  | yes | IFC | 2019-09-09 |  |  | 1 | 2019-09-07 | Done
1754 | Viandant Gelato Store - Gainsville | E190906b | 2019-09-06 | Bathroom fixture |  |  | no | AI |  |  |  | 3 | 2019-09-09 | Done
1864 | AKP-Amazing Kids Pediatric | E190906c | 2019-09-06 | Base files and content |  |  | no | AI | [5 empty] | Not Done
1869 | FMSHELL - Flowermound Office Shell | E190906d | 2019-09-06 | Proposal |  |  | no | PROP |  |  |  | 2 | 2019-09-09 | Done
1801 | HOU -- Univ of Houston Transmitter | E190903e | 2019-09-06 | Existing Drawings |  |  | no | AI | [5 empty] | Not Done
1801 | HOU -- Univ of Houston Transmitter | E190904a | 2019-09-06 | Proposed Section |  |  | no | AI | [5 empty] | Not Done
1865 | FC-Fort Capital Addison |  | 2019-09-06 | IFR |  |  | no | IFC | 2019-09-26 |  |  |  | 2019-09-16 | Done
1870 | MEL2 - Melissa Lot # 2 | E190906g | 2019-09-06 | Proposal |  |  | no | PROP |  |  |  | 1 | 2019-09-09 | Done
1754 | Viandant Gelato Store - Gainsville | E190906j | 2019-09-06 | Updated base files |  |  | no | AI |  |  |  | 3 | 2019-09-09 | Done
1705 | North Fort Worth Baptist Church | E190906h | 2019-09-06 | RFI 7 |  |  | no | RFI |  |  |  |  | 2019-09-06 | Done
1754 | Viandant Gelato Store - Gainsville |  | 2019-09-09 | IFC |  |  | yes | IFC | 2019-09-11 | 2019-09-10 |  |  |  | Not Done
1868 | HULEN Park Place Office |  | 2019-09-09 | IFC |  |  | yes |  |  |  |  | 2 | 2019-09-09 | Done
1841 | TJCH - The Joint Cedar Hill | E190909b | 2019-09-09 | Rev 2 - City Comments |  |  | no |  |  |  |  | 1 | 2019-09-09 | Done
1629 | Heritage Glenn MOB Shell | E190911a | 2019-09-11 | RFI 27 |  |  | no | RFI |  |  |  | 0.5 | 2019-09-11 | Done
1808 | PCN-Putnam City North HS | E190909c | 2019-09-09 | Updated base files | superceded |  | no | AI |  |  |  |  | 2019-09-11 | Done
1808 | PCN-Putnam City North HS | E190911b | 2019-09-11 | Changes Proposal |  |  | no | PROP |  |  |  | 0.5 | 2019-09-16 | Done
1808 | PCN-Putnam City North HS | E190910a | 2019-09-11 | Updated base files |  |  | no | AI | [5 empty] | Not Done
1835 | JUMBO Hills Warehouse | E190910b | 2019-09-11 | Changes Proposal |  |  | no | PROP |  |  |  | 1 | 2019-09-11 | Done
1600 | Gun Experience | E190911c | 2019-09-11 | RFI 70 |  |  | no | RFI | [5 empty] | Not Done
1801 | HOU -- Univ of Houston Transmitter | E190910c | 2019-09-11 | Generate questions |  |  | no | RFI | [5 empty] | Not Done
1796 | IAGULLI - Castle NRH MOB | E190910d | 2019-09-11 | Updated base files |  |  | no | AI | [5 empty] | Not Done
1796 | IAGULLI - Castle NRH MOB | E190910e | 2019-09-11 | Civil Set for Review |  |  | no | AI | [5 empty] | Not Done
1801 | HOU -- Univ of Houston Transmitter | E190906f | 2019-09-11 | Review emails |  |  | no | AI | [5 empty] | Not Done
1810 | XWGUY-Xpress Wellness Guymon OK | E190911d | 2019-09-11 | Review emails |  |  | no | AI | [5 empty] | Not Done
1865 | FC-Fort Capital Addison | E190912a | 2019-09-11 | As to Qs and updated base file |  |  | no | AI |  |  |  |  | 2019-09-16 | Done
1837 | DRALCO | E190916a | 2019-09-16 | Owner comments |  |  | yes | IFC | [5 empty] | Not Done
1865 | FC-Fort Capital Addison | E190916b | 2019-09-16 | Project Canceled |  |  | billed | AI |  |  |  | 0.5 | 2019-09-16 | Done
1872 | PV-Park Ventura | E190916c | 2019-09-16 | Proposal |  |  | no | PROP | [5 empty] | Not Done
1867 | UCO-UCO Test Engine | E190910f | 2019-09-16 | Site Visit |  |  | no | SV |  |  |  | 8 | 2019-09-13 | Done
1867 | UCO-UCO Test Engine | E190916d | 2019-09-16 | Proposal |  |  | no | PROP |  |  |  | 1 | 2019-09-16 | Done
1864 | AKP-Amazing Kids Pediatric | E190904b | 2019-09-16 | Qs and As | Includes official name |  | no | RFI | [5 empty] | Not Done
1840 | SUPERIOR - Livestock Auction | E190916e | 2019-09-16 | Border with sheet numbering info |  |  | no | AI | [5 empty] | Not Done
1808 | PCN-Putnam City North HS | E190916f | 2019-09-16 | Confirm IT room power |  |  | no | AI | [5 empty] | Not Done
1796 | IAGULLI - Castle NRH MOB | E190906g | 2019-09-16 | Qs and As and updated base file |  |  | no | AI | [5 empty] | Not Done
1840 | SUPERIOR - Livestock Auction | E190906j | 2019-09-16 | Updated base files |  |  | no | AI | [5 empty] | Not Done
1834 | TEMPLE - Temple High School | E190918a | 2019-09-18 | MP Coordination |  |  | no | AI | [5 empty] | Not Done
1834 | TEMPLE - Temple High School | E190918c | 2019-09-18 | Updated base files |  |  | no | AI | [5 empty] | Not Done
1531 | MLK Drop-off Changes | E190918d | 2019-09-18 | RFI 15 |  |  | no | RFI |  |  |  | 0.5 | 2019-09-18 | Done
1864 | AKP-Amazing Kids Pediatric | E190917b | 2019-09-18 | HVAC info |  |  | no | AI | [5 empty] | Not Done
1835 | JUMBO Hills Warehouse | E190918e | 2019-09-18 | Updated plans and base files |  |  | no | AI | [5 empty] | Not Done
1801 | HOU -- Univ of Houston Transmitter | E190919a | 2019-09-19 | Border |  |  | no | AI | [5 empty] | Not Done
1478 | Handley Meadowbrook Rec Center | E190923a | 2019-09-23 | Record set |  |  | no | AI |  |  |  | 1 | 2019-09-27 | Done
1477 | Eugene McCray Recreation Center | E190923a | 2019-09-23 | Record set |  |  | no | AI |  |  |  | 1 | 2019-09-27 | Done
1867 | UCO-UCO Test Engine | E190920a | 2019-09-23 | Base Files |  |  | no | AI |  |  |  | 1 | 2019-09-24 | Done
1806 | XWGUT - Xpress Wellness Guthrie OK | E190919a | 2019-09-23 | Code Lettter |  |  | no | AI |  |  |  | 1 | 2019-09-23 | Done
1801 | HOU -- Univ of Houston Transmitter | E190921a | 2019-09-23 | Generator information |  |  | no | AI | [5 empty] | Not Done
1873 | AAC - Argyle Activity Center | E190919b | 2019-09-23 | Proposal |  |  | no | AI |  |  |  | 2 | 2019-09-23 | Done
1759 | KHSH-Keller-Haslet Restaurant Shell | E190922a | 2019-09-23 | Base files |  |  | no | AI | [5 empty] | Not Done
1840 | SUPERIOR - Livestock Auction | E190923c | 2019-09-23 | Updated base files |  |  | no | AI | [5 empty] | Not Done
1845 | PADEN Schools | E190923d | 2019-09-23 | Updated base files |  |  | no | AI |  |  |  | 1 | 2019-09-24 | Done
1796 | IAGULLI - Castle NRH MOB | E190923e | 2019-09-23 | Photometrics and LFS |  |  | no | AI | [5 empty] | Not Done
1732 | City of Lake Worth Projects | E190924a | 2019-09-24 | Submittals |  |  | yes | SUB |  |  |  | 2 | 2019-09-24 | Done
1844 | BLKELEM Balko Elementary | E190924b | 2019-09-24 | Comments to utility package | No electrical comments |  | no | AI |  |  |  | 0 | 2019-09-24 | Done
1825 | NWCC - North West Church of Christ |  | 2019-09-24 | NTP |  |  | no | AI |  |  |  | 0 | 2019-09-24 | Done
1840 | SUPERIOR - Livestock Auction | E190924c | 2019-09-24 | Lift Station | Boost transformer may be needed. |  | no | AI | [5 empty] | Not Done
1844 | BLKELEM Balko Elementary | E190227a | 2019-09-27 | Utility Package IFC comments |  |  | no | AI | [5 empty] | Not Done
| #N/A | [12 empty] | #N/A
| #N/A | [12 empty] | #N/A
| #N/A | [12 empty] | #N/A
| #N/A | [12 empty] | #N/A
| #N/A | [12 empty] | #N/A
| #N/A | [12 empty] | #N/A
| #N/A | [12 empty] | #N/A
| #N/A | [12 empty] | #N/A
| #N/A | [12 empty] | #N/A
| #N/A | [12 empty] | #N/A
| #N/A | [12 empty] | #N/A
| #N/A | [12 empty] | #N/A

## Projects
PN | Project Name
HM | Home Projects
MKT | Marketing
OPS | Operations
TEMP | Template Project
church | Church Template
Office | Office Template
TJ | The Joint Site Adapt Checklist
0804 | Website and MKT materials
0805 | Liability Insurance
0806 | UNT Arts Building Upgrade
0807 | MARE, Inc.
0808 | TX Facilities PM Services
0809 | Health Insurance
0810 | Accounting Services
0811 | Lonestar Customs
0812 | Fort Brag Manchu Wok
0813 | Fort Meade Taco Bell
0814 | DCCCD North Lake Remodel
0815 | DCCCD MVC Remodel
0816 | DCCCD Eastfield Remodel
0817 | DCCCD Richland Remodel
0818 | T-Mobile
0819 | Celeris
0820 | TAMUS Submittal Review
0821 | EPB Associates
0822 | Crossroads Wireless
0823 | Avalon Stone Products
0824 | Fort Worth Transportation Authority
0825 | FWISD Technology Design
0826 | Dannon energy Assessment
0827 | FWISD Bond Package
0828 | Mission Sales Tax
0829 | Bimbo Sales Tax
0830 | FWISD Sagamore ES
0831 | FWISD Meadowbrook ES
0832 | FWISD Polytechnic HS
0833 | FWISD William James MS
0834 | Popeye's
0835 | DCCCD 2008-2009
0836 | Oculus Teel Crossing 1
0837 | DCCCD MVC Cooling Tower
0838 | DCCCD MVC Pool Remodel
0839 | DCCCD CV Switchgear replacement
0840 | DCCCD EF Bromine Exhaust
0841 | UNT Student Center
0842 | Chacon Autos - Retail COMCheck
0943 | FWISD BP 33
0944 | FWISD Forest Oak MS
0945 | FWISD Oaklawn ES
0946 | FWISD South Hills ES
0947 | FWISD South Hills Pre-K
0948 | Lake Worth Animal Shelter
0949 | Paramount Building Renovation
0950 | Residential Addition
0951 | Cash Store Prototype
0952 | Camp Bow Wow Duncanville
0953 | Acton Municipal Building
0954 | Landscaping Company
0955 | Progressive Packaging
0956 | Burger King
0957 | McKinney MOB
0958 | FWPL Library Assessment
0959 | Popeye's Waxahachie
0960 | Hickory Creek Animal Shelter
0961 | White Settlement Gas Station
0962 | DCCCD 2009-2010
1061 | Most Blessed Sacrament Catholic Church
1062 | Calvary Bible Church
1063 | Water Wizard
1064 | MHMR
1065 | Motorola FW Relocation
1066 | FWISD BP58
1067 | Cityville Oak Park Restaurant
1068 | Minot AFB Popeyes
1069 | R.D. Evans Community Center
1070 | DV8 Salon
1071 | UNT-B131
1072 | C C Worth Heights - Grease Trap
1073 | C C Como - Grease Trap
1074 | C C Tri Ethnic - Grease Trap
1075 | Fort Worth Dental Clinic
1076 | UNT Concert Hall Review
1077 | Preston Park Church
1078 | FWISD Sunrise-McMillan ES
1079 | DCCCD NLC Scoreboard
1080 | Dallas Office Tenant Finishout
1081 | FWISD - BP24 ASA C
1082 | FW - 3000 Bolt St Generator
1083 | COFW - Fire Station 3
1084 | COFW - Fire Station 7
1085 | COFW - Fire Station 12
1086 | COFW - Fire Station 23
1087 | COFW - GUINN Complex
1088 | COFW - Meacham Housing
1089 | UNT Dallas - Alterations
1090 | FWISD-BP33-ASA A
1091 | FWISD-BP24-ASA D (Gym)
1092 | COFW - Convention Center Mtg Room Renovations
1093 | FWISD - BP60
1094 | UNT Warehouse
1095 | COFW-Elevators
1096 | FWISD-Sunrise Auditorium
1097 | COFW-Alliance Tower
1098 | Greenville Animal Shelter
1099 | Arlington Warehouse
1100 | Dunbar HS Field House
1101 | FWISD BP33- FO Admin ASA
1102 | Primeria Baptist Church
1103 | Morris Wayne Garrett Community Center
1104 | FW Animal Control
1105 | James Ave Fire Pump Test Station
1106 | Brennan Impound Renovations
1107 | Del Taco Restaurants
1108 | UNT ACES
1109 | Christ Chapel Bible Church
1110 | Renaissance Square
1111 | Orange Leaf Louetta
1112 | Orange Leaf Parkway
1113 | FWISD BP33- SH HVAC
1114 | COFW- Fire Station 15
1115 | TCC Master Plan
1116 | COFW Police Horse Barn
1117 | Heritage Baptist Church
1118 | TCC Meacham Airport Hangar
1119 | Las Vegas New Horse/K9 Facility
1120 | Popeye's Mesquite
1121 | Orange Leaf Klein
1122 | BP24 - Poly - Washer and Dryer
1123 | AA Meacham Offices
1124 | 1850 Airfield
1125 | Building 5E
1126 | Solid Waste 1400 Columbus Trail
1127 | Family Dollar
1128 | Stoll Neurodiagnostics
1129 | Soil Lab Stoves
1130 | Public Safety Building 5th Floor
1131 | Lake Worth City Hall
1132 | Orange Leaf Kingwood
1133 | UNT Lab
1134 | Arlington Library Remodel
1135 | Hilton Houston
1136 | Home2 Hotel Austin
1137 | Jiffy Trip
1138 | BP33 South Hills New Outlets
1139 | Hammon Public School
1140 | Aeroterm Mail Sort Conversion Building A
1141 | Cottonwood Clinic
1142 | Pizza Restaurant
1143 | Jasco
1144 | Top That Pizza
1145 | COFW - Fire Station 6
1146 | Go Frac
1147 | Travis Avenue Baptist Church
1148 | City of Crowley
1149 | JPS Medical Home
1150 | COFW - IDIQ
1151 | San Mateo Mission
1152 | Mansfield Code Surveys
1153 | COFW WRMC Garage Offices
1154 | Eagle-Mountain SOQ
1155 | UNT Discovery Park - F102E
1156 | Aeroterm Building B
1157 | Aeroterm CAE
1158 | Water Treatment Service Center
1159 | Discovery Park C136
1160 | Moncrieff Concessions
1161 | Dollar General Mansfield
1162 | Aeroterm AG
1163 | Convention Center Cafe
1164 | UNT Dallas Information Booth
1165 | UNT Dallas Booth - CMA
1166 | Crowley PW Generator
1167 | Texas Urology
1168 | Flower Mound Women's Health
1169 | Flower Mound River Walk Building 101
1170 | Flower Mound River Walk Building 105
1171 | COFW Visitor's Center
1172 | Wylie Labs
1173 | FWISD RFP
1174 | Edmond Body Shop
1175 | JLL Grocery Distribution
1176 | Watagua Pavillion
1177 | Watagua Concessions
1178 | Watagua Community Center
1179 | FWISD Eastern Hills HS
1180 | Brandao
1181 | Zaza Hotel Ballroom Addition
1182 | ZaZa Hotel Thomas St
1183 | PECOFacet Research Center
1184 | Mansfield Medical Office Building
1185 | Mansfield Medical Office Building
1186 | Northern Hills Elementary
1187 | Korean Church
1188 | Sulphur Pocket at Gateway Park
1189 | Starr Conspiracy
1190 | Granbury Dental Office
1191 | 908 Monroe
1192 | Flower Mound MOB
1193 | 2850 Crestline Annex Building Service Bay Renovations
1194 | Forest Park Pool
1195 | Spinks Airport Warehouse
1196 | Bolt Street Renovations
1197 | Renfro Foods
1198 | Dunbar Community Center
1199 | Rudy's Tortillas
1200 | Greenville Auditorium
1201 | Nutrishop - Alliance
1202 | Reed V Twins
1203 | CMA Plan Review
1204 | Watagua Restrooms
1205 | Godley Office Building
1206 | COFW Animal Control Facility
1207 | Sr Citizen Elevator
1208 | Dralco Systems
1209 | Equipment Services at Holly
1210 | Cedar Hill MOB
1211 | UNT HSC Library
1212 | Japanese Gardens
1213 | Euless Boiler Room
1214 | Houston Street Shell
1215 | Agra Public Schools
1216 | Garland DO
1217 | Russom Ranch Pump Station
1218 | Melissa Scale House
1219 | Bolt Street Fire Department Kitchen
1220 | SW Nature Preserve
1221 | Castle Creek Pet Resort
1222 | Farmers Bank and Trust
1223 | JPS Renal Dialysis Unit
1224 | Elements Office (DNJ 6th Ave Investments)
1225 | Jiffy Trip Cherokee
1226 | Apache Corporation
1227 | Dralco Systems - PA Building
1228 | Frisco Concession Stand
1229 | McKinney Mexican Restaurant
1230 | Murphy Animal Shelter
1231 | Jasco Products
1232 | CenturyLink Call Center
1233 | Convention Center SE Doors
1234 | XpressWellness Enid
1235 | XpressWellness Elk City
1236 | Calumet HS
1237 | ESD Holly Vehicle Damage
1238 | Hometown Postal
1239 | 2900 Hulen COMCheck
1240 | JPS Remodel
1241 | Koinonia Church Remodel
1242 | La Moderna Pasta Plant
1243 | UNT GAB 529+535
1244 | Speed of Light
1245 | Courtyard Pfluggerville
1246 | Argyle Showroom
1247 | Lewisville Warehouse
1248 | Renfro Mezannine
1249 | Dallas Church Gym
1250 | Keller Physical Therapy Bldg
1251 | Rental One
1252 | JPS Digital Media
1253 | Tuesday Monrning HVAC
1254 | Mid America Office Building
1255 | 2400 Circle Dr
1256 | MCMC HQ Lighting Design
1257 | 502 Grand Ave
1258 | Marine Creek Church
1259 | McLendon City Hall
1260 | Renaissance Square Lot 8
1261 | Binswanger Glass Co
1262 | AG Texas
1263 | Mellow Mushroom Restaurant
1264 | UNT Restroom Renovation
1265 | UNT Sage Hall Coffee Shop
1266 | Church of Fort Worth
1267 | JPS 710 W Leuda
1268 | Creekside Lift Station
1269 | Dallas Credit Union
1270 | Dallas Retail Space
1271 | UNT Chestnut 160
1272 | KXAS Building Remodel
1273 | Community Christian School
1274 | Keller Community Theater
1275 | Tarrant County Correctional Facilities
1276 | JL Reed Restroom addition
1277 | Building # 615
1278 | JPS Corridor
1279 | Klein Tools Expansion
1280 | Carroll Apartment Building
1281 | Texas Family Fitness
1282 | BlueLinx Dust Collector
1283 | Midlothian Multi-Housing
1284 | Providence Bank
1285 | NRH MOB
1286 | Nosredna Catering Kitchen
1287 | Wilks Community Center
1288 | ZaZa Ballroom Addition
1289 | Christ Community
1290 | 81 Ranch
1291 | Physical Therapy Building
1292 | Paradise Methodist Church
1293 | Celeris (2014)
1294 | USPS Dallas PDC
1295 | Small Retail Space
1296 | BHB Plumbing Project
1297 | Mansfield Pharmacy
1298 | Glade Parks
1299 | Arbors Nursing Home
1300 | Amcor
1301 | 777 Main St - Trinity River
1302 | Sacred Heart of Jesus
1303 | Arlington Highlands
1304 | Century Link UPS
1305 | Pioneer Chile Co
1306 | Xpress Wellness Shawnee
1307 | Dallas Airmotive Mezzanine
1308 | Dallas Airmotive Warehouse
1309 | Frisco Office Building
1310 | Wisdom Center
1311 | Brandao
1312 | Parks Coffee
1313 | Panaderia Denton
1314 | Wackenhut
1315 | Xpress Wellness Weatherford
1316 | The Joint Corporate Office
1317 | Joyce Dr PD Station
1318 | Memory Care Building
1319 | Accupunturist Office Flower Mound
1320 | Lucy's Bakery
1321 | Aspermont MOB
1322 | Calumet HS Electrical Service
1323 | First American Title
1324 | Burleson Bartlett Park
1325 | Houston Apts
1326 | Brennan Swap Shop
1327 | Lucky's Warehouse
1328 | Mansfield Industrial Facility
1329 | Xpress Wellness Muskogee
1330 | Calumet Barn
1331 | Plano BBQ Nation
1332 | Grapevine Finishout
1333 | Waxahachie Shell
1334 | Mellow Mushroom Iowa
1335 | Fossil Rim Store
1336 | Flowermound Clinic
1337 | Timberline Office Building
1338 | Proctor Apartment Buildings
1339 | Xpress Wellness Woodward
1340 | JPS TSP Upgrades
1341 | Weather Radar
1342 | Patriot Paws
1343 | Community at Lake Ridge Mansfield
1344 | UNT Woodhill
1345 | 3611 Swiss
1346 | Tilt-wall Building
1347 | W.R Meadows Warehouse
1348 | Chisholm Trail Community Center
1349 | 1228 Glenn Park
1350 | Mineral Wells Warehouse
1351 | Net Auto Sales
1352 | Time Warner Data Center
1353 | Southridge Animal Hospital
1354 | Fox Conn
1355 | 3102 West Division St
1356 | Mountain View Shopping Ctr - ULTA
1357 | Reese DO
1358 | Wylie Railroad
1359 | Rockwall Church
1360 | Fire Station # 23 RR
1361 | Fire Station # 16 RR
1362 | Fire Station # 28 RR
1363 | Precinct Ridge MOBs
1364 | Xpress Wellness Sapulpa
1365 | Carrollton Central Services Center
1366 | OK Indian Clinic
1367 | Mansfield MOBs
1368 | Eckerd Lazy River
1369 | Nissan River Oaks Auction House
1370 | Hurst One Retail Center
1371 | Electra ISD
1372 | 2944 S Grove St
1373 | 777 Main St - Transwestern
1374 | 2900 Alta Mere
1375 | Mansfield Flex Building
1376 | Brentonwood Stair Remodel
1377 | Eufaula HVAC
1378 | Henderson Dentist Office
1379 | 2001 Coit Rd
1380 | Tom's Daiquiri Bar
1381 | Xpress Wellness Lawton
1382 | JPS Cancer Center Remodel
1383 | Bibb Engineers
1384 | Horizon ER
1385 | Log Cabin Village Restrooms
1386 | Xpress Wellness Prototype
1387 | Cooper Companies
1388 | Oak Hill Restaurant
1389 | New Apt Building in Denton
1390 | CenturyLink 3rd Floor CR
1391 | Rudy's Tortillas Consultation
1392 | UNT Clark Bakery
1393 | JPS ER X-Ray Replacement
1394 | UNT Bruce Hall
1395 | Marine Creek Classroom Addition
1396 | Mellow Mushroom Austin
1397 | Mellow Mushroom Round Rock
1398 | Elite Wireless Office
1399 | Celeris (2015)
1400 | Calumet Elementary
1401 | CenturyLink 1st Floor
1402 | 60 Village Lane
1403 | Koinonia Church CAD
1404 | Center of Hope
1405 | Werner
1406 | Xpress Wellness Lawrence
1407 | Fire Station # 23 RR
1408 | Anadarko Police Dept
1409 | Sovereign Pharma Vaults
1410 | Just Cut It Keller
1411 | Advanced Auto
1412 | Edmond School Shelter
1413 | JPS Doctor Work Spaces
1414 | COFW Grease Traps
1415 | Mansfield Fieldhouse
1416 | DCCCD Eastfield Generator
1417 | Eufaula Football Lighting
1418 | Eufaula Kitchen Remodel
1419 | Eufaula VoAg Buildings
1420 | Eufaula Elementary Gym
1421 | KXAS Remodel
1422 | Fort Worth MOB Shell
1423 | COFW Grease Trap Southside
1424 | COFW Grease Trap MLK
1425 | Eufaula HS HVAC
1426 | JPS Waiver Offices
1427 | Torchy's Tacos Plan Review
1428 | White Settlement Building
1429 | Fort Worth MOB Shells
1430 | Mellow Mushroom Kentucky
1431 | Southlake Tenant Improvement
1432 | Frank Kent Office Remodel
1433 | Frank Kent Wine Restaurant
1434 | JPS 3rd Floor Storage
1435 | Metroplex Family Church
1436 | Dr Rameau DO
1437 | The Joint Southlake
1438 | Animal Eye Clinic
1439 | Temple Schools Football Bldg
1440 | 1015 Belknap
1441 | 900 Industrial, Henderson
1442 | Dr Everett DO
1443 | Bailey Lake Park
1444 | Escape Southlake
1445 | Botox Clinic
1446 | 101 River Oaks, Southlake
1447 | Mellow Mushroom Houston
1448 | JPS Geriatric
1449 | MOB Shell-Arlington
1450 | Averitt Express
1451 | The Door Church
1452 | Tuscany Warehouse
1453 | Stephenville MOB
1454 | Xpress Wellness Andover
1455 | Woodland Heights Baptist Church
1456 | Dralco PA SWN Analyzer
1457 | Xpress Wellness - Shopping Center
1458 | Suite 245
1459 | Fitness Connection
1460 | TAMU Office Expansion
1461 | Botanic Gardens
1462 | The Joint Richardson
1463 | J&E Masonry Office
1464 | The Juice Bar
1465 | 81 Ranch Parking
1466 | Cleveland OK HVAC
1467 | Eufaula HVAC Consultation
1468 | Vista Gardens
1469 | Dralco - Runge TX
1470 | Forney Medical (SNEH)
1471 | JPS Toilet
1472 | DCCCD SOQ
1473 | Rise Phase 2
1474 | Malawi's Pizza
1475 | Century Link Restrooms
1476 | EPB 2015
1477 | Eugene McCray Recreation Center
1478 | Handley Meadowbrook Rec Center
1479 | Keller Parkway Office
1480 | Duke Schools Bond Program
1481 | The Joint Mansfield
1482 | Range Resources
1483 | Westchester Place
1484 | Low T - Her Kare
1485 | Cook Children's Genetic Clinic
1486 | Xpress Prototype Proposal
1487 | Pattonair
1488 | Dry Cleaner
1489 | Bakery
1490 | KLA drawing Review
1491 | Xpress Wellness Chickasha
1492 | Little York Oil Change
1493 | Calumet Phase 3
1494 | Celina Pool
1495 | UNT Child Development. Lab
1496 | Austin Hotel
1497 | Grand Prairie Church
1498 | Dallas Sign Project
1499 | Anytime Fitness
1500 | Rhome Insdustrial Facility
1501 | Kimbell East Parking
1502 | The Joint Las Colinas
1503 | Creative Soul Music School
1504 | Blackwood Development
1505 | Luna Restaurant
1506 | Rojas Kitchen
1507 | Beth Maries
1508 | Page Office Finishout
1509 | Nolen Drive Restaurant
1510 | Residential MOB
1511 | Celeris (2016)
1512 | Duke HVAC Replacement
1513 | Dralco - Enlink NNG
1514 | Greg Wright DO
1515 | Fort Stockton RV Park
1516 | Hair Stars Salon
1517 | Ventamatic
1518 | Fredericksburg AS
1519 | Werner Trucking - El Paso
1520 | Sisk Hangar
1521 | St Laurence Episcopal Church
1522 | Weatherford Public Library
1523 | Convention Center OH Door
1524 | McKinney MOB
1525 | Stomp Music Studios
1526 | MTSI Corp Expansion
1527 | Serendipity SPA
1528 | Mansfield Office
1529 | Texas Back Institute # 306
1530 | Brennan Drop-off Changes
1531 | MLK Drop-off Changes
1532 | Old Hemphill Drop-off Changes
1533 | Malawi's Virginia
1534 | FW Municipal Courts Building
1535 | Cornerstone Baptist Church
1536 | Edmond Christian Church
1537 | Quorum Office Remodel
1538 | UNT Coliseum Concourse
1539 | FW Retail + Shell
1540 | The Joint - Rowlett
1541 | Rudy's New Equipment
1542 | City Hall Tunnel Renovation
1543 | Crown Enterprises
1544 | The Community At Lake Ridge
1545 | Village Creek
1546 | Mont Belvieu
1547 | New Restaurant
1548 | Precision Hayes
1549 | Lapage Salon
1550 | National Bus Sales
1551 | Central Library - RR renovation
1552 | 629 Spaceway
1553 | Stephenville MOB Expansion
1554 | City of Arlington Pump Building
1555 | Low-T Her Kare Arlington
1556 | Houston Sites
1557 | Othello's Parking Lot
1558 | Harlingen TX Retail building
1559 | Southlake MOB Shell
1560 | Lasertron
1561 | RPM-Lockhart
1562 | Shell Station
1563 | COFW Brennan Body Shop
1564 | Just Cut It Fort Worth
1565 | JPS CT Replacement
1566 | Cross Timbers Church Remodel
1567 | Acupuncture Building - Keller
1568 | Putnam HS
1569 | International Hydraulics
1570 | Forney MOB Tenant Improvement
1571 | Airco Expansion
1572 | 350 Belknap
1573 | Arlington Catering
1574 | Denton Apts
1575 | North Fort Worth Warehouse
1576 | Dirt Cheap
1577 | WRMC Sales Center
1578 | WRMC Street Lighting
1579 | 1020 Explorer Drive
1580 | Rental One - Denton
1581 | Crescent Schools
1582 | Northern Hills Elementary Safe Room
1583 | 7 City Church
1584 | Ambassador Aviation
1585 | Talbot MOB
1586 | 204W Oak Denton Salon
1587 | Rental One Willow Park
1588 | Montex Hangar
1589 | Denton Municipal Hangar
1590 | Prairie Plaza
1591 | JPS 3rd Floor OR Renovation
1592 | Deer Park Animal Shelter
1593 | Richie Bros Auctioneers
1594 | Pflugerville AS
1595 | Organic Mattresses
1596 | Cerebrum
1597 | North Service Center Sign
1598 | Austin Hotel Bar
1599 | Breakout Games
1600 | Gun Experience
1601 | Beach and Thompson Shell
1602 | Shipleys Donuts
1603 | Virtual Packaging
1604 | Botanic Garden Assessment
1605 | The Joint - North Richland Hills
1606 | Tindall Storage Building
1607 | Optometrist Office
1608 | Unifirst
1609 | Arlington Heights Attorney's Office
1610 | UNT HSC Child Care
1611 | Riverside Gallery
1612 | Frisco Shell
1613 | Norman Hotel
1614 | Euless Library
1615 | Celeris (2017)
1616 | Grand Prairie Building Assessment
1617 | Werner Enterprises Laredo
1618 | Townhouse Office
1619 | Optic Kleer
1620 | City of Weatherford Service Center
1621 | The Creek Church Phase II
1622 | Bronson Rock RR Renovation
1623 | Phenix Salon Suites
1624 | Fuego de Dios Church
1625 | Bentley's Restaurant Patio
1626 | Bentley's Bryant Inving
1627 | Blo Blow Dry Bar
1628 | Machine House
1629 | Heritage Glenn MOB Shell
1630 | Low Key Pokie
1631 | Brown Street Church Addition
1632 | Upper Trinity Conservation
1633 | Car Customizing Co. Event Center
1634 | Dalrock Crossing
1635 | Camp Bow Wow
1636 | Living Waters Worship Center
1637 | Mercy Clinic
1638 | 1121 Parker Suite 200
1639 | 1121 Parker Suite 206
1640 | Joyce Dr Changes
1641 | TCBY Irving
1642 | Lewisville MOB
1643 | Pantheon Construction Haltom City
1644 | Dallas Church Gym
1645 | Watauga Church Narrative
1646 | Italian Bistro
1647 | Hope Church Addition
1648 | OWT Offices
1649 | Magnolia Per Resort
1650 | Fit and Fancy Med Spa
1651 | Nidoma Warehouse
1652 | Manufacturing Bldg additiona
1653 | Keller 2-story renovations
1654 | Mineral Wells Head Start
1655 | The Joint - Lake Highlands
1656 | Northern Hills Saferoom Addition
1657 | Cleburne SWAT
1658 | Cleanpart Hazardous Materials Room
1659 | The Joint Saginaw
1660 | 1217 8th Avenue
1661 | Othello's Restaurant
1662 | Heritage Glenn Office Park
1663 | 412 W Bolt St
1664 | Pool Corporation Warehouse Building
1665 | Civil Constructors
1666 | The Joint - Glade Parks
1667 | Modern Acupunture - Plano
1668 | Johnson Equipment
1669 | Sleep In Hotel
1670 | Brookhaven Generator
1671 | CE DFW Conference Room
1672 | FBC Watauga - Phase 1
1673 | 3330 Matlock Pizzeria
1674 | The Dove Church in Southlake
1675 | Cornerstone Church Rowlett
1676 | National Indoor RV Building
1677 | Kansas City Railroad Mexico
1678 | The Joint - Timberland
1679 | New Yoga Studio
1680 | ATP Arlington Hangar
1681 | McKinney Office Building
1682 | Clarus Interior Renovation
1683 | Weatherford RR Remodel
1684 | Angelina's Restaurant
1685 | Norman Hotel Evaluation
1686 | Ludelle Warehouse Narrative
1687 | Crowley MOB
1688 | Parkwood Cycling Center
1689 | Jasco Security Gate
1690 | Low T Her Kare Fort Worth
1691 | Sushi Restaurant Dallas
1692 | Celeris (2018)
1693 | The Table Church
1694 | Event Venue in Carrollton
1695 | Cotton Gin Project
1696 | EPIROC Headquarters
1697 | Moss Insurance Office Addition
1698 | Modern Acupunture - Houston
1699 | RV Sales Office - Hurst
1700 | T Top Metal Fabrication
1701 | Celeris New Office
1702 | 3-story Office Building-Fort Worth
1703 | Aledo Retail
1704 | Knights Inn Willow Park
1705 | North Fort Worth Baptist Church
1706 | The Joint Windsong Ranch
1707 | Ryan Schools
1708 | Velma Schools
1709 | Koinonia Church New Offices
1710 | Jasco Office Addition
1711 | Funky Town Donut Shop
1712 | 6ksf New Restaurant
1713 | Xpress Wellness new layout
1714 | Dickies Retail Renovation
1715 | Modern Acupuncture - Kingwood
1716 | Humane Society Animal Shelter
1717 | Greenbriar CC Reception Desk
1718 | Cantilivered Restaurant
1719 | Grand Prairie Warehouse Additions
1720 | GAF Renovations
1721 | Granite Schools
1722 | Low T Heritage Glenn
1723 | Atlas Vein Clinic
1724 | TDC Parking Phase 1
1725 | Camacho UPV Office
1726 | Lana's New Project
1727 | Moss Public Schools
1728 | The Joint - Park Forest
1729 | Angel Montisory
1730 | The Joint - Edmond OK
1731 | Church at the Crossings
1732 | City of Lake Worth Projects
1733 | Nekter
1734 | The Joint - Quail Springs
1735 | Staybridge Hotel
1736 | Varsity Orthopedics at Heritage Glen
1737 | The Joint - Champions Park
1738 | Rudys Power Monitor
1739 | Moss Schools Concessions
1740 | Hill Residence
1741 | Baytown Cabin
1742 | City of Fort Worth Water Conservation Renovations
1743 | Southlake MOB Photometrics
1744 | Viandant Gelato Store - Denton
1745 | Mellow Mushroom Round Rock Electrical Diagnostics
1746 | Xpress Wellness Liberal KS
1747 | TCAL CAD Release
1748 | Modern Acupuncture Las Colinas
1749 | Dove Church Remodel
1750 | HG Finishout
1751 | District 90 Salon
1752 | Parkwood Hill Addition
1753 | Modern Acupuncture Alliance
1754 | Viandant Gelato Store - Gainsville
1755 | Decatur MOB
1756 | Brazilian Joes
1757 | Blo Blow Dry Bar - Preston Village
1758 | The Joint - Amarillo
1759 | KHSH-Keller-Haslet Restaurant Shell
1760 | Church at Walnut Square
1761 | 130K SF Warehouse
1762 | Stonebridge MOB Shells
1763 | Long Prairie Road MOB Shell
1764 | FWTA Body Shop Addition
1765 | Xpress Wellness Altus OK
1766 | Xpress Wellness Duncan OK
1767 | FW Forest Park Pool Shed
1768 | NRGV Volleyball Facility Mansfield
1769 | Coolgreens Restaurant
1770 | Lake Dallas Project
1771 | Argyle Public Works
1772 | COFW North Tri-Ethnic CC TAS
1773 | COFW Worth Heights Multi-purpose TAS
1774 | FWPL East Branch Restroom Renovations
1775 | The Joint Norman OK
1776 | ECC Eitz Chaim Church
1777 | BALKO Cafeteria Changes
1778 | HGOS Heritage Glenn Oral Surgery
1779 | MEL5K Melissa 5.3K SF Shell
1780 | MEL7K Melissa 7.4K SF Shell
1781 | GRACE Revolution
1782 | AETIO Biotherapy
1783 | CLEBRV Cleburne RV
1784 | ITPWR DCCCD IT Closet Upgrades
1785 | RCIT Richland College IT Closets
1786 | OFF Office Addition
1787 | MANS Mansfield Shell
1788 | HONDA Denton
1789 | TJTR - The Joint Timber Ridge
1790 | TJPP - The Joint Pinnacle Park
1791 | RIGHT - Righteous Food
1792 | CELERIS - Celeris (2019)
1793 | VERDEN - Verden Schools Elec Upgrade
1794 | FREEFORM - Freeform Chiropractic
1795 | CURTIS - Curtis Drive Warehouses
1796 | IAGULLI - Castle NRH MOB
1797 | FWLAB - Tactical Center Lab Renovations
1798 | OAK-Oak Knoll Office
1799 | NEKARB - Nekter Arboretum
1800 | SALON - Lana's Hair Salon
1801 | HOU -- Univ of Houston Transmitter
1802 | Lana's 7500 SF Shell
1803 | Mesquite Bakery
1804 | HIGHLAND - Office Bldg and Shell
1805 | TJMID - The Joint Midland
1806 | XWGUT - Xpress Wellness Guthrie OK
1807 | WCG - Weatherford Church of God Office Building
1808 | PCN-Putnam City North HS
1809 | XWARD-Xpress Wellness Ardmore OK
1810 | XWGUY-Xpress Wellness Guymon OK
1811 | XWDGE-Xpress Wellness Dodge City OK
1812 | XWGB-Xpress Wellness Great Bend OK
1813 | KODAK
1814 | MRGUN-Gun Range
1815 | TJME-The Joint Market East Mesquite
1816 | MOON - Summer Moon Coffee Shop
1817 | DCSG - Dickie Carr Sand & Gravel
1818 | FWPL-FW Public Library Assessment
1819 | DHHS - Weatherford
1820 | MATA - DISD Mata ES Swing Space
1821 | AGRA - Agra Hitting Building
1822 | ROANOKE - Gun Range
1823 | 360CW-360 Commerce Warehouse
1824 | CYL - Sauna Studio
1825 | NWCC - North West Church of Christ
1826 | RI - Resource Industries
1827 | 360CO-360 Commerce Office
1828 | NUVO-Desk Project
1829 | CALHB-Calumet Hitting Building
1830 | LWPW-Lake Worth Public Works
1831 | 1217-8TH-Funkytown Redevelopment
1832 | TCEC-Munday
1833 | GS-Goose and Stinky
1834 | TEMPLE - Temple High School
1835 | JUMBO Hills Warehouse
1836 | FFB First Financial Bank
1837 | DRALCO
1838 | THURMAN - Camp Thurman
1839 | HUNT - Hunt Regional Cardiovascular
1840 | SUPERIOR - Livestock Auction
1841 | TJCH - The Joint Cedar Hill
1842 | KSMY - KidsStrong McKinney
1843 | AIM-Artistry In Motion
1844 | BLKELEM Balko Elementary
1845 | PADEN Schools
1846 | BCFPE-Brookhaven College Switchgear
1847 | TJGP-The Joint Grand Prairie
1848 | FRS- Forney Retail Shell
1849 | HEMP - Hemphill St Church
1850 | CFWC - Calvary Family Worship Center
1851 | SGCM-Sovereign Grace Church Midland
1852 | AFCC-Armed Forces Career Center
1853 | TJMP-The Joint Montgomery Plaza
1854 | TJMK - The Joint McKinney
1855 | KECO Lab
1856
1857 | SUMMIT-Summit Middle Schools
1858 | GP-Glamour Paws
1859 | GARDEN-Garden Park Apartments
1860 | TURPIN-Turpin Schools
1861 | SERVE-Serve Denton
1862 | TWUBUS-TWU Bus Stop
1863 | TWU-Locust Office Renovation
1864 | AKP-Amazing Kids Pediatric
1865 | FC-Fort Capital Addison
1866 | WLM-WL McNatt
1867 | UCO-UCO Test Engine
1868 | HULEN Park Place Office
1869 | FMSHELL - Flowermound Office Shell
1870 | MEL2 - Melissa Lot # 2
1871 | LO-Lewusville Office
1872 | PV-Park Ventura
1873 | AAC - Argyle Activity Center
1874
1875
1876
1877
1878
1879
1880
1881
1882
1883
1884
1885
1886
1887
1888
1889
1890
1891
1892
1893